## Dashboard
🔗 Open Interactive Dashboard
Keep this file and budget_dashboard.html in the same folder.

## Category Table
CVR Month: | May, 2026
|  | SU | OC | MA | SU | OC | MA | SU | OC | MA | SU | OC | MA | SU | OC | MA | SU | OC | MA | SU | OC | MA | SU | OC | MA | SU | OC | MA | SU | OC | MA | SU | OC | MA |  |  |  | SU | OC | MA | SU | OC | MA
Cost Code | Item | Subcontracts CVR Actual Cost | Supplies CVR Actual Cost | Material CVR Actual Cost | Subcontracts CVR FC | Supplies CVR FC | Material CVR FC | Subcontracts CVR Accruals | Supplies CVR Accruals | Material CVR Accruals | Subcontracts CVR Out PO's | Supplies CVR Out PO's | Material CVR Out PO's | Subcontracts CVR EAC | Supplies CVR EAC | Material CVR EAC | Subcontracts PO Log Amount | Supplies PO Log Amount | Material PO Log Amount | Subcontracts Accrued Costs | Supplies Accrued Costs | Material Accrued Costs | Subcontracts Comms Actuals | Supplies Comms Actuals | Material Comms Actuals | Subcontracts Committed | Supplies Committed | Material Committed | Subcontracts Total Comms JTD Cost | Supplies Total Comms JTD Cost | Material Total Comms JTD Cost | Subcontracts CTD | Supplies CTD | Material CTD | Subcontracts Manual Adjustment | Supplies Manual Adjustment | Material Manual Adjustment | Subcontracts Rem EAC | Supplies Rem EAC | Material Rem EAC | Subcontracts Over/Under | Supplies Over/Under | Material Over/Under
0-4000 | 0-4000-Mobilization | 0 | 38865 | 0 | 178048.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4001 | 0-4001-Demobilization | 0 | 2350 | 0 | 220300.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4004-01 | 0-4004-01 Racking Materials | 0 | 1035502.42 | 9355889.1 |  |  | -8395820.01 | 0 | 0 | 0 | 0 | 11408138.22 | 24924070.87
0-4004-02 | 0-4004-02 Inverter Materials | 0 | 0 | 4983660 | -350000 |  | -4812801.78 | 0 | 0 | 0 | 0 | 0 | 16959929.76
0-4004-04 | 0-4004-04 HV Breakers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4004-05 | 0-4004-05 PV Power Cable Materi | 0 | 0 | 4497552.64 | 1264434.05 | -385787.98 |  | 0 | 0 | 21748.27 | 0 | 1033828.47 | 14990593.76
0-4004-06 | 0-4004-06 Cable Management | 0 | 0 | 0 | 0 | 0 | 1624883.96 | 0 | 0 | 0 | 0 | 0 | 0
0-4004-07 | 0-4004-07 Scada | 0 | 0 | 0 | 138740 | 0 | 1848766.26 | 0 | 0 | 0 | 0 | 0 | 0
0-4004-08 | 0-4004-08 PV Harness & LBDs | 0 | 0 | 0 | 0 | 0 | 11679119.26 | 0 | 0 | 0 | 0 | 0 | 0
0-4004-10 | 0-4004-10 PV Electrical Materia | 0 | 123.43 | 34204.68 | 0 | -132692.59 | 2032532.16 | 0 | 10.4 | 2127.89 | 0 | 0 | 4.0927e-12
0-4004-12 | 0-4004-12 Non Tracker Piles | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 212948.61 | 754485.45
0-4004-13 | 0-4004-13 CenterPoint's Breaker | 0 | 0 | 0 | 0 | 0 | -33000 | 0 | 0 | 0 | 0 | 0 | 333000
0-4005 | 0-4005-FOE | 0 | 20433.51 | 0 | 0 | 3435.3685 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4005-02 | 0-4005-02 Commish FOE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4006 | 0-4006-Yard and Trailer | 0 | 35420.42 | 0 | 76535.4465 |  | 0 | 0 | 0 | 0 | 0 | 277325.56 | 0
0-4007 | 0-4007-Mowing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4008 | 0-4008-Supplies | 0 | 108788 | 0 | 0 | 2245561.25 | 0 | 0 | 10749.05 | 0 | 0 | 60149.43 | 0
0-4010 | 0-4010-FOG | 0 | 42925.37 | 0 | 0 | 1855762.86 | 0 | 0 | -63562.62 | 0 | 0 | 0 | 0
0-4013 | 0-4013-Contingency | 0 | 0 | 0 | 4883701.58 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4013-01 | 0-4013-01-LD's | 0 | 0 | 0 | 1800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4013-02 | 0-4013-02-Weather Cont. | 0 | 0 | 0 | 1386220.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4015 | 0-4015-Survey | 28288.75 | 956.01 | 325.83 | 466368.3015 | -144949.5389 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4016 | 0-4016-Permits | 20024.36 | 0 | 0 | 0 | 0 | 36554.39 | 0 | 0 | 0 | 43421.25 | 0 | 0
0-4017 | 0-4017-Utility Locate | 0 | 849.86 | 0 | 2821.59 | 0 | 0 | 0 | 0 | 0 | 0 | 21328.55 | 0
0-4024 | 0-4024-Engineering | 1128965.04 | 28340.55 | 0 | 1419040.4 | 0 | 0 | 0 | 0 | 0 | 223654.01 | 0 | 0
0-4029 | 0-4029-ACS | 0 | 0 | 0 | 1680000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4031 | 0-4031-Hire-In and Orientation | 0 | 1549.5 | 0 | 0 | 544.2454 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4115 | 0-4115-Clean Up | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4300 | 0-4300-Mechanical Receiving | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4301 | 0-4301-Pile Layout | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4302 | 0-4302-Pile Installs | 0 | 0 | 0 | 0 | 0 | 114488.16 | 0 | 0 | 0 | 0 | 0 | 0
0-4303 | 0-4303-Pile QAQC | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4304 | 0-4304-Racking Layout | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4305 | 0-4305-Racking Install | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4306 | 0-4306-Racking QAQC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4307 | 0-4307-Modules Layout | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4308 | 0-4308-Modules Install | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4309 | 0-4309-Modules QAQC | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4320 | 0-4320-Mechanical Punch List | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4400 | 0-4400-Electrical Receiving | 0 | 0 | 0 | 0 | 389.5113 | 32475 | 0 | 0 | 0 | 0 | 0 | 0
0-4401 | 0-4401-DC Trenching & Boring | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4402 | 0-4402-Transitions Pre-Fab | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4403 | 0-4403-DC Transitions Install | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4405 | 0-4405-DC Homerun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4407 | 0-4407-Module Wiring | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4408 | 0-4408-Harness Install | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4410 | 0-4410-DC Terminations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4411 | 0-4411-LDB Install | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4412 | 0-4412-CAB System Install | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4413 | 0-4413-DC Testing | 0 | 0 | 0 | 0 | 0 | 59537.5 | 0 | 0 | 0 | 0 | 0 | 0
0-4414 | 0-4414- Commisioning | 0 | 0 | 0 | 0 | 3621.9884 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4415 | 0-4415-Grounding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4416 | 0-4416-Trunk Bus System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4417 | 0-4417-MV Juntion Box | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4418 | 0-4418 - Electrical QAQC | 0 | 0 | 0 | 0 | 108.6132 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4420 | 0-4420-Electrical DC Punch List | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4500 | 0-4500-AC-MV Plowing | 0 | 0 | 0 | 0 |  | 147627.24 | 0 | 0 | 0 | 0 | 0 | 0
0-4501 | 0-4501-AC-MV Terminations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4502 | 0-4502-AC-MV Splices | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4503 | 0-4503-AC-MV Cable Tie-ins | 0 | 0 | 0 | 0 | 0 | 2877.54 | 0 | 0 | 0 | 0 | 0 | 0
0-4505 | 0-4505-AC-MV Boring | 0 | 0 | 0 | 22500 | 200836.63 | 1735000 | 0 | 0 | 0 | 0 | 0 | 0
0-4508 | 0-4508-AC-MV Trenching & BackFill | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0
0-4510 | 0-4510-AC-MV Cable Pull | 0 | 274.5 | 0 | 0 | 0 | 70000 | 0 | -304.7 | 54063.48 | 0 | 609.71 | 119487.57
0-4512 | 0-4512-AC Testing | 0 | 0 | 0 | 231000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4520 | 0-4520-Electrical MV Punch List | 0 | 0 | 0 | 0 | 8004.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4700 | 0-4700-Inv Skid Excavation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4701 | 0-4701-Inv Skid Conduit | 0 | 0 | 0 | 0 | 3096.4138 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4702 | 0-4702-Inv Skid Backfill | 0 | 0 | 0 | 0 | 0 | 59537.5 | 0 | 0 | 0 | 0 | 0 | 0
0-4703 | 0-4703-Inv Pile Caps | 0 | 0 | 0 | 0 | 0 | 8182.95 | 0 | 0 | 0 | 0 | 0 | 0
0-4704 | 0-4704-Inv Skid Setting | 0 | 0 | 0 | 95200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4000-01 | 0-4000-01-Mobilization | 0 | 0 | 0 | 66371.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4001-01 | 0-4001-01-Demobilization | 0 | 0 | 0 | 60400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4005-01 | 0-4005-01-Civil FOE | 0 | 0 | 0 | 0 | 0 | 7988.3629 | 0 | 0 | 0 | 0 | 0 | 0
0-4100 | 0-4100-Silt Fence | 0 | 48956.07 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0
0-4100-01 | 0-4100-01-Erosion Control | 0 | 24756.07 | 0 | 0 | 0 | 18278.9267 | 0 | 0 | 0 | 0 | 82.58 | 99900
0-4101 | 0-4101-Clearing & Grubbing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4102 | 0-4102-Cut&Fill | 0 | 0 | 0 | 0 | 0 | 7477.79 | 0 | 0 | 0 | 0 | 0 | 0
0-4103 | 0-4103-Drainage | 0 | 0 | 0 | 0 | 0 | 233266.3 | 0 | 0 | 0 | 0 | 0 | 0
0-4104 | 0-4104-Grading | 0 | 0 | 0 | 0 | 0 | 2165 | 0 | 0 | 0 | 0 | 0 | 0
0-4105 | 0-4105-Top Soil Stripping | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4106 | 0-4106-Top Soil Respread | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4107 | 0-4107-Seeding & Revegetation | 0 | 0 | 0 | 536369.2832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 795093
0-4108 | 0-4108-Fences & Gates | 0 | 0 | 0 | 1066260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4109 | 0-4109-Site Roadways | 0 | 0 | 0 | 0 | 0 | 1256921.05 | 0 | 0 | 0 | 0 | 0 | 1993005
0-4015-01 | 0-4015-01-Survey | 0 | 1196.88 | 0 |  | 9755.8065 | 5412.5 | 0 | 0 | 0 | 0 | -8.5265e-14 | 0
0-4110 | 0-4110-Ditches | 0 | 0 | 0 | 0 | 361.688 | 86810.01 | 0 | 0 | 0 | 0 | 0 | 0
0-4110-01 | 0-4110-01-Canal Bridge Repair | 0 | 0 | 0 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4111 | 0-4111-Compaction Testing | 0 | 0 | 0 | 166283.9969 | 0 | 0 | 0 | 0 | 0 | 0 | 55500 | 0
0-4113 | 0-4113-Construction Entrance | 0 | 0 | 0 | 0 | 0 | 114993.9729 | 0 | 0 | 0 | 0 | 0 | 0
0-4115-01 | 0-4115-01-Clean Up | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4116 | 0-4116-Bush Hog | 0 | 0 | 0 | 0 | 0 | 53177.5002 | 0 | 0 | 0 | 0 | 0 | 0
0-4121 | 0-4121-Laydown Areas | 0 | 0 | 156147.77 | 29000 | 0 | 153564.5769 | 0 | 832.5 | 1057.94 | 0 | 0 | 596875.57
0-4122 | 0-4122-Road Maintenance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4123 | 0-4123-Dust Control | 0 | 0 | 0 | 0 | 0 | 95877.2535 | 0 | 0 | 0 | 0 | 0 | 0
0-4124 | 0-4124-Dewatering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4125 | 0-4125-SWPPP Maintenance | 0 | 0 | 0 | 0 | 0 | 13345.3505 | 0 | 0 | 0 | 0 | 0 | 0
0-4128 | 0-4128-Basin Installation | 0 | 0 | 0 | 0 | 0 | 154560.43 | 0 | 0 | 0 | 0 | 0 | 0
0-4705 | 0-4705-Inverter Pads | 0 | 0 | 0 | 0 | 0 | 186821.46 | 0 | 0 | 0 | 0 | 0 | 0
2-4004 | 2-4004 Substation and T-Line | 867327 | 0 | 0 | 668815.75 | 0 | 1114000 | 0 | 0 | 0 | 9612857.25 | 0 | 0
2-4005 | 2-4005-SS FOE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2-4205 | 2-4205-SS Pad | 0 | 0 | 0 | 0 | 19492.4881 | 75000 | 0 | 0 | 0 | 0 | 0 | 477300
2-4209 | 2-4209-SS Road | 0 | 500 | 0 |  | 9613.74 | 370889.22 | 0 | 0 | 0 | 0 | 666 | 243373.05
0-4011 | 0-4011 Taxas Conptroller Taxes | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4999 | 0-4999 Job Abuse | 0 | 1035.85 | 0 | 3278.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4018 | 0-4018 Travel | 0 | 36745.18 | 0 | 13254.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4027 | 0-4027 Early Work | 0 | 2274.82 | 5745.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190.51
0-4614 | 0-4614 SCADA MET Install | 0 | 0 | 0 | 0 | 6000 | 36860.7 | 0 | 0 | 0 | 0 | 0 | 0
0-4602 | Fiber Terms | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4xyy | Risk | 0 | 0 | 0 | -2390722.7742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0-4xxy | Opps |  |  |  |  | -1220810.6278 | -1200000 | 0 | 0 | 0 | 0 | 0 | 0

## PO Log
Date | PO Number | Cost Code | Category | Amount | Description of Cost

## Committments Dump
Record Type | Cost Code | Category | ttJTrans.ponumber | CA | PO Number | Order Date | Post Date | Item | Cost Code | Description | Quantity | Current Order Value | Type | Account Number | Name | Accrued Costs | Actual Costs To Date | Committed Costs | Labor Hours
ttJTrans | 0-4000 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4000 | HT060 2020 PETERBILT 389 SLEEPER 2020 PETERBILT 389 SLEEPER | 0 | 0 |  | HT060 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4000 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4000 | HT060 2020 PETERBILT 389 SLEEPER 2020 PETERBILT 389 SLEEPER | 0 | 0 |  | HT060 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4000 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4000 | HT060 2020 PETERBILT 389 SLEEPER 2020 PETERBILT 389 SLEEPER | 0 | 0 |  | HT060 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4000 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4000 | HT060 2020 PETERBILT 389 SLEEPER 2020 PETERBILT 389 SLEEPER | 0 | 0 |  | HT060 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4000 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4000 | HT064 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | HT064 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4000 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4000 | HT064 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | HT064 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4000 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4000 | HT064 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | HT064 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4000 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4000 | HT064 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | HT064 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4000 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4000 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4000 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4000 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4000 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4000 | TR407 2020 48' KALYN SIEBERT DROP DECK TRAILER 2020 48' KALYN SIEBERT DROP DECK TRAILER | 0 | 0 |  | TR407 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4000 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4000 | TR407 2020 48' KALYN SIEBERT DROP DECK TRAILER 2020 48' KALYN SIEBERT DROP DECK TRAILER | 0 | 0 |  | TR407 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4000 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4000 | TR407 2020 48' KALYN SIEBERT DROP DECK TRAILER 2020 48' KALYN SIEBERT DROP DECK TRAILER | 0 | 0 |  | TR407 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4000 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4000 | TR407 2020 48' KALYN SIEBERT DROP DECK TRAILER 2020 48' KALYN SIEBERT DROP DECK TRAILER | 0 | 0 |  | TR407 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4000 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4000 | TR410 2022 LANDOLL 455-53 53FT 55 TON TRAILER 2022 LANDOLL 455-53 53FT 55 TON TRAILER | 0 | 0 |  | TR410 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4000 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4000 | TR410 2022 LANDOLL 455-53 53FT 55 TON TRAILER 2022 LANDOLL 455-53 53FT 55 TON TRAILER | 0 | 0 |  | TR410 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4000 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4000 | TR410 2022 LANDOLL 455-53 53FT 55 TON TRAILER 2022 LANDOLL 455-53 53FT 55 TON TRAILER | 0 | 0 |  | TR410 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4000 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4000 | TR410 2022 LANDOLL 455-53 53FT 55 TON TRAILER 2022 LANDOLL 455-53 53FT 55 TON TRAILER | 0 | 0 |  | TR410 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4000 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4000 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4000 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4000 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4000 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4000 | HT060 2020 PETERBILT 389 SLEEPER 2020 PETERBILT 389 SLEEPER | 0 | 0 |  | HT060 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4000 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4000 | HT060 2020 PETERBILT 389 SLEEPER 2020 PETERBILT 389 SLEEPER | 0 | 0 |  | HT060 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4000 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4000 | TR410 2022 LANDOLL 455-53 53FT 55 TON TRAILER 2022 LANDOLL 455-53 53FT 55 TON TRAILER | 0 | 0 |  | TR410 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4000 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4000 | TR410 2022 LANDOLL 455-53 53FT 55 TON TRAILER 2022 LANDOLL 455-53 53FT 55 TON TRAILER | 0 | 0 |  | TR410 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4000 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4000 | HT060 2020 PETERBILT 389 SLEEPER 2020 PETERBILT 389 SLEEPER | 0 | 0 |  | HT060 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4000 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4000 | TR410 2022 LANDOLL 455-53 53FT 55 TON TRAILER 2022 LANDOLL 455-53 53FT 55 TON TRAILER | 0 | 0 |  | TR410 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4000 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4000 | HT056 2020 PETERBILT MODEL 389 DAY CAB 2020 PETERBILT MODEL 389 DAY CAB | 0 | 0 |  | HT056 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4000 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4000 | TR401 2014 53' GREAT DANE DROP DECK TRAILER 2014 53' GREAT DANE DROP DECK TRAILER | 0 | 0 |  | TR401 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4000 | ER |  | ER |  |  | 2026-04-12 |  | 0-4000 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-12 |  | 0-4005 | PR P0COST 000521 (PR) Summary | 0 | 0 |  |  |  | 0 | 567.16 | 0 | 12.31
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-12 |  | 0-4005 | PR P0COST 000521 (PR) Summary | 0 | 0 |  |  |  | 0 | 645.04 | 0 | 11.05
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-12 |  | 0-4005 | PR P0COST 000521 (PR) Summary | 0 | 0 |  |  |  | 0 | 645.04 | 0 | 11.85
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-16 |  | 0-4005 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 3577.56 | 0 | 53.5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-16 |  | 0-4005 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 3654.76 | 0 | 81.55
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-23 |  | 0-4005 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 638.16 | 0 | 13.34
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-23 |  | 0-4005 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 555.81 | 0 | 11.26
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-27 |  | 0-4005 | PR P2COST 000290 (PR) Summary | 0 | 0 |  |  |  | 0 | 589.6 | 0 | 8
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-30 |  | 0-4005 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 661.01 | 0 | 13.9
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-08 |  | 0-4005 | COST CODE TRANSFER 25-4005 | 0 | 0 |  |  |  | 0 | -10283.53 | 0 | -194.86
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-07 |  | 0-4005 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 439.25 | 0 | 5.82
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-12 |  | 0-4005 | PR P2COST 000292 (PR) Summary | 0 | 0 |  |  |  | 0 | 299.5 | 0 | 4
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-12 |  | 0-4005 | PR P2COST 000292 (PR) Summary | 0 | 0 |  |  |  | 0 | 598.95 | 0 | 8
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-12 |  | 0-4005 | PR P2COST 000292 (PR) Summary | 0 | 0 |  |  |  | 0 | 599 | 0 | 8
ttJTrans | 0-4000 | OC | MA1009024 | OC | MA1009024 | 2025-11-12 | 2025-11-12 | 1 | 0-4000 | PC88 MINE EX, JCB 3TS SKIDSTEER & SILT FENCE | 1 | 1659.45 | PO:COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 1659.45 | 0
ttJTrans | 0-4000 | OC | MA1009024 | OC | MA1009024 | 2025-11-12 | 2025-11-12 | 1 | 0-4000 | PC88 MINE EX, JCB 3TS SKIDSTEER & SILT FENCE | 1 | 1659.45 | INVOICE:ADJ-COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | -1659.45 | 0
ttJTrans | 0-4000 | OC | MA1009024 | OC | MA1009024 | 2025-11-12 | 2025-11-22 | 1 | 0-4000 | PC88 MINE EX, JCB 3TS SKIDSTEER & SILT FENCE | 1 | 1659.45 | INVOICE | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4000 | OC | MA1010372 | OC | MA1010372 | 2026-03-02 | 2026-03-09 | 1 | 0-4000 | PALLET OF ROAD SIGNS FROM MIDLAND TO WHARTON | 1 | 832.5 | INVOICE | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4000 | OC | MA1010372 | OC | MA1010372 | 2026-03-02 | 2026-03-03 | 1 | 0-4000 | PALLET OF ROAD SIGNS FROM MIDLAND TO WHARTON | 1 | 832.5 | INVOICE:ADJ-COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | -832.5 | 0
ttJTrans | 0-4000 | OC | MA1010372 | OC | MA1010372 | 2026-03-02 | 2026-03-03 | 1 | 0-4000 | PALLET OF ROAD SIGNS FROM MIDLAND TO WHARTON | 1 | 832.5 | PO:COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 832.5 | 0
ttJTrans | 0-4000 | OC | MA1010514 | OC | MA1010514 | 2026-03-11 | 2026-03-10 | 1 | 0-4000 | MOB IN TR419 R1107238 FROM MIDLAND TO | 1 | 2497.5 | INVOICE:ADJ-COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | -2497.5 | 0
ttJTrans | 0-4000 | OC | MA1010514 | OC | MA1010514 | 2026-03-11 | 2026-03-10 | 1 | 0-4000 | MOB IN TR419 R1107238 FROM MIDLAND TO | 1 | 2497.5 | PO:COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 2497.5 | 0
ttJTrans | 0-4000 | OC | MA1010514 | OC | MA1010514 | 2026-03-11 | 2026-03-27 | 1 | 0-4000 | MOB IN TR419 R1107238 FROM MIDLAND TO | 1 | 2497.5 | INVOICE | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4000 | OC | MA1010985 | OC | MA1010985 | 2026-04-06 | 2026-04-14 | 1 | 0-4000 | 2 P/u Trucks RT1447 Rt1385 | 1 | 2081.25 | INVOICE | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4000 | OC | MA1010985 | OC | MA1010985 | 2026-04-06 | 2026-04-28 | 2 | 0-4000 | Stack trailers, Plow | 1 | 1598.4 | INVOICE | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4000 | OC | MA1010985 | OC | MA1010985 | 2026-04-06 | 2026-04-28 | 3 | 0-4000 | Power only enclosed trailer TR425 | 1 | 1387.5 | INVOICE | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4000 | OC | MA1010985 | OC | MA1010985 | 2026-04-06 | 2026-04-07 | 2 | 0-4000 | Stack trailers, Plow | 1 | 1598.4 | PO:COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 1598.4 | 0
ttJTrans | 0-4000 | OC | MA1010985 | OC | MA1010985 | 2026-04-06 | 2026-04-07 | 3 | 0-4000 | Power only enclosed trailer TR425 | 1 | 1387.5 | INVOICE:ADJ-COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | -1387.5 | 0
ttJTrans | 0-4000 | OC | MA1010985 | OC | MA1010985 | 2026-04-06 | 2026-04-07 | 2 | 0-4000 | Stack trailers, Plow | 1 | 1598.4 | INVOICE:ADJ-COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | -1598.4 | 0
ttJTrans | 0-4000 | OC | MA1010985 | OC | MA1010985 | 2026-04-06 | 2026-04-07 | 1 | 0-4000 | 2 P/u Trucks RT1447 Rt1385 | 1 | 2081.25 | INVOICE:ADJ-COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | -2081.25 | 0
ttJTrans | 0-4000 | OC | MA1010985 | OC | MA1010985 | 2026-04-06 | 2026-04-07 | 1 | 0-4000 | 2 P/u Trucks RT1447 Rt1385 | 1 | 2081.25 | PO:COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 2081.25 | 0
ttJTrans | 0-4000 | OC | MA1010985 | OC | MA1010985 | 2026-04-06 | 2026-04-07 | 3 | 0-4000 | Power only enclosed trailer TR425 | 1 | 1387.5 | PO:COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 1387.5 | 0
ttJTrans | 0-4000 | OC | MA1011022 | OC | MA1011022 | 2026-04-07 | 2026-04-07 | 1 | 0-4000 | Deliver Farm tractor FT011 W/ Brush hog FE017 | 1 | 2430.9 | PO:COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 2430.9 | 0
ttJTrans | 0-4000 | OC | MA1011022 | OC | MA1011022 | 2026-04-07 | 2026-04-07 | 1 | 0-4000 | Deliver Farm tractor FT011 W/ Brush hog FE017 | 1 | 2430.9 | INVOICE:ADJ-COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | -2430.9 | 0
ttJTrans | 0-4000 | OC | MA1011022 | OC | MA1011022 | 46119 | 2026-04-16 | 1 | 0-4000 | Deliver Farm tractor FT011 W/ Brush hog FE017 | 1 | 2430.9 | INVOICE | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4000 | OC | MA1011045 | OC | MA1011045 | 46120 | 2026-04-16 | 1 | 0-4000 | Deliver Enclosed trailer TR145 to Luke | 1 | 2103.45 | INVOICE | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4000 | OC | MA1011045 | OC | MA1011045 | 46120 | 2026-04-08 | 1 | 0-4000 | Deliver Enclosed trailer TR145 to Luke | 1 | 2103.45 | PO:COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 2103.45 | 0
ttJTrans | 0-4000 | OC | MA1011045 | OC | MA1011045 | 2026-04-08 | 2026-04-08 | 1 | 0-4000 | Deliver Enclosed trailer TR145 to Luke | 1 | 2103.45 | INVOICE:ADJ-COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | -2103.45 | 0
ttJTrans | 0-4000 | OC | MA1011046 | OC | MA1011046 | 46120 | 2026-04-08 | 1 | 0-4000 | Deliver Tool van TR260 to Ruben | 1 | 2769.45 | PO:COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 2769.45 | 0
ttJTrans | 0-4000 | OC | MA1011046 | OC | MA1011046 | 2026-04-08 | 2026-04-08 | 1 | 0-4000 | Deliver Tool van TR260 to Ruben | 1 | 2769.45 | INVOICE:ADJ-COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | -2769.45 | 0
ttJTrans | 0-4000 | OC | MA1011046 | OC | MA1011046 | 2026-04-08 | 2026-04-14 | 1 | 0-4000 | Deliver Tool van TR260 to Ruben | 1 | 2769.45 | INVOICE | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4000 | OC | MA1011247 | OC | MA1011247 | 46127 | 2026-04-23 | 1 | 0-4000 | Transport 2 utility Trailers TR154 TR280 | 1 | 2103.45 | INVOICE | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4000 | OC | MA1011247 | OC | MA1011247 | 46127 | 2026-04-15 | 1 | 0-4000 | Transport 2 utility Trailers TR154 TR280 | 1 | 2103.45 | INVOICE:ADJ-COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | -2103.45 | 0
ttJTrans | 0-4000 | OC | MA1011247 | OC | MA1011247 | 46127 | 2026-04-15 | 1 | 0-4000 | Transport 2 utility Trailers TR154 TR280 | 1 | 2103.45 | PO:COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 2103.45 | 0
ttJTrans | 0-4000 | OC | MA1011473 | OC | MA1011473 | 46136 | 2026-04-27 | 1 | 0-4000 | Transport forklift, 2 Cable real trailers | 1 | 2430.9 | PO:COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 2430.9 | 0
ttJTrans | 0-4000 | OC | MA1011473 | OC | MA1011473 | 46136 | 2026-04-27 | 2 | 0-4000 | Transport 2 Dodge truck, 1 Cable real trailer | 1 | 1942.5 | PO:COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 1942.5 | 0
ttJTrans | 0-4000 | OC | MA1011473 | OC | MA1011473 | 46136 | 2026-04-27 | 1 | 0-4000 | Transport forklift, 2 Cable real trailers | 1 | 2430.9 | INVOICE:ADJ-COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | -2430.9 | 0
ttJTrans | 0-4000 | OC | MA1011473 | OC | MA1011473 | 46136 | 2026-04-27 | 2 | 0-4000 | Transport 2 Dodge truck, 1 Cable real trailer | 1 | 1942.5 | INVOICE:ADJ-COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | -1942.5 | 0
ttJTrans | 0-4000 | OC | MA1011473 | OC | MA1011473 | 46136 | 2026-05-07 | 2 | 0-4000 | Transport 2 Dodge truck, 1 Cable real trailer | 1 | 1942.5 | INVOICE | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4000 | OC | MA1011473 | OC | MA1011473 | 46136 | 2026-05-07 | 1 | 0-4000 | Transport forklift, 2 Cable real trailers | 1 | 2430.9 | INVOICE | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4000 | OC | MA1011576 | OC | MA1011576 | 46141 | 2026-05-11 | 1 | 0-4000 | PC88 MINI EXCAVATOR & SKID STEER GRAPPLE | 1 | 2430.9 | INVOICE | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4000 | OC | MA1011576 | OC | MA1011576 | 46141 | 2026-04-29 | 1 | 0-4000 | PC88 MINI EXCAVATOR & SKID STEER GRAPPLE | 1 | 2430.9 | PO:COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 2430.9 | 0
ttJTrans | 0-4000 | OC | MA1011576 | OC | MA1011576 | 46141 | 2026-04-29 | 1 | 0-4000 | PC88 MINI EXCAVATOR & SKID STEER GRAPPLE | 1 | 2430.9 | INVOICE:ADJ-COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | -2430.9 | 0
ttJTrans | 0-4000 | OC | MA1011704 | OC | MA1011704 | 46148 | 2026-05-06 | 1 | 0-4000 | Trucking Barrels & T-Post to job site | 1 | 1942.5 | INVOICE:ADJ-COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | -1942.5 | 0
ttJTrans | 0-4000 | OC | MA1011704 | OC | MA1011704 | 46148 | 2026-05-06 | 1 | 0-4000 | Trucking Barrels & T-Post to job site | 1 | 1942.5 | PO:COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 1942.5 | 0
ttJTrans | 0-4000 | OC | MA1011704 | OC | MA1011704 | 46148 | 2026-05-14 | 1 | 0-4000 | Trucking Barrels & T-Post to job site | 1 | 1942.5 | INVOICE | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4000 | OC | MA1011898 | OC | MA1011898 | 46155 | 2026-05-22 | 2 | 0-4000 | Haul 3 loads mats F/ Midland yard T/ Wharton | 1 | 6160.5 | INVOICE | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4000 | OC | MA1011898 | OC | MA1011898 | 46155 | 2026-05-22 | 1 | 0-4000 | Haul 5 loads mats F/ Midland yard T/ Wharton | 1 | 10267.5 | INVOICE | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4000 | OC | MA1011898 | OC | MA1011898 | 46155 | 2026-05-22 | 1 | 0-4000 | Haul 5 loads mats F/ Midland yard T/ Wharton | 1 | 10267.5 | INVOICE | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4000 | OC | MA1011898 | OC | MA1011898 | 46155 | 2026-05-22 | 1 | 0-4000 | Haul 5 loads mats F/ Midland yard T/ Wharton | 1 | 10267.5 | INVOICE | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4000 | OC | MA1011898 | OC | MA1011898 | 46155 | 2026-05-22 | 1 | 0-4000 | Haul 5 loads mats F/ Midland yard T/ Wharton | 1 | 10267.5 | INVOICE | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4000 | OC | MA1011898 | OC | MA1011898 | 46155 | 2026-05-22 | 1 | 0-4000 | Haul 5 loads mats F/ Midland yard T/ Wharton | 1 | 10267.5 | INVOICE | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4000 | OC | MA1011898 | OC | MA1011898 | 46155 | 2026-05-22 | 2 | 0-4000 | Haul 3 loads mats F/ Midland yard T/ Wharton | 1 | 6160.5 | INVOICE | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4000 | OC | MA1011898 | OC | MA1011898 | 46155 | 2026-05-20 | 1 | 0-4000 | Haul 5 loads mats F/ Midland yard T/ Wharton | 1 | 10267.5 | PO:COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 10267.5 | 0
ttJTrans | 0-4000 | OC | MA1011898 | OC | MA1011898 | 46155 | 2026-05-20 | 2 | 0-4000 | Haul 3 loads mats F/ Midland yard T/ Wharton | 1 | 6160.5 | PO:COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 6160.5 | 0
ttJTrans | 0-4000 | OC | MA1011898 | OC | MA1011898 | 46155 | 2026-05-20 | 2 | 0-4000 | Haul 3 loads mats F/ Midland yard T/ Wharton | 1 | 6160.5 | INVOICE:ADJ-COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | -2053.5 | 0
ttJTrans | 0-4000 | OC | MA1011898 | OC | MA1011898 | 46155 | 2026-05-20 | 1 | 0-4000 | Haul 5 loads mats F/ Midland yard T/ Wharton | 1 | 10267.5 | INVOICE:ADJ-COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | -2053.5 | 0
ttJTrans | 0-4000 | OC | MA1011898 | OC | MA1011898 | 46155 | 2026-05-20 | 1 | 0-4000 | Haul 5 loads mats F/ Midland yard T/ Wharton | 1 | 10267.5 | INVOICE:ADJ-COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | -2053.5 | 0
ttJTrans | 0-4000 | OC | MA1011898 | OC | MA1011898 | 46155 | 2026-05-20 | 1 | 0-4000 | Haul 5 loads mats F/ Midland yard T/ Wharton | 1 | 10267.5 | INVOICE:ADJ-COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | -2053.5 | 0
ttJTrans | 0-4000 | OC | MA1011898 | OC | MA1011898 | 46155 | 2026-05-20 | 1 | 0-4000 | Haul 5 loads mats F/ Midland yard T/ Wharton | 1 | 10267.5 | INVOICE:ADJ-COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | -2053.5 | 0
ttJTrans | 0-4000 | OC | MA1011898 | OC | MA1011898 | 46155 | 2026-05-20 | 1 | 0-4000 | Haul 5 loads mats F/ Midland yard T/ Wharton | 1 | 10267.5 | INVOICE:ADJ-COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | -2053.5 | 0
ttJTrans | 0-4000 | OC | MA1011898 | OC | MA1011898 | 46155 | 2026-05-20 | 2 | 0-4000 | Haul 3 loads mats F/ Midland yard T/ Wharton | 1 | 6160.5 | INVOICE:ADJ-COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | -2053.5 | 0
ttJTrans | 0-4000 | OC | MA1011898 | OC | MA1011898 | 46155 | 2026-05-20 | 2 | 0-4000 | Haul 3 loads mats F/ Midland yard T/ Wharton | 1 | 6160.5 | INVOICE:ADJ-COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | -2053.5 | 0
ttJTrans | 0-4000 | OC |  | OC |  |  | 2025-11-22 |  | 0-4000 | HAULING PC88 MINI EX SN:BH235/JCB 3TS SKIDSTEER SN:WLD110/SILT FENCE PLOW SN:WLD144 FROM WHC MIDLAND TO WHC BOLING TX | 0 | 0 |  | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 1495 | 0 | 0
ttJTrans | 0-4000 | OC |  | OC |  |  | 2026-02-11 |  | 0-4000 | 260100459,LYLE MACHINERY,11/13-12/10 HYPER VR BASE & ROVER,11/30/25,R48918 | 0 | 0 |  |  |  | 0 | 500 | 0 | 0
ttJTrans | 0-4000 | OC |  | OC |  |  | 2026-03-09 |  | 0-4000 | PALLET OF ROAD SIGNS FROM MIDLAND TO WHARTON TX | 0 | 0 |  | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 750 | 0 | 0
ttJTrans | 0-4000 | OC |  | OC |  |  | 2026-03-27 |  | 0-4000 | HAULING ENCLOSED CARGO TRAILER FROM WHC MIDLAND TO WHC WHARTON TX | 0 | 0 |  | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 2250 | 0 | 0
ttJTrans | 0-4000 | OC |  | OC |  |  | 2026-04-16 |  | 0-4000 | HAULING ENCLOSED TRAILER TR145 FROM MIDLAND TO WHARTON TX | 0 | 0 |  | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 1895 | 0 | 0
ttJTrans | 0-4000 | OC |  | OC |  |  | 2026-04-16 |  | 0-4000 | HAULING JD6130 W/BUCKET &BUSH HOG FT011 &FE017 FROM MIDLAND TO WHARTON TX | 0 | 0 |  | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 2190 | 0 | 0
ttJTrans | 0-4000 | OC |  | OC |  |  | 2026-04-13 |  | 0-4000 | HAULING W P/U TRUCKS RT1447 &RT1385 FROM WHC MIDLAND TO WHC LANE CITY TX | 0 | 0 |  | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 1875 | 0 | 0
ttJTrans | 0-4000 | OC |  | OC |  |  | 2026-04-13 |  | 0-4000 | HAULING TOOL VAN TRAILER TR260 FROM WHC MIDLAND TO WHARTON TX | 0 | 0 |  | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 2495 | 0 | 0
ttJTrans | 0-4000 | OC |  | OC |  |  | 2026-04-23 |  | 0-4000 | HAULING 2 STACKED UTILITY TRAILERS TR154/TR280 | 0 | 0 |  | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 1895 | 0 | 0
ttJTrans | 0-4000 | OC |  | OC |  |  | 2026-04-28 |  | 0-4000 | REBILL HAULING STACKED TRAILERS/SILT FENCE PLOW FROM MIDLAND TO LANE CITY TX | 0 | 0 |  | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 1440 | 0 | 0
ttJTrans | 0-4000 | OC |  | OC |  |  | 2026-04-28 |  | 0-4000 | REBILL HAULING ENCLOSED CARGO TRAILER FROM MIDLAND TO LANE CITY TX | 0 | 0 |  | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 1250 | 0 | 0
ttJTrans | 0-4000 | OC |  | OC |  |  | 2026-04-28 |  | 0-4000 | ORIGINAL INVOICE/RECEIVED CREDIT AND REBILL | 0 | 0 |  | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 1440 | 0 | 0
ttJTrans | 0-4000 | OC |  | OC |  |  | 2026-04-28 |  | 0-4000 | ORIGINAL INVOICE/ RECEIVED CREDIT AND REBILL | 0 | 0 |  | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 1250 | 0 | 0
ttJTrans | 0-4000 | OC |  | OC |  |  | 2026-04-28 |  | 0-4000 | FULL CREDIT FOR ARINV0001318 | 0 | 0 |  | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | -1440 | 0 | 0
ttJTrans | 0-4000 | OC |  | OC |  |  | 2026-04-28 |  | 0-4000 | FULL CREDIT FOR ARINV0001436 | 0 | 0 |  | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | -1250 | 0 | 0
ttJTrans | 0-4000 | OC |  | OC |  |  | 2026-05-14 |  | 0-4000 | HUALING MISC MATERIALS FROM WHC MIDLAND TX TO WHC WHARTON TX | 0 | 0 |  | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 1750 | 0 | 0
ttJTrans | 0-4000 | OC |  | OC |  |  | 2026-05-05 |  | 0-4000 | HAULING JCB TELEHANDLER WLD133/CABLE TOLLS FROM MIDLAND TO WHARTON TX | 0 | 0 |  | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 2190 | 0 | 0
ttJTrans | 0-4000 | OC |  | OC |  |  | 2026-05-05 |  | 0-4000 | HAULING RAM RT1242 TRUCK/2 CABLE ROLLS FROM MIDLAND TO WHARTON TX | 0 | 0 |  | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 1750 | 0 | 0
ttJTrans | 0-4000 | OC |  | OC |  |  | 2026-05-11 |  | 0-4000 | HAULINNG SKID STEER GRAPPLE BUCKET/PC88 MINI EXCAVATOR BH235/SSRAKE03 FROM MIDLAND TO SUNROPER TX | 0 | 0 |  | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 2190 | 0 | 0
ttJTrans | 0-4000 | OC |  | OC |  |  | 2026-05-22 |  | 0-4000 | HAULING MATS FROM MIDLAND TO WHC SUNROPER TX | 0 | 0 |  | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 1850 | 0 | 0
ttJTrans | 0-4000 | OC |  | OC |  |  | 2026-05-22 |  | 0-4000 | HAULING MATS FROM MIDLAND TO SUNROPER TX | 0 | 0 |  | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 1850 | 0 | 0
ttJTrans | 0-4000 | OC |  | OC |  |  | 2026-05-22 |  | 0-4000 | HAULING MATS FROM MIDLAND TX TO WHC SUNROPER TX | 0 | 0 |  | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 1850 | 0 | 0
ttJTrans | 0-4000 | OC |  | OC |  |  | 2026-05-22 |  | 0-4000 | HAULING MATS FROM MIDLAND TO WHC SUNROPER | 0 | 0 |  | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 1850 | 0 | 0
ttJTrans | 0-4000 | OC |  | OC |  |  | 2026-05-22 |  | 0-4000 | HAULING MATS FROM MIDLAND TO WHC SUNROPER | 0 | 0 |  | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 1850 | 0 | 0
ttJTrans | 0-4000 | OC |  | OC |  |  | 2026-05-22 |  | 0-4000 | HUALING MATS FROM MIDLAND TO WHC SUNROPER TX | 0 | 0 |  | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 1850 | 0 | 0
ttJTrans | 0-4000 | OC |  | OC |  |  | 2026-05-22 |  | 0-4000 | HAULING MATS FROM MIDLAND TO WHC SUNROPER TX | 0 | 0 |  | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 1850 | 0 | 0
ttJTrans | 0-4000-01 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4000-01 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4000-01 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4000-01 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4000-01 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4000-01 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4000-01 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4000-01 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4000-01 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4000-01 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4000-01 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4000-01 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4000-01 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4000-01 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4000-01 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4000-01 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4000-01 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4000-01 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4000-01 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4000-01 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4000-01 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4000-01 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4000-01 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4000-01 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4000-01 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4000-01 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-30 |  | 0-4005 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 223.71 | 0 | 2
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-30 |  | 0-4005 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 335.56 | 0 | 3
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-30 |  | 0-4005 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 335.56 | 0 | 3
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-09 |  | 0-4005 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 3848.13 | 0 | 80
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-09 |  | 0-4005 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 2716.92 | 0 | 34
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-09 |  | 0-4005 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 2194.26 | 0 | 40
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-09 |  | 0-4005 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 2058.4 | 0 | 40
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-09 |  | 0-4005 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 610.99 | 0 | 10
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-09 |  | 0-4005 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 1569.06 | 0 | 32
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-09 |  | 0-4005 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 858.82 | 0 | 10
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-16 |  | 0-4005 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 1222.51 | 0 | 20
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-23 |  | 0-4005 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 721.79 | 0 | 10
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-23 |  | 0-4005 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 602.44 | 0 | 8
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-23 |  | 0-4005 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 579.31 | 0 | 6
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-23 |  | 0-4005 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 660.32 | 0 | 10
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-23 |  | 0-4005 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 660.32 | 0 | 10
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-23 |  | 0-4005 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 660.32 | 0 | 10
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-23 |  | 0-4005 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 259.51 | 0 | 4
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-23 |  | 0-4005 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 383.5 | 0 | 8
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-08 |  | 0-4005 | COST CODE TRANSFER 25-4005 | 0 | 0 |  |  |  | 0 | -20501.43 | 0 | -340
ttJTrans | 0-4001 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4001 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4001 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4001 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4001 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4001 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4001 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4001 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4001 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4001 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4001 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4001 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4001 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4001 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4001 | OC | MA1009075 | OC | MA1009075 | 45978 | 2025-11-17 | 1 | 0-4001 | PC88 MINE EX, JCB 3TS SKIDSTEER & SILT FENCE | 1 | 2608.5 | PO:COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 2608.5 | 0
ttJTrans | 0-4001 | OC | MA1009075 | OC | MA1009075 | 45978 | 2025-11-17 | 1 | 0-4001 | PC88 MINE EX, JCB 3TS SKIDSTEER & SILT FENCE | 1 | 2608.5 | INVOICE:ADJ-COMMIT | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | -2608.5 | 0
ttJTrans | 0-4001 | OC | MA1009075 | OC | MA1009075 | 45978 | 2025-12-15 | 1 | 0-4001 | PC88 MINE EX, JCB 3TS SKIDSTEER & SILT FENCE | 1 | 2608.5 | INVOICE | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4001 | OC |  | OC |  |  | 2025-12-15 |  | 0-4001 | HAULING PC88 MINI EX/JCB 3TS SKIDSTEER/SILT FENCE PLOW FROM WHC BOLING TO WHC MIDLAND TX | 0 | 0 |  | 20050 | STANDARD FREIGHT LOGISTICS, LLC | 0 | 2350 | 0 | 0
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-12-11 |  | 0-4005 | PR P2COST 000278 (PR) Summary | 0 | 0 |  |  |  | 0 | 292.09 | 0 | 4
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-12-11 |  | 0-4005 | PR P2COST 000278 (PR) Summary | 0 | 0 |  |  |  | 0 | 292.09 | 0 | 4
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-12-11 |  | 0-4005 | PR P2COST 000278 (PR) Summary | 0 | 0 |  |  |  | 0 | 292.09 | 0 | 4
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-12-11 |  | 0-4005 | PR P2COST 000278 (PR) Summary | 0 | 0 |  |  |  | 0 | 292.09 | 0 | 4
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-12-11 |  | 0-4005 | PR P2COST 000278 (PR) Summary | 0 | 0 |  |  |  | 0 | 292.09 | 0 | 4
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-08 |  | 0-4005 | COST CODE TRANSFER 25-4005 | 0 | 0 |  |  |  | 0 | -1460.45 | 0 | -20
ttJTrans | 0-4004-01 | MA | MA1009990 | MA | MA1009990 | 46059 | 2026-04-13 | 1 | 0-4004-01 | 30% Deposit of Equipment/Materials as | 1 | 10385036.9 | INVOICE | 18727 | GAMECHANGE SOLAR CORP | 0 | 0 | 0 | 0
ttJTrans | 0-4004-01 | MA | MA1009990 | MA | MA1009990 | 46059 | 2026-03-13 | 1 | 0-4004-01 | 30% Deposit of Equipment/Materials as | 1 | 10385036.9 | INVOICE:ADJ-COMMIT | 18727 | GAMECHANGE SOLAR CORP | 0 | 0 | -10385036.9 | 0
ttJTrans | 0-4004-01 | MA | MA1009990 | MA | MA1009990 | 46059 | 2026-03-13 | 1 | 0-4004-01 | 30% Deposit of Equipment/Materials as | 1 | 10385036.9 | PO:COMMIT | 18727 | GAMECHANGE SOLAR CORP | 0 | 0 | 10385036.9 | 0
ttJTrans | 0-4004-01 | MA |  | MA |  |  | 2026-04-13 |  | 0-4004-01 | 30% DEPOSIT - Racking & Piles | 0 | 0 |  | 18727 | GAMECHANGE SOLAR CORP | 0 | 9355889.1 | 0 | 0
ttJTrans | 0-4004-01 | MA | MA1009990 | MA | MA1009990 | 46059 | 2026-03-13 | 4 | 0-4004-01 | Site Commissioning and Training Services as | 1 | 384621.66 | PO:COMMIT | 18727 | GAMECHANGE SOLAR CORP | 0 | 0 | 384621.66 | 0
ttJTrans | 0-4004-01 | MA | MA1009990 | MA | MA1009990 | 46059 | 2026-03-13 | 3 | 0-4004-01 | Engineering Services as Outlined in | 1 | 307696.44 | PO:COMMIT | 18727 | GAMECHANGE SOLAR CORP | 0 | 0 | 307696.44 | 0
ttJTrans | 0-4004-01 | MA | MA1009990 | MA | MA1009990 | 46059 | 2026-03-13 | 2 | 0-4004-01 | All Racking Equipment/Material - Less 30% | 1 | 24231752.77 | PO:COMMIT | 18727 | GAMECHANGE SOLAR CORP | 0 | 0 | 24231752.77 | 0
ttJTrans | 0-4004-01 | OC | MA1009990 | OC | MA1009990 | 46059 | 2026-03-13 | 6 | 0-4004-01 | Delivery of Equipment/Materials as Outlined | 1 | 4155140.7 | PO:COMMIT | 18727 | GAMECHANGE SOLAR CORP | 0 | 0 | 4155140.7 | 0
ttJTrans | 0-4004-01 | OC | MA1009990 | OC | MA1009990 | 46059 | 2026-03-13 | 5 | 0-4004-01 | Tariff Charges as Outlined in Attachment A | 1 | 7252997.52 | PO:COMMIT | 18727 | GAMECHANGE SOLAR CORP | 0 | 0 | 7252997.52 | 0
ttJTrans | 0-4004-02 | MA | MA1010844 | MA | MA1010844 | 46170 |  | 2 | 0-4004-02 | Tariffs - Upon MVT Shipment | 1 | 3556136.97 | PO:COMMIT | 21398 | TMEIC CORPORATION AMERICAS | 0 | 0 | 3556136.97 | 0
ttJTrans | 0-4004-02 | MA | MA1010844 | MA | MA1010844 | 46170 |  | 4 | 0-4004-02 | Upon Completion of Commissioning Services | 1 | 496113.39 | PO:COMMIT | 21398 | TMEIC CORPORATION AMERICAS | 0 | 0 | 496113.39 | 0
ttJTrans | 0-4004-02 | MA | MA1010844 | MA | MA1010844 | 46170 |  | 1 | 0-4004-02 | 30% Deposit for Equipment and Materials as | 1 | 5531862.6 | INVOICE:ADJ-COMMIT | 21398 | TMEIC CORPORATION AMERICAS | 0 | 0 | -5531862.6 | 0
ttJTrans | 0-4004-02 | MA | MA1010844 | MA | MA1010844 | 46170 |  | 1 | 0-4004-02 | 30% Deposit for Equipment and Materials as | 1 | 5531862.6 | PO:COMMIT | 21398 | TMEIC CORPORATION AMERICAS | 0 | 0 | 5531862.6 | 0
ttJTrans | 0-4004-02 | MA | MA1010844 | MA | MA1010844 | 46170 |  | 3 | 0-4004-02 | All Equipment/Materials Less Advanced | 1 | 12907679.4 | PO:COMMIT | 21398 | TMEIC CORPORATION AMERICAS | 0 | 0 | 12907679.4 | 0
ttJTrans | 0-4004-02 | MA | MA1010844 | MA | MA1010844 | 46170 | 2026-04-22 | 1 | 0-4004-02 | 30% Deposit for Equipment and Materials as | 1 | 5531862.6 | INVOICE | 21398 | TMEIC CORPORATION AMERICAS | 0 | 0 | 0 | 0
ttJTrans | 0-4004-02 | MA |  | MA |  |  | 2026-04-22 |  | 0-4004-02 | 30% Deposit for Equipment and Materials as Outlined in Attachment A | 0 | 0 |  | 21398 | TMEIC CORPORATION AMERICAS | 0 | 4983660 | 0 | 0
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-30 |  | 0-4005 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 436.96 | 0 | 4
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-30 |  | 0-4005 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 436.96 | 0 | 4
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-30 |  | 0-4005 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 436.96 | 0 | 4
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-30 |  | 0-4005 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 436.96 | 0 | 4
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-30 |  | 0-4005 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 436.96 | 0 | 4
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-08 |  | 0-4005 | COST CODE TRANSFER 25-4005 | 0 | 0 |  |  |  | 0 | -2184.8 | 0 | -20
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-14 |  | 0-4005 | PR P2COST 000289 (PR) Summary | 0 | 0 |  |  |  | 0 | 978.59 | 0 | 10
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-14 |  | 0-4005 | PR P2COST 000289 (PR) Summary | 0 | 0 |  |  |  | 0 | 978.62 | 0 | 10
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-14 |  | 0-4005 | PR P2COST 000289 (PR) Summary | 0 | 0 |  |  |  | 0 | 978.59 | 0 | 10
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-08 |  | 0-4005 | COST CODE TRANSFER 25-4005 | 0 | 0 |  |  |  | 0 | -2935.8 | 0 | -30
ttJTrans | 0-4004-05 | MA | MA1010387 | MA | MA1010387 | 46104 | 2026-03-26 | 1 | 0-4004-05 | 30% Deposit for Equipment and Materials as | 1 | 3545645.32 | INVOICE | 20718 | JAVELIN SUPPLIES LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4004-05 | MA | MA1010387 | MA | MA1010387 | 46104 | 2026-03-26 | 2 | 0-4004-05 | All Equipment/Materials Less Advanced | 1 | 8273172.39 | INVOICE | 20718 | JAVELIN SUPPLIES LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4004-05 | MA | MA1010387 | MA | MA1010387 | 46104 | 2026-05-18 | 3 | 0-4004-05 | All CO1 Equipment/Materials as Outlined in | 1 | 2715612.26 | INVOICE | 20718 | JAVELIN SUPPLIES LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4004-05 | MA | MA1010387 | MA | MA1010387 | 46104 | 2026-03-30 | 1 | 0-4004-05 | 30% Deposit for Equipment and Materials as | 1 | 3545645.32 | PO:COMMIT | 20718 | JAVELIN SUPPLIES LLC | 0 | 0 | 3545645.32 | 0
ttJTrans | 0-4004-05 | MA | MA1010387 | MA | MA1010387 | 46104 | 2026-03-30 | 2 | 0-4004-05 | All Equipment/Materials Less Advanced | 1 | 8273172.39 | INVOICE:ADJ-COMMIT | 20718 | JAVELIN SUPPLIES LLC | 0 | 0 | -3545.63 | 0
ttJTrans | 0-4004-05 | MA | MA1010387 | MA | MA1010387 | 2026-03-23 | 2026-03-30 | 3 | 0-4004-05 | All CO1 Equipment/Materials as Outlined in | 1 | 2715612.26 | PO:COMMIT | 20718 | JAVELIN SUPPLIES LLC | 0 | 0 | 2715612.26 | 0
ttJTrans | 0-4004-05 | MA | MA1010387 | MA | MA1010387 | 2026-03-23 | 2026-03-30 | 2 | 0-4004-05 | All Equipment/Materials Less Advanced | 1 | 8273172.39 | PO:COMMIT | 20718 | JAVELIN SUPPLIES LLC | 0 | 0 | 8273172.39 | 0
ttJTrans | 0-4004-05 | MA | MA1010387 | MA | MA1010387 | 2026-03-23 | 2026-03-30 | 1 | 0-4004-05 | 30% Deposit for Equipment and Materials as | 1 | 3545645.32 | INVOICE:ADJ-COMMIT | 20718 | JAVELIN SUPPLIES LLC | 0 | 0 | -3545645.32 | 0
ttJTrans | 0-4004-05 | MA | MA1010387 | MA | MA1010387 | 2026-03-23 | 2026-03-30 | 3 | 0-4004-05 | All CO1 Equipment/Materials as Outlined in | 1 | 2715612.26 | INVOICE:ADJ-COMMIT | 20718 | JAVELIN SUPPLIES LLC | 0 | 0 | -895672.33 | 0
ttJTrans | 0-4004-05 | MA | MA1010787 | MA | MA1010787 | 2026-05-27 |  | 2 | 0-4004-05 | All Equipment/Material Less 10% Advanced | 1 | 4901027.07 | PO:COMMIT | 19974 | KBI COSMOLINK CO., LTD. | 0 | 0 | 4901027.07 | 0
ttJTrans | 0-4004-05 | MA | MA1010787 | MA | MA1010787 | 46169 |  | 1 | 0-4004-05 | 10% Deposit for Equipment/Material as | 1 | 544558.56 | INVOICE:ADJ-COMMIT | 19974 | KBI COSMOLINK CO., LTD. | 0 | 0 | -544558.56 | 0
ttJTrans | 0-4004-05 | MA | MA1010787 | MA | MA1010787 | 46169 |  | 1 | 0-4004-05 | 10% Deposit for Equipment/Material as | 1 | 544558.56 | PO:COMMIT | 19974 | KBI COSMOLINK CO., LTD. | 0 | 0 | 544558.56 | 0
ttJTrans | 0-4004-05 | MA | MA1010787 | MA | MA1010787 | 46169 | 2026-04-13 | 1 | 0-4004-05 | 10% Deposit for Equipment/Material as | 1 | 544558.56 | INVOICE | 19974 | KBI COSMOLINK CO., LTD. | 0 | 0 | 0 | 0
ttJTrans | 0-4004-05 | MA | MA1011688 | MA | MA1011688 | 46168 | 2026-05-20 | 5 | 0-4004-05 | SUBSTATION: 7510 - Ground Rod, Copper Coated, | 70 | 2680.65 | INVOICE | 18867 | REXEL USA, INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4004-05 | MA | MA1011688 | MA | MA1011688 | 46168 |  | 6 | 0-4004-05 | SUBSTATION: 2 AWG Soft Drawn Solid Bare | 1500 | 3604.76 | PO:COMMIT | 18867 | REXEL USA, INC. | 3604.76 | 0 | 0 | 0
ttJTrans | 0-4004-05 | MA | MA1011688 | MA | MA1011688 | 46168 |  | 4 | 0-4004-05 | SUBSTATION: YGHC34C29 - 300-500 TO 3/0-250 | 190 | 4534.35 | PO:COMMIT | 18867 | REXEL USA, INC. | 4534.35 | 0 | 0 | 0
ttJTrans | 0-4004-05 | MA | MA1011688 | MA | MA1011688 | 46168 |  | 3 | 0-4004-05 | SUBSTATION: YGL29C2 - 2-250 To 6-2 Grd | 190 | 7771.67 | PO:COMMIT | 18867 | REXEL USA, INC. | 7771.67 | 0 | 0 | 0
ttJTrans | 0-4004-05 | MA | MA1011688 | MA | MA1011688 | 46168 |  | 1 | 0-4004-05 | SUBSTATION: YGHC29C29 - C-Tap Connector, | 190 | 2762.79 | PO:COMMIT | 18867 | REXEL USA, INC. | 2762.79 | 0 | 0 | 0
ttJTrans | 0-4004-05 | MA | MA1011688 | MA | MA1011688 | 46168 |  | 2 | 0-4004-05 | SUBSTATION: YGHC29C26 - C-Tap Connector, | 190 | 2530.8 | PO:COMMIT | 18867 | REXEL USA, INC. | 2530.8 | 0 | 0 | 0
ttJTrans | 0-4004-05 | MA | MA1011688 | MA | MA1011688 | 46168 |  | 5 | 0-4004-05 | SUBSTATION: 7510 - Ground Rod, Copper Coated, | 70 | 2680.65 | INVOICE:ADJ-ACCRUAL | 18867 | REXEL USA, INC. | -2680.65 | 0 | 0 | 0
ttJTrans | 0-4004-05 | MA | MA1011688 | MA | MA1011688 | 46168 |  | 5 | 0-4004-05 | SUBSTATION: 7510 - Ground Rod, Copper Coated, | 70 | 2680.65 | PO:COMMIT | 18867 | REXEL USA, INC. | 2680.65 | 0 | 0 | 0
ttJTrans | 0-4004-05 | MA | MA1011688 | MA | MA1011688 | 2026-05-26 |  | 7 | 0-4004-05 | SUBSTATION: S12SOLSDBC-BK #12 SOLID BARE | 2000 | 543.9 | PO:COMMIT | 18867 | REXEL USA, INC. | 543.9 | 0 | 0 | 0
ttJTrans | 0-4004-05 | MA |  | MA |  |  | 2026-03-26 |  | 0-4004-05 | PV Cable | 0 | 0 |  | 20718 | JAVELIN SUPPLIES LLC | 0 | 3197469.33 | 0 | 0
ttJTrans | 0-4004-05 | MA |  | MA |  |  | 2026-04-13 |  | 0-4004-05 | 10% DOWN PAYMENT - MV Cable | 0 | 0 |  | 19974 | KBI COSMOLINK CO., LTD. | 0 | 490593.3 | 0 | 0
ttJTrans | 0-4004-05 | MA |  | MA |  |  | 2026-05-18 |  | 0-4004-05 | PV Cable | 0 | 0 |  | 20718 | JAVELIN SUPPLIES LLC | 0 | 806912 | 0 | 0
ttJTrans | 0-4004-05 | MA |  | MA |  |  | 2026-05-17 |  | 0-4004-05 | 10FT COPPER GROUND ROD PN:257145 | 0 | 0 |  | 18867 | REXEL USA, INC. | 0 | 2578.01 | 0 | 0
ttJTrans | 0-4004-05 | OC | MA1010787 | OC | MA1010787 | 46169 |  | 3 | 0-4004-05 | Tariff Cost as Outlined in Attachment A | 1 | 1033828.47 | PO:COMMIT | 19974 | KBI COSMOLINK CO., LTD. | 0 | 0 | 1033828.47 | 0
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-14 |  | 0-4005 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 881.29 | 0 | 16
ttJTrans | 0-4004-10 | MA | MA1011628 | MA | MA1011628 | 46146 | 2026-05-05 | 6 | 0-4004-10 | 4FT STAKES - 1IN X 2IN X 48IN | 1000 | 3074.7 | INVOICE:ADJ-COMMIT | 20581 | THE REYNOLDS COMPANY | 0 | 0 | -3074.7 | 0
ttJTrans | 0-4004-10 | MA | MA1011628 | MA | MA1011628 | 46146 | 2026-05-05 | 5 | 0-4004-10 | 42-101 - NON-DETECTABLE UNDERGROUND TAPE - | 50 | 2418.14 | INVOICE:ADJ-COMMIT | 20581 | THE REYNOLDS COMPANY | 0 | 0 | -2321.41 | 0
ttJTrans | 0-4004-10 | MA | MA1011628 | MA | MA1011628 | 46146 | 2026-05-05 | 5 | 0-4004-10 | 42-101 - NON-DETECTABLE UNDERGROUND TAPE - | 50 | 2418.14 | INVOICE:ADJ-COMMIT | 20581 | THE REYNOLDS COMPANY | 0 | 0 | -96.73 | 0
ttJTrans | 0-4004-10 | MA | MA1011628 | MA | MA1011628 | 46146 | 2026-05-05 | 2 | 0-4004-10 | 78885 - CEMC20 QUART PVC SOLVENT CEMENT LOW | 240 | 3226.1 | PO:COMMIT | 20581 | THE REYNOLDS COMPANY | 0 | 0 | 3226.1 | 0
ttJTrans | 0-4004-10 | MA | MA1011628 | MA | MA1011628 | 46146 | 2026-05-05 | 3 | 0-4004-10 | 77328 - EB45 3" PVC MLD END BELL SOCKET MLD | 800 | 2530.8 | PO:COMMIT | 20581 | THE REYNOLDS COMPANY | 0 | 0 | 2530.8 | 0
ttJTrans | 0-4004-10 | MA | MA1011628 | MA | MA1011628 | 46146 | 2026-05-05 | 4 | 0-4004-10 | EWDT-8 - DUCT TAPE 8 MIL | 50 | 458.99 | PO:COMMIT | 20581 | THE REYNOLDS COMPANY | 0 | 0 | 458.99 | 0
ttJTrans | 0-4004-10 | MA | MA1011628 | MA | MA1011628 | 46146 | 2026-05-05 | 4 | 0-4004-10 | EWDT-8 - DUCT TAPE 8 MIL | 50 | 458.99 | INVOICE:ADJ-COMMIT | 20581 | THE REYNOLDS COMPANY | 0 | 0 | -458.99 | 0
ttJTrans | 0-4004-10 | MA | MA1011628 | MA | MA1011628 | 46146 | 2026-05-05 | 6 | 0-4004-10 | 4FT STAKES - 1IN X 2IN X 48IN | 1000 | 3074.7 | PO:COMMIT | 20581 | THE REYNOLDS COMPANY | 0 | 0 | 3074.7 | 0
ttJTrans | 0-4004-10 | MA | MA1011628 | MA | MA1011628 | 46146 | 2026-05-05 | 1 | 0-4004-10 | P30UC - 3" x 10' PVC Conduit SCH40 | 11250 | 22977 | INVOICE:ADJ-COMMIT | 20581 | THE REYNOLDS COMPANY | 0 | 0 | -22977 | 0
ttJTrans | 0-4004-10 | MA | MA1011628 | MA | MA1011628 | 46146 | 2026-05-05 | 2 | 0-4004-10 | 78885 - CEMC20 QUART PVC SOLVENT CEMENT LOW | 240 | 3226.1 | INVOICE:ADJ-COMMIT | 20581 | THE REYNOLDS COMPANY | 0 | 0 | -3226.1 | 0
ttJTrans | 0-4004-10 | MA | MA1011628 | MA | MA1011628 | 46146 | 2026-05-05 | 3 | 0-4004-10 | 77328 - EB45 3" PVC MLD END BELL SOCKET MLD | 800 | 2530.8 | INVOICE:ADJ-COMMIT | 20581 | THE REYNOLDS COMPANY | 0 | 0 | -2530.8 | 0
ttJTrans | 0-4004-10 | MA | MA1011628 | MA | MA1011628 | 46146 | 2026-05-05 | 1 | 0-4004-10 | P30UC - 3" x 10' PVC Conduit SCH40 | 11250 | 22977 | PO:COMMIT | 20581 | THE REYNOLDS COMPANY | 0 | 0 | 22977 | 0
ttJTrans | 0-4004-10 | MA | MA1011628 | MA | MA1011628 | 46146 | 2026-05-05 | 5 | 0-4004-10 | 42-101 - NON-DETECTABLE UNDERGROUND TAPE - | 50 | 2418.14 | PO:COMMIT | 20581 | THE REYNOLDS COMPANY | 0 | 0 | 2418.14 | 0
ttJTrans | 0-4004-10 | MA | MA1011628 | MA | MA1011628 | 46146 | 2026-05-19 | 1 | 0-4004-10 | P30UC - 3" x 10' PVC Conduit SCH40 | 11250 | 22977 | INVOICE | 20581 | THE REYNOLDS COMPANY | 0 | 0 | 0 | 0
ttJTrans | 0-4004-10 | MA | MA1011628 | MA | MA1011628 | 46146 | 2026-05-14 | 6 | 0-4004-10 | 4FT STAKES - 1IN X 2IN X 48IN | 1000 | 3074.7 | INVOICE | 20581 | THE REYNOLDS COMPANY | 0 | 0 | 0 | 0
ttJTrans | 0-4004-10 | MA | MA1011628 | MA | MA1011628 | 46146 | 2026-05-14 | 5 | 0-4004-10 | 42-101 - NON-DETECTABLE UNDERGROUND TAPE - | 50 | 2418.14 | INVOICE | 20581 | THE REYNOLDS COMPANY | 0 | 0 | 0 | 0
ttJTrans | 0-4004-10 | MA | MA1011628 | MA | MA1011628 | 46146 | 2026-05-14 | 5 | 0-4004-10 | 42-101 - NON-DETECTABLE UNDERGROUND TAPE - | 50 | 2418.14 | INVOICE | 20581 | THE REYNOLDS COMPANY | 0 | 0 | 0 | 0
ttJTrans | 0-4004-10 | MA | MA1011628 | MA | MA1011628 | 46146 | 2026-05-14 | 4 | 0-4004-10 | EWDT-8 - DUCT TAPE 8 MIL | 50 | 458.99 | INVOICE | 20581 | THE REYNOLDS COMPANY | 0 | 0 | 0 | 0
ttJTrans | 0-4004-10 | MA | MA1011628 | MA | MA1011628 | 46146 | 2026-05-19 | 3 | 0-4004-10 | 77328 - EB45 3" PVC MLD END BELL SOCKET MLD | 800 | 2530.8 | INVOICE | 20581 | THE REYNOLDS COMPANY | 0 | 0 | 0 | 0
ttJTrans | 0-4004-10 | MA | MA1011628 | MA | MA1011628 | 46146 | 2026-05-19 | 2 | 0-4004-10 | 78885 - CEMC20 QUART PVC SOLVENT CEMENT LOW | 240 | 3226.1 | INVOICE | 20581 | THE REYNOLDS COMPANY | 0 | 0 | 0 | 0
ttJTrans | 0-4004-10 | MA | MA1011688 | MA | MA1011688 | 46168 | 2026-05-20 | 12 | 0-4004-10 | 7510 - Ground Rod, Copper Coated, 3/4", 10' | 10 | 382.84 | INVOICE | 18867 | REXEL USA, INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4004-10 | MA | MA1011688 | MA | MA1011688 | 46168 |  | 9 | 0-4004-10 | YGHC29C26 - C-Tap Connector, Wire Range 3/0 | 10 | 133.2 | PO:COMMIT | 18867 | REXEL USA, INC. | 133.2 | 0 | 0 | 0
ttJTrans | 0-4004-10 | MA | MA1011688 | MA | MA1011688 | 46168 |  | 10 | 0-4004-10 | YGL29C2 - 2-250 To 6-2 Grd Grid/ro | 10 | 409.04 | PO:COMMIT | 18867 | REXEL USA, INC. | 409.04 | 0 | 0 | 0
ttJTrans | 0-4004-10 | MA | MA1011688 | MA | MA1011688 | 46168 |  | 13 | 0-4004-10 | 2 AWG Soft Drawn Solid Bare Copper, Cut to | 500 | 1201.59 | PO:COMMIT | 18867 | REXEL USA, INC. | 1201.59 | 0 | 0 | 0
ttJTrans | 0-4004-10 | MA | MA1011688 | MA | MA1011688 | 46168 |  | 12 | 0-4004-10 | 7510 - Ground Rod, Copper Coated, 3/4", 10' | 10 | 382.84 | PO:COMMIT | 18867 | REXEL USA, INC. | 382.84 | 0 | 0 | 0
ttJTrans | 0-4004-10 | MA | MA1011688 | MA | MA1011688 | 46168 |  | 12 | 0-4004-10 | 7510 - Ground Rod, Copper Coated, 3/4", 10' | 10 | 382.84 | INVOICE:ADJ-ACCRUAL | 18867 | REXEL USA, INC. | -153.18 | 0 | 0 | 0
ttJTrans | 0-4004-10 | MA | MA1011688 | MA | MA1011688 | 46168 |  | 12 | 0-4004-10 | 7510 - Ground Rod, Copper Coated, 3/4", 10' | 10 | 382.84 | INVOICE:ADJ-ACCRUAL | 18867 | REXEL USA, INC. | -229.66 | 0 | 0 | 0
ttJTrans | 0-4004-10 | MA | MA1011688 | MA | MA1011688 | 46168 |  | 11 | 0-4004-10 | YGHC34C29 - 300-500 TO 3/0-250 GRD C ***SHIP | 10 | 238.65 | PO:COMMIT | 18867 | REXEL USA, INC. | 238.65 | 0 | 0 | 0
ttJTrans | 0-4004-10 | MA | MA1011688 | MA | MA1011688 | 46168 |  | 8 | 0-4004-10 | YGHC29C29 - C-Tap Connector, Wire Range 3/0 | 10 | 145.41 | PO:COMMIT | 18867 | REXEL USA, INC. | 145.41 | 0 | 0 | 0
ttJTrans | 0-4004-10 | MA |  | MA |  |  | 2026-05-14 |  | 0-4004-10 | WOODEN STAKES | 0 | 0 |  | 20581 | THE REYNOLDS COMPANY | 0 | 2998.53 | 0 | 0
ttJTrans | 0-4004-10 | MA |  | MA |  |  | 2026-05-14 |  | 0-4004-10 | TAPE CAUT ELEC LN BURI/RD | 0 | 0 |  | 20581 | THE REYNOLDS COMPANY | 0 | 2263.89 | 0 | 0
ttJTrans | 0-4004-10 | MA |  | MA |  |  | 2026-05-14 |  | 0-4004-10 | ELECTRICAL DUCT TAPE/ TAPE CAUT ELEC | 0 | 0 |  | 20581 | THE REYNOLDS COMPANY | 0 | 541.95 | 0 | 0
ttJTrans | 0-4004-10 | MA |  | MA |  |  | 2026-05-19 |  | 0-4004-10 | PVC SOLVENT CEMENT / PVC END BELL | 0 | 0 |  | 20581 | THE REYNOLDS COMPANY | 0 | 5614.27 | 0 | 0
ttJTrans | 0-4004-10 | MA |  | MA |  |  | 2026-05-19 |  | 0-4004-10 | PVC CONDUIT 10FT 3-IN ELECTICAL - ROAD CROSSING MTL - REQ#061 | 0 | 0 |  | 20581 | THE REYNOLDS COMPANY | 0 | 22407.75 | 0 | 0
ttJTrans | 0-4004-10 | MA |  | MA |  |  | 2026-05-19 |  | 0-4004-10 | CREDIT# 26793429-00 FOR INV# 26754656-03 WRONG PRICES. REBILL INV# 26793443-00 | 0 | 0 |  | 20581 | THE REYNOLDS COMPANY | 0 | -8093.73 | 0 | 0
ttJTrans | 0-4004-10 | MA |  | MA |  |  | 2026-05-19 |  | 0-4004-10 | APPLY CREDIT# 26793429-00 TO INV# 26754656-03. REBILL INV# 26793443-00 WITH CORRECTED PRICES PVC SOLVENT CEMENT / PVC END BELL | 0 | 0 |  | 20581 | THE REYNOLDS COMPANY | 0 | 8093.73 | 0 | 0
ttJTrans | 0-4004-10 | MA |  | MA |  |  | 2026-05-17 |  | 0-4004-10 | 10FT COPPER GROUND ROD PN:257145 | 0 | 0 |  | 18867 | REXEL USA, INC. | 0 | 147.32 | 0 | 0
ttJTrans | 0-4004-10 | MA |  | MA |  |  | 2026-05-17 |  | 0-4004-10 | 10FT COPPER GROUND ROD | 0 | 0 |  | 18867 | REXEL USA, INC. | 0 | 230.97 | 0 | 0
ttJTrans | 0-4004-10 | OC | MA1011688 | OC | MA1011688 | 46168 |  | 14 | 0-4004-10 | FREIGHT | 1 | 712.85 | PO:COMMIT | 18867 | REXEL USA, INC. | 138.75 | 0 | 0 | 0
ttJTrans | 0-4004-10 | OC | MA1011688 | OC | MA1011688 | 46168 |  | 14 | 0-4004-10 | FREIGHT | 1 | 712.85 | INVOICE:ADJ-ACCRUAL | 18867 | REXEL USA, INC. | -128.35 | 0 | 0 | 0
ttJTrans | 0-4004-10 | OC | MA1011688 | OC | MA1011688 | 46168 | 2026-05-20 | 14 | 0-4004-10 | FREIGHT | 1 | 712.85 | INVOICE | 18867 | REXEL USA, INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4004-10 | OC |  | OC |  |  | 2026-05-17 |  | 0-4004-10 | 10FT COPPER GROUND ROD PN:257145 | 0 | 0 |  | 18867 | REXEL USA, INC. | 0 | 123.43 | 0 | 0
ttJTrans | 0-4004-12 | MA | MA1011618 | MA | MA1011618 | 46143 | 2026-05-06 | 2 | 0-4004-12 | All Equipment/Materials Less Advanced | 1 | 603588.36 | PO:COMMIT | 20718 | JAVELIN SUPPLIES LLC | 0 | 0 | 603588.36 | 0
ttJTrans | 0-4004-12 | MA | MA1011618 | MA | MA1011618 | 46143 | 2026-05-06 | 1 | 0-4004-12 | 20% Deposit for Equipment/Materials as | 1 | 150897.09 | PO:COMMIT | 20718 | JAVELIN SUPPLIES LLC | 0 | 0 | 150897.09 | 0
ttJTrans | 0-4004-12 | OC | MA1011618 | OC | MA1011618 | 46143 | 2026-05-06 | 3 | 0-4004-12 | All Equipment/Materials | 1 | 41046.91 | PO:COMMIT | 20718 | JAVELIN SUPPLIES LLC | 0 | 0 | 41046.91 | 0
ttJTrans | 0-4004-12 | OC | MA1011618 | OC | MA1011618 | 46143 | 2026-05-06 | 4 | 0-4004-12 | Tariff Charges as Outlined in Attachment A | 1 | 171901.7 | PO:COMMIT | 20718 | JAVELIN SUPPLIES LLC | 0 | 0 | 171901.7 | 0
ttJTrans | 0-4004-13 | MA | MA1010311 | MA | MA1010311 | 46079 | 2026-02-27 | 1 | 0-4004-13 | Centerpoint Breaker Pass-Through | 1 | 333000 | PO:COMMIT | 21204 | SIEMENS ENERGY, INC. | 0 | 0 | 333000 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2025-11-16 |  | 0-4005 | BH235 2023 KOMATSU PC88MR-11 EXCAVATOR 2023 KOMATSU PC88MR-11 EXCAVATOR | 0 | 0 |  | BH235 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2025-11-16 |  | 0-4005 | BH235 2023 KOMATSU PC88MR-11 EXCAVATOR 2023 KOMATSU PC88MR-11 EXCAVATOR | 0 | 0 |  | BH235 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2025-11-16 |  | 0-4005 | WLD110 JCB 3TS-8T TRACK LOADER W/ BKT & FORKS JCB 3TS-8T TRACK LOADER W/ BKT & FORKS | 0 | 0 |  | WLD110 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2025-11-16 |  | 0-4005 | WLD110 JCB 3TS-8T TRACK LOADER W/ BKT & FORKS JCB 3TS-8T TRACK LOADER W/ BKT & FORKS | 0 | 0 |  | WLD110 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2025-11-16 |  | 0-4005 | WLD144 SILT FENCE PLOW 48" W/ PUSH PULL DESIGN SILT FENCE PLOW 48" W/ PUSH PULL DESIGN | 0 | 0 |  | WLD144 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2025-11-16 |  | 0-4005 | WLD144 SILT FENCE PLOW 48" W/ PUSH PULL DESIGN SILT FENCE PLOW 48" W/ PUSH PULL DESIGN | 0 | 0 |  | WLD144 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2025-11-23 |  | 0-4005 | BH235 2023 KOMATSU PC88MR-11 EXCAVATOR 2023 KOMATSU PC88MR-11 EXCAVATOR | 0 | 0 |  | BH235 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2025-11-23 |  | 0-4005 | WLD110 JCB 3TS-8T TRACK LOADER W/ BKT & FORKS JCB 3TS-8T TRACK LOADER W/ BKT & FORKS | 0 | 0 |  | WLD110 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2025-11-23 |  | 0-4005 | WLD144 SILT FENCE PLOW 48" W/ PUSH PULL DESIGN SILT FENCE PLOW 48" W/ PUSH PULL DESIGN | 0 | 0 |  | WLD144 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2025-12-07 |  | 0-4005 | WLD110 JCB 3TS-8T TRACK LOADER W/ BKT & FORKS JCB 3TS-8T TRACK LOADER W/ BKT & FORKS | 0 | 0 |  | WLD110 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2025-12-07 |  | 0-4005 | WLD110 JCB 3TS-8T TRACK LOADER W/ BKT & FORKS JCB 3TS-8T TRACK LOADER W/ BKT & FORKS | 0 | 0 |  | WLD110 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-02-28 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-02-28 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-02-28 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-02-28 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-02-28 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-02-28 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-08 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-15 |  | 0-4005 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-15 |  | 0-4005 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-15 |  | 0-4005 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-15 |  | 0-4005 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-15 |  | 0-4005 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-15 |  | 0-4005 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-15 |  | 0-4005 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-15 |  | 0-4005 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-15 |  | 0-4005 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-15 |  | 0-4005 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-15 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-15 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-15 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-15 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-15 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-15 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-15 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4005 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4005 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4005 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4005 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4005 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4005 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4005 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4005 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4005 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4005 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4005 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4005 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-29 |  | 0-4005 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-29 |  | 0-4005 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-29 |  | 0-4005 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-29 |  | 0-4005 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-29 |  | 0-4005 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-29 |  | 0-4005 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-29 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-29 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-29 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-29 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-29 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-29 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-29 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-29 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-29 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-29 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-29 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-29 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-31 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-31 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-31 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-31 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-31 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-03-31 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-05 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-05 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-05 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-05 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-05 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-05 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-05 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-05 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-05 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-05 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-05 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-05 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4005 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4005 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4005 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4005 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4005 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4005 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4005 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4005 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4005 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4005 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4005 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4005 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4005 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4005 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4005 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4005 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4005 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4005 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4005 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4005 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4005 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4005 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4005 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4005 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4005 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4005 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4005 | RT1242 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS | 0 | 0 |  | RT1242 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | RT1481 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1481 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | RT1242 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS | 0 | 0 |  | RT1242 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | RT1481 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1481 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | RT1481 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1481 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | RT1481 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1481 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | RT1481 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1481 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4005 | RT1481 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1481 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4005 | WLV106 2025 FORD F150 XL STX (SAFETY) 2025 FORD F150 XL STX (SAFETY) | 0 | 0 |  | WLV106 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4005 | RT1351 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 2024 CHEVROLET SILVERADO 2500 DIESEL CUSTOM 4X4 | 0 | 0 |  | RT1351 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4005 | TR429 SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR SPARTAN 7X16 CARGO TRAILER W/ RAMP DOOR | 0 | 0 |  | TR429 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4005 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4005 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4005 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4005 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4005 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4005 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4005 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4005 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4005 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4005 | RT1242 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS | 0 | 0 |  | RT1242 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4005 | RT1481 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1481 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4005 | ER |  | ER |  |  | 2025-11-16 |  | 0-4005 | RAT403 RANGER 100 4X4 CREW CAB CART RANGER 100 4X4 CREW CAB CART | 0 | 0 |  | RAT403 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4005 | ER |  | ER |  |  | 2025-11-16 |  | 0-4005 | RAT403 RANGER 100 4X4 CREW CAB CART RANGER 100 4X4 CREW CAB CART | 0 | 0 |  | RAT403 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4005 | ER |  | ER |  |  | 2025-11-16 |  | 0-4005 | RST279 HYPER BASE/ ROVER HYPER BASE/ ROVER | 0 | 0 |  | RST279 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4005 | ER |  | ER |  |  | 2025-11-16 |  | 0-4005 | RST279 HYPER BASE/ ROVER HYPER BASE/ ROVER | 0 | 0 |  | RST279 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4005 | ER |  | ER |  |  | 2025-11-23 |  | 0-4005 | RAT403 RANGER 100 4X4 CREW CAB CART RANGER 100 4X4 CREW CAB CART | 0 | 0 |  | RAT403 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4005 | ER |  | ER |  |  | 2025-11-23 |  | 0-4005 | RAT403 RANGER 100 4X4 CREW CAB CART RANGER 100 4X4 CREW CAB CART | 0 | 0 |  | RAT403 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4005 | ER |  | ER |  |  | 2025-11-23 |  | 0-4005 | RAT403 RANGER 100 4X4 CREW CAB CART RANGER 100 4X4 CREW CAB CART | 0 | 0 |  | RAT403 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4005 | ER |  | ER |  |  | 2025-11-23 |  | 0-4005 | RAT403 RANGER 100 4X4 CREW CAB CART RANGER 100 4X4 CREW CAB CART | 0 | 0 |  | RAT403 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4005 | ER |  | ER |  |  | 2025-11-23 |  | 0-4005 | RAT403 RANGER 100 4X4 CREW CAB CART RANGER 100 4X4 CREW CAB CART | 0 | 0 |  | RAT403 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4005 | ER |  | ER |  |  | 2025-11-23 |  | 0-4005 | RST279 HYPER BASE/ ROVER HYPER BASE/ ROVER | 0 | 0 |  | RST279 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4005 | ER |  | ER |  |  | 2025-11-23 |  | 0-4005 | RST279 HYPER BASE/ ROVER HYPER BASE/ ROVER | 0 | 0 |  | RST279 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4005 | ER |  | ER |  |  | 2025-11-23 |  | 0-4005 | RST279 HYPER BASE/ ROVER HYPER BASE/ ROVER | 0 | 0 |  | RST279 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4005 | ER |  | ER |  |  | 2025-11-23 |  | 0-4005 | RST279 HYPER BASE/ ROVER HYPER BASE/ ROVER | 0 | 0 |  | RST279 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4005 | ER |  | ER |  |  | 2025-11-23 |  | 0-4005 | RST279 HYPER BASE/ ROVER HYPER BASE/ ROVER | 0 | 0 |  | RST279 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4005 | ER |  | ER |  |  | 2025-11-23 |  | 0-4005 | RST279 HYPER BASE/ ROVER HYPER BASE/ ROVER | 0 | 0 |  | RST279 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4005 | ER |  | ER |  |  | 2025-11-30 |  | 0-4005 | RST279 HYPER BASE/ ROVER HYPER BASE/ ROVER | 0 | 0 |  | RST279 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4005 | ER |  | ER |  |  | 2026-04-30 |  | 0-4005 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4005 | ER |  | ER |  |  | 2026-04-30 |  | 0-4005 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4005 | ER |  | ER |  |  | 2026-04-30 |  | 0-4005 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4005 | ER |  | ER |  |  | 2026-04-30 |  | 0-4005 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4005 | ER |  | ER |  |  | 2026-05-10 |  | 0-4005 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-10-15 |  | 0-4005 | PR P2COST 000273 (PR) Summary | 0 | 0 |  |  |  | 0 | 60.03 | 0 | 1
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-10-15 |  | 0-4005 | PR P2COST 000273 (PR) Summary | 0 | 0 |  |  |  | 0 | 60.03 | 0 | 1
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-10-15 |  | 0-4005 | PR P2COST 000273 (PR) Summary | 0 | 0 |  |  |  | 0 | 1236.73 | 0 | 10
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-10-28 |  | 0-4005 | PR P2COST 000274 (PR) Summary | 0 | 0 |  |  |  | 0 | 815.5 | 0 | 9.5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-10-28 |  | 0-4005 | PR P2COST 000274 (PR) Summary | 0 | 0 |  |  |  | 0 | 703.92 | 0 | 8
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-10-28 |  | 0-4005 | PR P2COST 000274 (PR) Summary | 0 | 0 |  |  |  | 0 | 1527.57 | 0 | 17
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-10-28 |  | 0-4005 | PR P2COST 000274 (PR) Summary | 0 | 0 |  |  |  | 0 | 1404.73 | 0 | 16
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-10-28 |  | 0-4005 | PR P2COST 000274 (PR) Summary | 0 | 0 |  |  |  | 0 | 1242.91 | 0 | 14.5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-10-28 |  | 0-4005 | PR P2COST 000274 (PR) Summary | 0 | 0 |  |  |  | 0 | 1349.88 | 0 | 15
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-10-28 |  | 0-4005 | PR P2COST 000274 (PR) Summary | 0 | 0 |  |  |  | 0 | 986.16 | 0 | 11
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-10-28 |  | 0-4005 | PR P2COST 000274 (PR) Summary | 0 | 0 |  |  |  | 0 | 827.43 | 0 | 9
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-10-28 |  | 0-4005 | PR P2COST 000274 (PR) Summary | 0 | 0 |  |  |  | 0 | 827.42 | 0 | 9
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-10-28 |  | 0-4005 | PR P2COST 000274 (PR) Summary | 0 | 0 |  |  |  | 0 | 633.4 | 0 | 7
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-11-11 |  | 0-4005 | PR P2COST 000275 (PR) Summary | 0 | 0 |  |  |  | 0 | 1434.81 | 0 | 16
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-11-11 |  | 0-4005 | PR P2COST 000275 (PR) Summary | 0 | 0 |  |  |  | 0 | 916.29 | 0 | 10.5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-11-11 |  | 0-4005 | PR P2COST 000275 (PR) Summary | 0 | 0 |  |  |  | 0 | 2084.17 | 0 | 22.5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-11-11 |  | 0-4005 | PR P2COST 000275 (PR) Summary | 0 | 0 |  |  |  | 0 | 1660.97 | 0 | 18
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-11-11 |  | 0-4005 | PR P2COST 000275 (PR) Summary | 0 | 0 |  |  |  | 0 | 1248.98 | 0 | 13.5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-11-11 |  | 0-4005 | PR P2COST 000275 (PR) Summary | 0 | 0 |  |  |  | 0 | 802.49 | 0 | 9
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-11-11 |  | 0-4005 | PR P2COST 000275 (PR) Summary | 0 | 0 |  |  |  | 0 | 1248.97 | 0 | 13.5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-11-11 |  | 0-4005 | PR P2COST 000275 (PR) Summary | 0 | 0 |  |  |  | 0 | 1146.81 | 0 | 12.5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-11-11 |  | 0-4005 | PR P2COST 000275 (PR) Summary | 0 | 0 |  |  |  | 0 | 1220.14 | 0 | 13
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-11-11 |  | 0-4005 | PR P2COST 000275 (PR) Summary | 0 | 0 |  |  |  | 0 | 1013.81 | 0 | 11
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-11-20 |  | 0-4005 | PR P0COST 000503 (PR) Summary | 0 | 0 |  |  |  | 0 | 535.49 | 0 | 10
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-11-20 |  | 0-4005 | PR P0COST 000503 (PR) Summary | 0 | 0 |  |  |  | 0 | 535.49 | 0 | 10
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-11-20 |  | 0-4005 | PR P0COST 000503 (PR) Summary | 0 | 0 |  |  |  | 0 | 535.49 | 0 | 10
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-11-20 |  | 0-4005 | PR P0COST 000503 (PR) Summary | 0 | 0 |  |  |  | 0 | 532.99 | 0 | 10
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-11-24 |  | 0-4005 | PR P2COST 000276 (PR) Summary | 0 | 0 |  |  |  | 0 | 1717.45 | 0 | 20
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-11-24 |  | 0-4005 | PR P2COST 000276 (PR) Summary | 0 | 0 |  |  |  | 0 | 2098.49 | 0 | 24
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-11-24 |  | 0-4005 | PR P2COST 000276 (PR) Summary | 0 | 0 |  |  |  | 0 | 1771.04 | 0 | 20
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-11-24 |  | 0-4005 | PR P2COST 000276 (PR) Summary | 0 | 0 |  |  |  | 0 | 1606.44 | 0 | 23.5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-11-24 |  | 0-4005 | PR P2COST 000276 (PR) Summary | 0 | 0 |  |  |  | 0 | 1623.26 | 0 | 18.5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-11-24 |  | 0-4005 | PR P2COST 000276 (PR) Summary | 0 | 0 |  |  |  | 0 | 1825.05 | 0 | 20.5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-11-24 |  | 0-4005 | PR P2COST 000276 (PR) Summary | 0 | 0 |  |  |  | 0 | 1466.13 | 0 | 17
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-11-24 |  | 0-4005 | PR P2COST 000276 (PR) Summary | 0 | 0 |  |  |  | 0 | 2822.4 | 0 | 32
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-11-24 |  | 0-4005 | PR P2COST 000276 (PR) Summary | 0 | 0 |  |  |  | 0 | 1377.39 | 0 | 16
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-11-24 |  | 0-4005 | PR P2COST 000276 (PR) Summary | 0 | 0 |  |  |  | 0 | 1376.5 | 0 | 16
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-11-24 |  | 0-4005 | PR P2COST 000276 (PR) Summary | 0 | 0 |  |  |  | 0 | 825.26 | 0 | 10
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-11-24 |  | 0-4005 | PR P2COST 000276 (PR) Summary | 0 | 0 |  |  |  | 0 | 412.61 | 0 | 5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-11-27 |  | 0-4005 | PR P0COST 000504 (PR) Summary | 0 | 0 |  |  |  | 0 | 519.24 | 0 | 10
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-11-27 |  | 0-4005 | PR P0COST 000504 (PR) Summary | 0 | 0 |  |  |  | 0 | 519.24 | 0 | 10
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-11-27 |  | 0-4005 | PR P0COST 000504 (PR) Summary | 0 | 0 |  |  |  | 0 | 519.24 | 0 | 10
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-11-27 |  | 0-4005 | PR P0COST 000504 (PR) Summary | 0 | 0 |  |  |  | 0 | 519.24 | 0 | 10
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-12-09 |  | 0-4005 | PR P2COST 000277 (PR) Summary | 0 | 0 |  |  |  | 0 | 4186.47 | 0 | 51
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-12-09 |  | 0-4005 | PR P2COST 000277 (PR) Summary | 0 | 0 |  |  |  | 0 | 3810.99 | 0 | 47
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-12-09 |  | 0-4005 | PR P2COST 000277 (PR) Summary | 0 | 0 |  |  |  | 0 | 2143.5 | 0 | 24
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-12-09 |  | 0-4005 | PR P2COST 000277 (PR) Summary | 0 | 0 |  |  |  | 0 | 1791.44 | 0 | 19
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-12-09 |  | 0-4005 | PR P2COST 000277 (PR) Summary | 0 | 0 |  |  |  | 0 | 2823.36 | 0 | 40
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-12-09 |  | 0-4005 | PR P2COST 000277 (PR) Summary | 0 | 0 |  |  |  | 0 | 2643.87 | 0 | 37
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-12-09 |  | 0-4005 | PR P2COST 000277 (PR) Summary | 0 | 0 |  |  |  | 0 | 1772.28 | 0 | 19
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-12-09 |  | 0-4005 | PR P2COST 000277 (PR) Summary | 0 | 0 |  |  |  | 0 | 2852.65 | 0 | 39
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-12-09 |  | 0-4005 | PR P2COST 000277 (PR) Summary | 0 | 0 |  |  |  | 0 | 498.21 | 0 | 6
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-12-09 |  | 0-4005 | PR P2COST 000277 (PR) Summary | 0 | 0 |  |  |  | 0 | 498.21 | 0 | 6
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-12-09 |  | 0-4005 | PR P2COST 000277 (PR) Summary | 0 | 0 |  |  |  | 0 | 1025.07 | 0 | 20
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-12-11 |  | 0-4005 | PR P2COST 000278 (PR) Summary | 0 | 0 |  |  |  | 0 | 2809.65 | 0 | 32
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-12-11 |  | 0-4005 | PR P2COST 000278 (PR) Summary | 0 | 0 |  |  |  | 0 | 1328.21 | 0 | 19
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-12-11 |  | 0-4005 | PR P2COST 000278 (PR) Summary | 0 | 0 |  |  |  | 0 | 1607.08 | 0 | 21
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-12-11 |  | 0-4005 | PR P2COST 000278 (PR) Summary | 0 | 0 |  |  |  | 0 | 1433.56 | 0 | 19
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-12-11 |  | 0-4005 | PR P2COST 000278 (PR) Summary | 0 | 0 |  |  |  | 0 | 2439.35 | 0 | 28
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-12-11 |  | 0-4005 | PR P2COST 000278 (PR) Summary | 0 | 0 |  |  |  | 0 | 1344.76 | 0 | 18
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-12-11 |  | 0-4005 | PR P2COST 000278 (PR) Summary | 0 | 0 |  |  |  | 0 | 390.23 | 0 | 5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-12-11 |  | 0-4005 | PR P2COST 000278 (PR) Summary | 0 | 0 |  |  |  | 0 | 1149.01 | 0 | 16
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-12-11 |  | 0-4005 | PR P2COST 000278 (PR) Summary | 0 | 0 |  |  |  | 0 | 1113.77 | 0 | 15
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-12-11 |  | 0-4005 | PR P2COST 000278 (PR) Summary | 0 | 0 |  |  |  | 0 | 2179.2 | 0 | 24
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-12-11 |  | 0-4005 | PR P2COST 000278 (PR) Summary | 0 | 0 |  |  |  | 0 | 851.53 | 0 | 12
ttJTrans | 0-4005 | LA |  | LA |  |  | 2025-12-11 |  | 0-4005 | PR P2COST 000278 (PR) Summary | 0 | 0 |  |  |  | 0 | 225.35 | 0 | 2
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-01-06 |  | 0-4005 | PR P2COST 000280 (PR) Summary | 0 | 0 |  |  |  | 0 | 1064.47 | 0 | 13
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-01-06 |  | 0-4005 | PR P2COST 000280 (PR) Summary | 0 | 0 |  |  |  | 0 | 1199.04 | 0 | 14
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-01-06 |  | 0-4005 | PR P2COST 000280 (PR) Summary | 0 | 0 |  |  |  | 0 | 1144 | 0 | 14
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-01-06 |  | 0-4005 | PR P2COST 000280 (PR) Summary | 0 | 0 |  |  |  | 0 | 1426.32 | 0 | 16.5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-01-06 |  | 0-4005 | PR P2COST 000280 (PR) Summary | 0 | 0 |  |  |  | 0 | 2795.13 | 0 | 28
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-01-06 |  | 0-4005 | PR P2COST 000280 (PR) Summary | 0 | 0 |  |  |  | 0 | 2135.16 | 0 | 21
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-01-06 |  | 0-4005 | PR P2COST 000280 (PR) Summary | 0 | 0 |  |  |  | 0 | 910.47 | 0 | 11
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-01-06 |  | 0-4005 | PR P2COST 000280 (PR) Summary | 0 | 0 |  |  |  | 0 | 2003.05 | 0 | 19
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-01-06 |  | 0-4005 | PR P2COST 000280 (PR) Summary | 0 | 0 |  |  |  | 0 | 230.28 | 0 | 2
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-01-06 |  | 0-4005 | PR P2COST 000280 (PR) Summary | 0 | 0 |  |  |  | 0 | 172.72 | 0 | 1.5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-01-19 |  | 0-4005 | PR P2COST 000281 (PR) Summary | 0 | 0 |  |  |  | 0 | 3267.49 | 0 | 31
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-01-19 |  | 0-4005 | PR P2COST 000281 (PR) Summary | 0 | 0 |  |  |  | 0 | 3486.6 | 0 | 35
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-01-19 |  | 0-4005 | PR P2COST 000281 (PR) Summary | 0 | 0 |  |  |  | 0 | 3273.09 | 0 | 32.5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-01-19 |  | 0-4005 | PR P2COST 000281 (PR) Summary | 0 | 0 |  |  |  | 0 | 918.96 | 0 | 10
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-01-19 |  | 0-4005 | PR P2COST 000281 (PR) Summary | 0 | 0 |  |  |  | 0 | 536.15 | 0 | 5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-01-19 |  | 0-4005 | PR P2COST 000281 (PR) Summary | 0 | 0 |  |  |  | 0 | 536.15 | 0 | 5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-01-19 |  | 0-4005 | PR P2COST 000281 (PR) Summary | 0 | 0 |  |  |  | 0 | 6245.35 | 0 | 61
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-01-19 |  | 0-4005 | PR P2COST 000281 (PR) Summary | 0 | 0 |  |  |  | 0 | 2165.28 | 0 | 20
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-01-19 |  | 0-4005 | PR P2COST 000281 (PR) Summary | 0 | 0 |  |  |  | 0 | 536.13 | 0 | 5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-01-19 |  | 0-4005 | PR P2COST 000281 (PR) Summary | 0 | 0 |  |  |  | 0 | 398.59 | 0 | 4
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-01-19 |  | 0-4005 | PR P2COST 000281 (PR) Summary | 0 | 0 |  |  |  | 0 | 3257.19 | 0 | 31
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-16 |  | 0-4005 | PR P2COST 000285 (PR) Summary | 0 | 0 |  |  |  | 0 | 5693.27 | 0 | 64.48
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-16 |  | 0-4005 | PR P2COST 000285 (PR) Summary | 0 | 0 |  |  |  | 0 | 4041.33 | 0 | 47.5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-16 |  | 0-4005 | PR P2COST 000285 (PR) Summary | 0 | 0 |  |  |  | 0 | 4365.5 | 0 | 51.39
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-16 |  | 0-4005 | PR P2COST 000285 (PR) Summary | 0 | 0 |  |  |  | 0 | 851.49 | 0 | 10
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-16 |  | 0-4005 | PR P2COST 000285 (PR) Summary | 0 | 0 |  |  |  | 0 | 1498.77 | 0 | 20
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-16 |  | 0-4005 | PR P2COST 000285 (PR) Summary | 0 | 0 |  |  |  | 0 | 7283.46 | 0 | 83.63
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-16 |  | 0-4005 | PR P2COST 000285 (PR) Summary | 0 | 0 |  |  |  | 0 | 3906.27 | 0 | 46.65
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-16 |  | 0-4005 | PR P2COST 000285 (PR) Summary | 0 | 0 |  |  |  | 0 | 3662.34 | 0 | 42.07
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-16 |  | 0-4005 | PR P2COST 000285 (PR) Summary | 0 | 0 |  |  |  | 0 | 52.76 | 0 | 0.73
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-02 |  | 0-4005 | PR P2COST 000284 (PR) Summary | 0 | 0 |  |  |  | 0 | 4612.79 | 0 | 51
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-02 |  | 0-4005 | PR P2COST 000284 (PR) Summary | 0 | 0 |  |  |  | 0 | 4760.37 | 0 | 52
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-02 |  | 0-4005 | PR P2COST 000284 (PR) Summary | 0 | 0 |  |  |  | 0 | 3142.37 | 0 | 37
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-02 |  | 0-4005 | PR P2COST 000284 (PR) Summary | 0 | 0 |  |  |  | 0 | 3031.63 | 0 | 35
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-02 |  | 0-4005 | PR P2COST 000284 (PR) Summary | 0 | 0 |  |  |  | 0 | 3715.12 | 0 | 44
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-02 |  | 0-4005 | PR P2COST 000284 (PR) Summary | 0 | 0 |  |  |  | 0 | 846.18 | 0 | 10
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-02 |  | 0-4005 | PR P2COST 000284 (PR) Summary | 0 | 0 |  |  |  | 0 | 3988.4 | 0 | 46
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-02 |  | 0-4005 | PR P2COST 000284 (PR) Summary | 0 | 0 |  |  |  | 0 | 1073.18 | 0 | 12
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-02 |  | 0-4005 | PR P2COST 000284 (PR) Summary | 0 | 0 |  |  |  | 0 | 3267.34 | 0 | 38
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-02 |  | 0-4005 | PR P2COST 000284 (PR) Summary | 0 | 0 |  |  |  | 0 | 3685.43 | 0 | 42
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-02 |  | 0-4005 | PR P2COST 000284 (PR) Summary | 0 | 0 |  |  |  | 0 | 3038.9 | 0 | 36
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-02 |  | 0-4005 | PR P2COST 000284 (PR) Summary | 0 | 0 |  |  |  | 0 | 2477.79 | 0 | 30
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-16 |  | 0-4005 | PR P2COST 000285 (PR) Summary | 0 | 0 |  |  |  | 0 | 5615.66 | 0 | 65.61
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-16 |  | 0-4005 | PR P2COST 000285 (PR) Summary | 0 | 0 |  |  |  | 0 | 4071.47 | 0 | 47.47
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-16 |  | 0-4005 | PR P2COST 000285 (PR) Summary | 0 | 0 |  |  |  | 0 | 4693.98 | 0 | 54.46
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-16 |  | 0-4005 | PR P2COST 000285 (PR) Summary | 0 | 0 |  |  |  | 0 | 5728.07 | 0 | 66.83
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-26 |  | 0-4005 | PR P0COST 000518 (PR) Summary | 0 | 0 |  |  |  | 0 | 899.66 | 0 | 8
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-26 |  | 0-4005 | PR P0COST 000518 (PR) Summary | 0 | 0 |  |  |  | 0 | 899.66 | 0 | 8
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-26 |  | 0-4005 | PR P0COST 000518 (PR) Summary | 0 | 0 |  |  |  | 0 | 899.66 | 0 | 8
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-26 |  | 0-4005 | PR P0COST 000518 (PR) Summary | 0 | 0 |  |  |  | 0 | 899.66 | 0 | 8
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-26 |  | 0-4005 | PR P0COST 000518 (PR) Summary | 0 | 0 |  |  |  | 0 | 899.69 | 0 | 8
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-02 |  | 0-4005 | PR P2COST 000286 (PR) Summary | 0 | 0 |  |  |  | 0 | 6838.18 | 0 | 73.38
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-02 |  | 0-4005 | PR P2COST 000286 (PR) Summary | 0 | 0 |  |  |  | 0 | 7209.73 | 0 | 76.03
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-02 |  | 0-4005 | PR P2COST 000286 (PR) Summary | 0 | 0 |  |  |  | 0 | 1434.59 | 0 | 16.5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-02 |  | 0-4005 | PR P2COST 000286 (PR) Summary | 0 | 0 |  |  |  | 0 | 5394.44 | 0 | 63.23
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-02 |  | 0-4005 | PR P2COST 000286 (PR) Summary | 0 | 0 |  |  |  | 0 | 1435.57 | 0 | 16.5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-02 |  | 0-4005 | PR P2COST 000286 (PR) Summary | 0 | 0 |  |  |  | 0 | 4521.21 | 0 | 50.55
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-02 |  | 0-4005 | PR P2COST 000286 (PR) Summary | 0 | 0 |  |  |  | 0 | 5053.41 | 0 | 60.9
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-02 |  | 0-4005 | PR P2COST 000286 (PR) Summary | 0 | 0 |  |  |  | 0 | 3494.61 | 0 | 39.14
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-02 |  | 0-4005 | PR P2COST 000286 (PR) Summary | 0 | 0 |  |  |  | 0 | 4119.91 | 0 | 48.55
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-02 |  | 0-4005 | PR P2COST 000286 (PR) Summary | 0 | 0 |  |  |  | 0 | 5503.2 | 0 | 64.02
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-02 |  | 0-4005 | PR P2COST 000286 (PR) Summary | 0 | 0 |  |  |  | 0 | 4188.25 | 0 | 51.3
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-02 |  | 0-4005 | PR P2COST 000286 (PR) Summary | 0 | 0 |  |  |  | 0 | 6606.47 | 0 | 83.5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-02 |  | 0-4005 | PR P2COST 000286 (PR) Summary | 0 | 0 |  |  |  | 0 | 6852.13 | 0 | 80.27
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-16 |  | 0-4005 | PR P2COST 000287 (PR) Summary | 0 | 0 |  |  |  | 0 | 7364.87 | 0 | 81.13
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-16 |  | 0-4005 | PR P2COST 000287 (PR) Summary | 0 | 0 |  |  |  | 0 | 6245.73 | 0 | 72.16
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-16 |  | 0-4005 | PR P2COST 000287 (PR) Summary | 0 | 0 |  |  |  | 0 | 9508.22 | 0 | 114.67
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-05 |  | 0-4005 | PR P0COST 000520 (PR) Summary | 0 | 0 |  |  |  | 0 | 912.66 | 0 | 8
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-05 |  | 0-4005 | PR P0COST 000520 (PR) Summary | 0 | 0 |  |  |  | 0 | 912.66 | 0 | 8
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-05 |  | 0-4005 | PR P0COST 000520 (PR) Summary | 0 | 0 |  |  |  | 0 | 912.66 | 0 | 8
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-05 |  | 0-4005 | PR P0COST 000520 (PR) Summary | 0 | 0 |  |  |  | 0 | 912.66 | 0 | 8
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-05 |  | 0-4005 | PR P0COST 000520 (PR) Summary | 0 | 0 |  |  |  | 0 | 912.69 | 0 | 8
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-16 |  | 0-4005 | PR P2COST 000287 (PR) Summary | 0 | 0 |  |  |  | 0 | 549.85 | 0 | 8
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-16 |  | 0-4005 | PR P2COST 000287 (PR) Summary | 0 | 0 |  |  |  | 0 | 549.82 | 0 | 8
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-16 |  | 0-4005 | PR P2COST 000287 (PR) Summary | 0 | 0 |  |  |  | 0 | 549.85 | 0 | 8
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-16 |  | 0-4005 | PR P2COST 000287 (PR) Summary | 0 | 0 |  |  |  | 0 | 593.96 | 0 | 6.5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-16 |  | 0-4005 | PR P2COST 000287 (PR) Summary | 0 | 0 |  |  |  | 0 | 4942.33 | 0 | 62.04
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-16 |  | 0-4005 | PR P2COST 000287 (PR) Summary | 0 | 0 |  |  |  | 0 | 9069.15 | 0 | 108.9
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-16 |  | 0-4005 | PR P2COST 000287 (PR) Summary | 0 | 0 |  |  |  | 0 | 6800.09 | 0 | 83.29
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-16 |  | 0-4005 | PR P2COST 000287 (PR) Summary | 0 | 0 |  |  |  | 0 | 1385.12 | 0 | 18.5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-16 |  | 0-4005 | PR P2COST 000287 (PR) Summary | 0 | 0 |  |  |  | 0 | 8223.51 | 0 | 91.37
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-16 |  | 0-4005 | PR P2COST 000287 (PR) Summary | 0 | 0 |  |  |  | 0 | 6651.02 | 0 | 78.1
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-16 |  | 0-4005 | PR P2COST 000287 (PR) Summary | 0 | 0 |  |  |  | 0 | 7433.13 | 0 | 94.01
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-16 |  | 0-4005 | PR P2COST 000287 (PR) Summary | 0 | 0 |  |  |  | 0 | 8410.4 | 0 | 106.08
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-16 |  | 0-4005 | PR P2COST 000287 (PR) Summary | 0 | 0 |  |  |  | 0 | 549.75 | 0 | 8
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-16 |  | 0-4005 | PR P2COST 000287 (PR) Summary | 0 | 0 |  |  |  | 0 | 549.85 | 0 | 8
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-16 |  | 0-4005 | PR P2COST 000287 (PR) Summary | 0 | 0 |  |  |  | 0 | 549.82 | 0 | 8
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-16 |  | 0-4005 | PR P2COST 000287 (PR) Summary | 0 | 0 |  |  |  | 0 | 549.85 | 0 | 8
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-16 |  | 0-4005 | PR P2COST 000287 (PR) Summary | 0 | 0 |  |  |  | 0 | 549.85 | 0 | 8
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-16 |  | 0-4005 | PR P2COST 000287 (PR) Summary | 0 | 0 |  |  |  | 0 | 549.85 | 0 | 8
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-16 |  | 0-4005 | PR P2COST 000287 (PR) Summary | 0 | 0 |  |  |  | 0 | 549.85 | 0 | 8
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-12 |  | 0-4005 | PR P0COST 000521 (PR) Summary | 0 | 0 |  |  |  | 0 | 603.07 | 0 | 10
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-12 |  | 0-4005 | PR P0COST 000521 (PR) Summary | 0 | 0 |  |  |  | 0 | 603.05 | 0 | 10
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-12 |  | 0-4005 | PR P0COST 000521 (PR) Summary | 0 | 0 |  |  |  | 0 | 1359.64 | 0 | 18
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-12 |  | 0-4005 | PR P0COST 000521 (PR) Summary | 0 | 0 |  |  |  | 0 | 1359.64 | 0 | 18
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-12 |  | 0-4005 | PR P0COST 000521 (PR) Summary | 0 | 0 |  |  |  | 0 | 1359.64 | 0 | 18
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-12 |  | 0-4005 | PR P0COST 000521 (PR) Summary | 0 | 0 |  |  |  | 0 | 1359.64 | 0 | 18
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-12 |  | 0-4005 | PR P0COST 000521 (PR) Summary | 0 | 0 |  |  |  | 0 | 899.69 | 0 | 8
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-19 |  | 0-4005 | PR P0COST 000522 (PR) Summary | 0 | 0 |  |  |  | 0 | 1163.93 | 0 | 20
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-19 |  | 0-4005 | PR P0COST 000522 (PR) Summary | 0 | 0 |  |  |  | 0 | 1163.9 | 0 | 20
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-19 |  | 0-4005 | PR P0COST 000522 (PR) Summary | 0 | 0 |  |  |  | 0 | 1741.62 | 0 | 28
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-19 |  | 0-4005 | PR P0COST 000522 (PR) Summary | 0 | 0 |  |  |  | 0 | 1345.55 | 0 | 18
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-19 |  | 0-4005 | PR P0COST 000522 (PR) Summary | 0 | 0 |  |  |  | 0 | 1344.8 | 0 | 18
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-19 |  | 0-4005 | PR P0COST 000522 (PR) Summary | 0 | 0 |  |  |  | 0 | 1344.05 | 0 | 18
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-19 |  | 0-4005 | PR P0COST 000522 (PR) Summary | 0 | 0 |  |  |  | 0 | 889.84 | 0 | 8
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-30 |  | 0-4005 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 11206.89 | 0 | 150.16
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-30 |  | 0-4005 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 10045.89 | 0 | 126
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-30 |  | 0-4005 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 11672.56 | 0 | 154.05
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-30 |  | 0-4005 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 12190.22 | 0 | 156.04
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-30 |  | 0-4005 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 10043.27 | 0 | 141
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-30 |  | 0-4005 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 9814.81 | 0 | 130.5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-30 |  | 0-4005 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 13786.75 | 0 | 168
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-30 |  | 0-4005 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 10181.8 | 0 | 128.5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-30 |  | 0-4005 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 10434.09 | 0 | 127.5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-30 |  | 0-4005 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 11242.67 | 0 | 135
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-30 |  | 0-4005 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 2433.25 | 0 | 46.5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-30 |  | 0-4005 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 3085.15 | 0 | 45
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-26 |  | 0-4005 | PR P0COST 000523 (PR) Summary | 0 | 0 |  |  |  | 0 | 1772.58 | 0 | 28
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-26 |  | 0-4005 | PR P0COST 000523 (PR) Summary | 0 | 0 |  |  |  | 0 | 1772.58 | 0 | 28
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-26 |  | 0-4005 | PR P0COST 000523 (PR) Summary | 0 | 0 |  |  |  | 0 | 2202.09 | 0 | 38
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-26 |  | 0-4005 | PR P0COST 000523 (PR) Summary | 0 | 0 |  |  |  | 0 | 2359.77 | 0 | 38
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-02 |  | 0-4005 | PR P0COST 000524 (PR) Summary | 0 | 0 |  |  |  | 0 | 567.35 | 0 | 10
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-02 |  | 0-4005 | PR P0COST 000524 (PR) Summary | 0 | 0 |  |  |  | 0 | 567.34 | 0 | 10
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-02 |  | 0-4005 | PR P0COST 000524 (PR) Summary | 0 | 0 |  |  |  | 0 | 1947.69 | 0 | 28
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-02 |  | 0-4005 | PR P0COST 000524 (PR) Summary | 0 | 0 |  |  |  | 0 | 1550.12 | 0 | 18
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-02 |  | 0-4005 | PR P0COST 000524 (PR) Summary | 0 | 0 |  |  |  | 0 | 1550.12 | 0 | 18
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-02 |  | 0-4005 | PR P0COST 000524 (PR) Summary | 0 | 0 |  |  |  | 0 | 1550.12 | 0 | 18
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-02 |  | 0-4005 | PR P0COST 000524 (PR) Summary | 0 | 0 |  |  |  | 0 | 902.84 | 0 | 8
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-09 |  | 0-4005 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 524.49 | 0 | 10
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-09 |  | 0-4005 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 1408.31 | 0 | 20
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-09 |  | 0-4005 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 1994.78 | 0 | 28
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-09 |  | 0-4005 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 1625.76 | 0 | 18
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-09 |  | 0-4005 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 1625.78 | 0 | 18
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-09 |  | 0-4005 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 1625.78 | 0 | 18
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-09 |  | 0-4005 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 1625.81 | 0 | 8
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-14 |  | 0-4005 | PR P2COST 000289 (PR) Summary | 0 | 0 |  |  |  | 0 | 11132.37 | 0 | 136.5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-14 |  | 0-4005 | PR P2COST 000289 (PR) Summary | 0 | 0 |  |  |  | 0 | 10692.64 | 0 | 129.11
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-14 |  | 0-4005 | PR P2COST 000289 (PR) Summary | 0 | 0 |  |  |  | 0 | 10807.98 | 0 | 129.03
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-14 |  | 0-4005 | PR P2COST 000289 (PR) Summary | 0 | 0 |  |  |  | 0 | 11260.82 | 0 | 134.02
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-14 |  | 0-4005 | PR P2COST 000289 (PR) Summary | 0 | 0 |  |  |  | 0 | 10735.75 | 0 | 131.56
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-14 |  | 0-4005 | PR P2COST 000289 (PR) Summary | 0 | 0 |  |  |  | 0 | 2671.38 | 0 | 33
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-14 |  | 0-4005 | PR P2COST 000289 (PR) Summary | 0 | 0 |  |  |  | 0 | 9624.52 | 0 | 113.25
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-14 |  | 0-4005 | PR P2COST 000289 (PR) Summary | 0 | 0 |  |  |  | 0 | 10612.35 | 0 | 125.49
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-14 |  | 0-4005 | PR P2COST 000289 (PR) Summary | 0 | 0 |  |  |  | 0 | 11087.85 | 0 | 127.22
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-14 |  | 0-4005 | PR P2COST 000289 (PR) Summary | 0 | 0 |  |  |  | 0 | 9891.52 | 0 | 121.47
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-14 |  | 0-4005 | PR P2COST 000289 (PR) Summary | 0 | 0 |  |  |  | 0 | 2356 | 0 | 32
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-14 |  | 0-4005 | PR P2COST 000289 (PR) Summary | 0 | 0 |  |  |  | 0 | 1223.39 | 0 | 14
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-16 |  | 0-4005 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 567.35 | 0 | 10
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-16 |  | 0-4005 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 567.34 | 0 | 10
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-16 |  | 0-4005 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 2227.09 | 0 | 38
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-16 |  | 0-4005 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 1532.99 | 0 | 18
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-16 |  | 0-4005 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 1533 | 0 | 18
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-16 |  | 0-4005 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 889.81 | 0 | 8
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-16 |  | 0-4005 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 1829.53 | 0 | 18
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-07 |  | 0-4005 | PR P2COST 000291 (PR) Summary | 0 | 0 |  |  |  | 0 | 1960 | 0 | 0
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-23 |  | 0-4005 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 567.35 | 0 | 10
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-23 |  | 0-4005 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 567.34 | 0 | 10
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-23 |  | 0-4005 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 2091.34 | 0 | 28
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-23 |  | 0-4005 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 1693.79 | 0 | 18
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-23 |  | 0-4005 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 1693.79 | 0 | 18
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-23 |  | 0-4005 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 1693.8 | 0 | 18
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-23 |  | 0-4005 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 889.84 | 0 | 8
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-27 |  | 0-4005 | PR P2COST 000290 (PR) Summary | 0 | 0 |  |  |  | 0 | 12216.65 | 0 | 154
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-27 |  | 0-4005 | PR P2COST 000290 (PR) Summary | 0 | 0 |  |  |  | 0 | 9744.51 | 0 | 121.5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-27 |  | 0-4005 | PR P2COST 000290 (PR) Summary | 0 | 0 |  |  |  | 0 | 7867.8 | 0 | 101.5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-27 |  | 0-4005 | PR P2COST 000290 (PR) Summary | 0 | 0 |  |  |  | 0 | 1483.04 | 0 | 20
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-27 |  | 0-4005 | PR P2COST 000290 (PR) Summary | 0 | 0 |  |  |  | 0 | 12848.76 | 0 | 164
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-27 |  | 0-4005 | PR P2COST 000290 (PR) Summary | 0 | 0 |  |  |  | 0 | 15817.78 | 0 | 198.07
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-27 |  | 0-4005 | PR P2COST 000290 (PR) Summary | 0 | 0 |  |  |  | 0 | 13721.68 | 0 | 173
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-27 |  | 0-4005 | PR P2COST 000290 (PR) Summary | 0 | 0 |  |  |  | 0 | 11199.78 | 0 | 147
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-27 |  | 0-4005 | PR P2COST 000290 (PR) Summary | 0 | 0 |  |  |  | 0 | 2845.54 | 0 | 37
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-27 |  | 0-4005 | PR P2COST 000290 (PR) Summary | 0 | 0 |  |  |  | 0 | 11721.96 | 0 | 141.5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-27 |  | 0-4005 | PR P2COST 000290 (PR) Summary | 0 | 0 |  |  |  | 0 | 12390.3 | 0 | 146.5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-27 |  | 0-4005 | PR P2COST 000290 (PR) Summary | 0 | 0 |  |  |  | 0 | 14547.78 | 0 | 171.71
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-27 |  | 0-4005 | PR P2COST 000290 (PR) Summary | 0 | 0 |  |  |  | 0 | 389.75 | 0 | 0
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-30 |  | 0-4005 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 2907.32 | 0 | 46
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-30 |  | 0-4005 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 2907.32 | 0 | 46
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-30 |  | 0-4005 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 2907.32 | 0 | 46
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-30 |  | 0-4005 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 1257.63 | 0 | 15
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-30 |  | 0-4005 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 2520.67 | 0 | 36
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-30 |  | 0-4005 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 2029.99 | 0 | 16
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-08 |  | 0-4005 | COST CODE TRANSFER 25-4005 | 0 | 0 |  |  |  | 0 | 647.3 | 0 | 10
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-08 |  | 0-4005 | COST CODE TRANSFER 25-4005 | 0 | 0 |  |  |  | 0 | 889.84 | 0 | 8
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-08 |  | 0-4005 | COST CODE TRANSFER 25-4005 | 0 | 0 |  |  |  | 0 | 13092.02 | 0 | 128
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-08 |  | 0-4005 | COST CODE TRANSFER 25-4005 | 0 | 0 |  |  |  | 0 | 3928.43 | 0 | 40
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-08 |  | 0-4005 | COST CODE TRANSFER 25-4005 | 0 | 0 |  |  |  | 0 | 1460.45 | 0 | 20
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-08 |  | 0-4005 | COST CODE TRANSFER 25-4005 | 0 | 0 |  |  |  | 0 | 2184.8 | 0 | 20
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-08 |  | 0-4005 | COST CODE TRANSFER 25-4005 | 0 | 0 |  |  |  | 0 | 2935.8 | 0 | 30
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-08 |  | 0-4005 | COST CODE TRANSFER 25-4005 | 0 | 0 |  |  |  | 0 | 3291.21 | 0 | 50
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-08 |  | 0-4005 | COST CODE TRANSFER 25-4005 | 0 | 0 |  |  |  | 0 | 780.31 | 0 | 20
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-08 |  | 0-4005 | COST CODE TRANSFER 25-4005 | 0 | 0 |  |  |  | 0 | 2287.4 | 0 | 40
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-07 |  | 0-4005 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 1661.09 | 0 | 20
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-07 |  | 0-4005 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 1996.78 | 0 | 24
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-07 |  | 0-4005 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 3691.3 | 0 | 56
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-07 |  | 0-4005 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 3100.85 | 0 | 46
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-07 |  | 0-4005 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 3100.85 | 0 | 46
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-07 |  | 0-4005 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 3099.04 | 0 | 46
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-07 |  | 0-4005 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 537.67 | 0 | 0
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-07 |  | 0-4005 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 2472 | 0 | 26
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-12 |  | 0-4005 | PR P2COST 000292 (PR) Summary | 0 | 0 |  |  |  | 0 | 12295.32 | 0 | 142
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-12 |  | 0-4005 | PR P2COST 000292 (PR) Summary | 0 | 0 |  |  |  | 0 | 14780.19 | 0 | 186.5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-12 |  | 0-4005 | PR P2COST 000292 (PR) Summary | 0 | 0 |  |  |  | 0 | 14017.36 | 0 | 181
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-12 |  | 0-4005 | PR P2COST 000292 (PR) Summary | 0 | 0 |  |  |  | 0 | 14451.45 | 0 | 185.5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-12 |  | 0-4005 | PR P2COST 000292 (PR) Summary | 0 | 0 |  |  |  | 0 | 2057.1 | 0 | 27
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-12 |  | 0-4005 | PR P2COST 000292 (PR) Summary | 0 | 0 |  |  |  | 0 | 8948.97 | 0 | 109
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-12 |  | 0-4005 | PR P2COST 000292 (PR) Summary | 0 | 0 |  |  |  | 0 | 11479.65 | 0 | 141.76
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-12 |  | 0-4005 | PR P2COST 000292 (PR) Summary | 0 | 0 |  |  |  | 0 | 9619.77 | 0 | 120.5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-12 |  | 0-4005 | PR P2COST 000292 (PR) Summary | 0 | 0 |  |  |  | 0 | 9598.19 | 0 | 121
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-12 |  | 0-4005 | PR P2COST 000292 (PR) Summary | 0 | 0 |  |  |  | 0 | 981.22 | 0 | 13
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-12 |  | 0-4005 | PR P2COST 000292 (PR) Summary | 0 | 0 |  |  |  | 0 | 758.02 | 0 | 10
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-12 |  | 0-4005 | PR P2COST 000292 (PR) Summary | 0 | 0 |  |  |  | 0 | 9509.77 | 0 | 117.5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-12 |  | 0-4005 | PR P2COST 000292 (PR) Summary | 0 | 0 |  |  |  | 0 | 11195.87 | 0 | 141.33
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-14 |  | 0-4005 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 1618.18 | 0 | 20
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-14 |  | 0-4005 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 2265.74 | 0 | 28
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-14 |  | 0-4005 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 2885.32 | 0 | 46
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-14 |  | 0-4005 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 2323.02 | 0 | 36
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-14 |  | 0-4005 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 2323.02 | 0 | 36
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-14 |  | 0-4005 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 1717.32 | 0 | 26
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-14 |  | 0-4005 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 1717.35 | 0 | 16
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-14 |  | 0-4005 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 1281.63 | 0 | 0
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-21 |  | 0-4005 | PR P0COST 000531 (PR) Summary | 0 | 0 |  |  |  | 0 | 4908.84 | 0 | 70
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-21 |  | 0-4005 | PR P0COST 000531 (PR) Summary | 0 | 0 |  |  |  | 0 | 5625.37 | 0 | 80
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-21 |  | 0-4005 | PR P0COST 000531 (PR) Summary | 0 | 0 |  |  |  | 0 | 4120.3 | 0 | 60
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-21 |  | 0-4005 | PR P0COST 000531 (PR) Summary | 0 | 0 |  |  |  | 0 | 4699.86 | 0 | 68
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-21 |  | 0-4005 | PR P0COST 000531 (PR) Summary | 0 | 0 |  |  |  | 0 | 2813.49 | 0 | 18
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-21 |  | 0-4005 | PR P0COST 000531 (PR) Summary | 0 | 0 |  |  |  | 0 | 647.55 | 0 | 8
ttJTrans | 0-4005 | OC |  | OC |  |  | 2025-11-02 |  | 0-4005 | TRAVELER G BIGLER 11/16/25 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 609.99 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2025-11-22 |  | 0-4005 | TRAVEL E ROJAS 11/15/25 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20.1 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2025-11-22 |  | 0-4005 | TRAVEL J TODD 11/13/25 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20.1 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2025-11-22 |  | 0-4005 | TRAVEL J RION 11/14/25 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20.1 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2025-11-22 |  | 0-4005 | TRAVEL K BELTRAN11/13/25 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20.1 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2025-11-22 |  | 0-4005 | TRAVEL E ROJAS 11/13/25 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20.1 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2025-11-22 |  | 0-4005 | TRAVEL J FLEMING 11/16/25 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20.1 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2025-11-22 |  | 0-4005 | TRAVEL J ROJAS 11/13/25 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20.1 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2025-12-04 |  | 0-4005 | TRAVEL E ROJAS 11/15/25 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 428.59 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2025-12-04 |  | 0-4005 | TRAVEL J RION 11/14/25 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 774.14 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2025-12-04 |  | 0-4005 | TRAVEL J TODD 11/14/25 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 40.2 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2025-12-04 |  | 0-4005 | TRAVEL K BELTRAM 11/15/25 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20.1 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2025-12-01 |  | 0-4005 | TRAVEL G BIGLER 11/16/25 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 660.95 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2025-12-01 |  | 0-4005 | TRAVEL K BELTRAN 11/13/25 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 279.95 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2025-12-01 |  | 0-4005 | TRAVEL E ROJAS 11/13/25 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 317.98 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2025-12-01 |  | 0-4005 | TRAVEL J TODD 11/13/25 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 159.73 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2025-12-01 |  | 0-4005 | TRAVEL J ROJAS 11/13/25 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 319.47 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2025-12-09 |  | 0-4005 | TRAVEL J TODD 11/14/25 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 147.63 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2025-12-09 |  | 0-4005 | TRAVEL J ROJAS 11/15/25 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20.1 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2025-12-09 |  | 0-4005 | TRAVEL J FLEMMING 11/16/25 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 1360.51 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-01-20 |  | 0-4005 | WEEKLY SHIPPING INVOICE | 0 | 0 |  | 12681 | FEDERAL EXPRESS CORPORATION | 0 | 40.06 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-01-23 |  | 0-4005 | COMDATA 12/29/25 (SP) STARLINK INTERNET 12/21/25 | 0 | 0 |  | 2230 |  | 0 | 165 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-01-29 |  | 0-4005 | WEEKLY SHIPPING INVOICE | 0 | 0 |  | 12681 | FEDERAL EXPRESS CORPORATION | 0 | 22.5 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-02-09 |  | 0-4005 | DISA 2935584 FROM PREPAID | 0 | 0 |  |  |  | 0 | 83.5 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-02-18 |  | 0-4005 | WEEKLY SHIPPING INVOICE | 0 | 0 |  | 12681 | FEDERAL EXPRESS CORPORATION | 0 | 672.47 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-03-12 |  | 0-4005 | TRAVEL G BIGLER 3/15/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 850.99 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-03-12 |  | 0-4005 | TRAVEL J STEELMAN 3/10/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 1006.42 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-03-12 |  | 0-4005 | TRAVEL J BARTLES 3/9/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 1033.05 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-03-12 |  | 0-4005 | TRAVEL J RION 3/9/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20.1 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-03-12 |  | 0-4005 | TRAVEL L COOLEY 2/26/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 156.72 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-03-12 |  | 0-4005 | TRAVEL J STEELMAN 2/26/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 141.98 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-03-12 |  | 0-4005 | TRAVEL L BIVENS 3/9/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 333.01 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-03-12 |  | 0-4005 | TRAVEL J RION 2/26/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 144.82 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-03-05 |  | 0-4005 | WEEKLY SHIPPING INVOICE | 0 | 0 |  | 12681 | FEDERAL EXPRESS CORPORATION | 0 | 333.46 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-01 |  | 0-4005 | COMDATA 3/16/26 (LB) IAH WHATABURGER 3/06/26 | 0 | 0 |  | 2265 |  | 0 | 11.32 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-01 |  | 0-4005 | COMDATA 3/16/26 (EU) CVS/PHARMACY #06738 3/10/26 | 0 | 0 |  | 2265 |  | 0 | 17.89 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-01 |  | 0-4005 | COMDATA 3/16/26 (EU) MILAM DONUT SHOP 3/11/26 | 0 | 0 |  | 2265 |  | 0 | 32 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-01 |  | 0-4005 | COMDATA 3/16/26 (EU) HINZES BARBQUE 3/11/26 | 0 | 0 |  | 2265 |  | 0 | 235.99 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-01 |  | 0-4005 | COMDATA 3/16/26 (EU) PIZZA HUT 061673 3/12/26 | 0 | 0 |  | 2265 |  | 0 | 83.58 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-01 |  | 0-4005 | COMDATA 3/16/26 (EU) MILAM DONUT SHOP 3/12/26 | 0 | 0 |  | 2265 |  | 0 | 12.53 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-01 |  | 0-4005 | COMDATA 3/16/26 (LB) MEMPHISSHELBYAIRPORT 3/13/26 | 0 | 0 |  | 2265 |  | 0 | 45 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-01 |  | 0-4005 | COMDATA 3/16/26 (DQ) HAMPTON INN 3/12/26 | 0 | 0 |  | 2265 |  | 0 | 492.34 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-01 |  | 0-4005 | COMDATA 3/16/26 (JRION) O'REILLY 417 3/09/26 | 0 | 0 |  | 2265 |  | 0 | 19.47 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-01 |  | 0-4005 | COMDATA 3/16/26 (JRION) 02855 - SPRINGFIELD BR 3/12/26 | 0 | 0 |  | 2265 |  | 0 | 70 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-01 |  | 0-4005 | COMDATA 3/16/26 (EU) 9ER'S GRILL @ WHARTON 3/10/26 | 0 | 0 |  | 2265 |  | 0 | 239.82 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-01 |  | 0-4005 | COMDATA 3/16/26 (LB) UNITED 3/08/26 | 0 | 0 |  | 2265 |  | 0 | 40 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-01 |  | 0-4005 | COMDATA 3/16/26 (LB) LA CASONA MEXICAN REST 3/09/26 | 0 | 0 |  | 2265 |  | 0 | 86.03 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-01 |  | 0-4005 | COMDATA 3/16/26 (LB) 9ER'S GRILL @ WHARTON 3/11/26 | 0 | 0 |  | 2265 |  | 0 | 63.41 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-01 |  | 0-4005 | COMDATA 3/16/26 (LB) SALTGRASS ROCKWALL 3/12/26 | 0 | 0 |  | 2265 |  | 0 | 222.87 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-01 |  | 0-4005 | COMDATA 3/16/26 (LB) KYOTO JAPANESE STEAKHO 3/12/26 | 0 | 0 |  | 2265 |  | 0 | 212.67 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-01 |  | 0-4005 | COMDATA 3/16/26 (JB) RDUAA PUBLIC PARKING 3/12/26 | 0 | 0 |  | 2265 |  | 0 | 78.75 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-03-23 |  | 0-4005 | JOHN STEELMAN EXPENSE REPORT | 0 | 0 |  | 21331 | STEELMAN, JOHN D | 0 | 522.98 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-03-31 |  | 0-4005 | COMDATA 3/09/26 (DQ) HAMPTON INN 2/27/26 | 0 | 0 |  | 2264 |  | 0 | 298.28 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-03-31 |  | 0-4005 | COMDATA 3/09/26 (AS) HAMPTON INN 2/27/26 | 0 | 0 |  | 2264 |  | 0 | 146.58 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-03-31 |  | 0-4005 | TRAVEL J STEELMAN 3/10/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 205.32 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-01 |  | 0-4005 | JOHN STEELMAN EXPENSE REPORT | 0 | 0 |  | 21331 | STEELMAN, JOHN D | 0 | 298.57 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-01 |  | 0-4005 | NICK SALINAS EXPENSE REPORT | 0 | 0 |  | 13193 | SALINAS, NICHOLAS A | 0 | 408 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-01 |  | 0-4005 | CAR RENTAL J STEELMAN 3/10/26 | 0 | 0 |  | 18873 | EAN SERVICES, LLC | 0 | 173.12 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-30 |  | 0-4005 | 1258 FM 442 ANNUAL EXTINGUISHER INSPECTION | 0 | 0 |  | 21395 | ALLIED FIRE PROTECTION, LLC | 0 | 350 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-28 |  | 0-4005 | COMDATA 4/20/26 (EU) SQ *ABC SAFETY SOLUTIO 4/17/26 | 0 | 0 |  | 2294 |  | 0 | 525 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-28 |  | 0-4005 | COMDATA 4/13/26 (EU) MILAM DONUT SHOP 4/06/26 | 0 | 0 |  | 2293 |  | 0 | 12.53 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-28 |  | 0-4005 | COMDATA 4/13/26 (EU) DOLLAR-GENERAL #3445 4/06/26 | 0 | 0 |  | 2293 |  | 0 | 22.3 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-28 |  | 0-4005 | COMDATA 4/13/26 (EU) MILAM DONUT SHOP 4/07/26 | 0 | 0 |  | 2293 |  | 0 | 16.5 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-28 |  | 0-4005 | COMDATA 4/13/26 (EU) HINZE COUNTRY KITCHEN 4/07/26 | 0 | 0 |  | 2293 |  | 0 | 129.35 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-07 |  | 0-4005 | WEEKLY SHIPPING INVOICE | 0 | 0 |  | 12681 | FEDERAL EXPRESS CORPORATION | 0 | 71.66 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-20 |  | 0-4005 | NECS INVOICE 108206 | 0 | 0 |  |  |  | 0 | 23.25 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-13 |  | 0-4005 | WEEKLY SHIPPING INVOICE | 0 | 0 |  | 12681 | FEDERAL EXPRESS CORPORATION | 0 | 31.54 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-14 |  | 0-4005 | AT&T INVOICE 820105662X04032026 | 0 | 0 |  |  |  | 0 | 18.99 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-21 |  | 0-4005 | COMDATA 4/06/26 (EU) MILAM DONUT SHOP 4/01/26 | 0 | 0 |  | 2285 |  | 0 | 16.42 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-21 |  | 0-4005 | COMDATA 4/06/26 (EU) FAMILY DOLLAR 4/01/26 | 0 | 0 |  | 2285 |  | 0 | 22.84 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-21 |  | 0-4005 | COMDATA 4/06/26 (EU) MILAM DONUT SHOP 4/02/26 | 0 | 0 |  | 2285 |  | 0 | 12.53 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-21 |  | 0-4005 | COMDATA 4/06/26 (EU) SORELLA'S 4/02/26 | 0 | 0 |  | 2285 |  | 0 | 95.52 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-21 |  | 0-4005 | COMDATA 4/06/26 (LB) MEMPHISSHELBYAIRPORT 4/01/26 | 0 | 0 |  | 2285 |  | 0 | 48 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-21 |  | 0-4005 | COMDATA 4/06/26 (DQ) HAMPTON INN 4/01/26 | 0 | 0 |  | 2285 |  | 0 | 137.16 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-21 |  | 0-4005 | COMDATA 4/06/26 (JRION) 02855 - SPRINGFIELD BR 4/02/26 | 0 | 0 |  | 2285 |  | 0 | 42 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-21 |  | 0-4005 | COMDATA 4/06/26 (EU) TX WHARTON UTILITY 3/30/26 | 0 | 0 |  | 2285 |  | 0 | 810 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-21 |  | 0-4005 | COMDATA 4/06/26 (EU) 9ER'S GRILL @ WHARTON 4/01/26 | 0 | 0 |  | 2285 |  | 0 | 246.25 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-21 |  | 0-4005 | COMDATA 4/06/26 (LB) UBER *TRIP 3/30/26 | 0 | 0 |  | 2285 |  | 0 | 3.1 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-21 |  | 0-4005 | COMDATA 4/06/26 (LB) OJOS LOCOS SPORTS 6001 3/30/26 | 0 | 0 |  | 2285 |  | 0 | 63.57 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-21 |  | 0-4005 | COMDATA 4/06/26 (LB) IAH CN BAM BAM 3/30/26 | 0 | 0 |  | 2285 |  | 0 | 64.94 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-21 |  | 0-4005 | COMDATA 4/06/26 (LB) UBER *TRIP 3/31/26 | 0 | 0 |  | 2285 |  | 0 | 5.99 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-21 |  | 0-4005 | COMDATA 4/06/26 (LB) UBER *TRIP 3/31/26 | 0 | 0 |  | 2285 |  | 0 | 29.95 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-21 |  | 0-4005 | COMDATA 4/06/26 (LB) UBER *TRIP 3/30/26 | 0 | 0 |  | 2285 |  | 0 | 29.4 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-14 |  | 0-4005 | COMDATA 3/23/26 (AS) MACHS RESTAURANT 3/20/26 | 0 | 0 |  | 2282 |  | 0 | 95.79 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-15 |  | 0-4005 | DISA INV 2971779 | 0 | 0 |  |  |  | 0 | 141.75 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-14 |  | 0-4005 | COMDATA 3/23/26 (JB) RDUAA PUBLIC PARKING 3/16/26 | 0 | 0 |  | 2282 |  | 0 | 15.75 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-14 |  | 0-4005 | COMDATA 3/23/26 (EU) RBT PIZZA HUT 061673 3/16/26 | 0 | 0 |  | 2282 |  | 0 | -3.34 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-15 |  | 0-4005 | DISA INVOICE 2981632 | 0 | 0 |  |  |  | 0 | 47.25 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-14 |  | 0-4005 | NECS INVOICE 107046 | 0 | 0 |  |  |  | 0 | 24.25 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-16 |  | 0-4005 | DISA INVOICE 2989971 | 0 | 0 |  |  |  | 0 | 94.5 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-20 |  | 0-4005 | WEEKLY SHIPPING INVOICE | 0 | 0 |  | 12681 | FEDERAL EXPRESS CORPORATION | 0 | 170.13 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-20 |  | 0-4005 | WEEKLY SHIPPING INVOICE | 0 | 0 |  | 12681 | FEDERAL EXPRESS CORPORATION | 0 | 32.94 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-21 |  | 0-4005 | MVR STATE FEES/ DQ NEW DRIVER / ONBOARDING/ SERVICE FEES | 0 | 0 |  | 20710 | NATIONAL ENERGY CONTROL SERVICES, INC. | 0 | 103.25 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-22 |  | 0-4005 | DRUG SCREEN | 0 | 0 |  | 10630 | DISA GLOBAL SOLUTIONS INC | 0 | 519.75 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-27 |  | 0-4005 | WEEKLY SHIPPING INVOICE | 0 | 0 |  | 12681 | FEDERAL EXPRESS CORPORATION | 0 | 152.72 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-28 |  | 0-4005 | COMDATA 4/13/26 (EU) RBT PIZZA HUT 061673 4/09/26 | 0 | 0 |  | 2293 |  | 0 | -4.45 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-28 |  | 0-4005 | COMDATA 4/13/26 (EU) MILAM DONUT SHOP 4/09/26 | 0 | 0 |  | 2293 |  | 0 | 12.53 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-28 |  | 0-4005 | COMDATA 4/13/26 (EU) DD *DOORDASH THEMELTDO 4/09/26 | 0 | 0 |  | 2293 |  | 0 | 186.74 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-28 |  | 0-4005 | COMDATA 4/13/26 (EU) HINZE COUNTRY KITCHEN 4/07/26 | 0 | 0 |  | 2293 |  | 0 | 14.51 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-28 |  | 0-4005 | COMDATA 4/13/26 (EU) DOLLAR-GENERAL #3445 4/07/26 | 0 | 0 |  | 2293 |  | 0 | 9.74 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-28 |  | 0-4005 | COMDATA 4/13/26 (EU) MILAM DONUT SHOP 4/08/26 | 0 | 0 |  | 2293 |  | 0 | 11.39 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-28 |  | 0-4005 | COMDATA 4/13/26 (EU) FAMILY DOLLAR 4/08/26 | 0 | 0 |  | 2293 |  | 0 | 20.03 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-28 |  | 0-4005 | COMDATA 4/13/26 (EU) SORELLA'S 4/08/26 | 0 | 0 |  | 2293 |  | 0 | 232.17 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-28 |  | 0-4005 | COMDATA 4/13/26 (LB) LA CASONA MEXICAN REST 4/07/26 | 0 | 0 |  | 2293 |  | 0 | 100 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-28 |  | 0-4005 | COMDATA 4/13/26 (EU) PIZZA HUT 061673 4/06/26 | 0 | 0 |  | 2293 |  | 0 | 111.27 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-28 |  | 0-4005 | COMDATA 4/20/26 (DQ) HAMPTON INN 4/16/26 | 0 | 0 |  | 2294 |  | 0 | 140.21 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-04-28 |  | 0-4005 | COMDATA 4/20/26 (PR) HCTRA EZ TAG ONLINE 4/14/26 | 0 | 0 |  | 2294 |  | 0 | 11.38 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-05-04 |  | 0-4005 | WEEKLY SHIPPING INVOICE | 0 | 0 |  | 12681 | FEDERAL EXPRESS CORPORATION | 0 | 37.42 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-05-14 |  | 0-4005 | HOUSTON FIRE ALARM LABOR - REGULAR | 0 | 0 |  | 21395 | ALLIED FIRE PROTECTION, LLC | 0 | 671.15 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-05-11 |  | 0-4005 | WEEKLY SHIPPING INVOICE | 0 | 0 |  | 12681 | FEDERAL EXPRESS CORPORATION | 0 | 177.17 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-05-18 |  | 0-4005 | WEEKLY SHIPPING INVOICE | 0 | 0 |  | 12681 | FEDERAL EXPRESS CORPORATION | 0 | 108.14 | 0 | 0
ttJTrans | 0-4005 | OC |  | OC |  |  | 2026-05-18 |  | 0-4005 | WEEKLY SHIPPING INVOICE | 0 | 0 |  | 12681 | FEDERAL EXPRESS CORPORATION | 0 | 69.94 | 0 | 0
ttJTrans | 0-4005-01 | LA |  | LA |  |  | 2026-05-12 |  | 0-4005-01 | PR P2COST 000292 (PR) Summary | 0 | 0 |  |  |  | 0 | 255.37 | 0 | 2
ttJTrans | 0-4005-01 | LA |  | LA |  |  | 2026-05-12 |  | 0-4005-01 | PR P2COST 000292 (PR) Summary | 0 | 0 |  |  |  | 0 | 255.37 | 0 | 2
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-03-15 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-03-15 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-03-15 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-03-15 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-03-29 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-03-29 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-03-29 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-03-29 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-03-29 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-03-29 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-03-31 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-03-31 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-05 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-05 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-05 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-05 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR461 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR461 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR461 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR461 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR461 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR461 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR462 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR462 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR462 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR462 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR462 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR462 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR463 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR463 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR463 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR463 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR463 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR463 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR464 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR464 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR464 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR464 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | TR464 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR464 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4006 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | TR461 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR461 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | TR461 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR461 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | TR461 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR461 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | TR462 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR462 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | TR462 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR462 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | TR462 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR462 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | TR463 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR463 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | TR463 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR463 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | TR463 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR463 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | TR464 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR464 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | TR464 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR464 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | TR464 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR464 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | TR456 40' DOUBLE DOOR CONTAINER 40' DOUBLE DOOR CONTAINER | 0 | 0 |  | TR456 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | TR456 40' DOUBLE DOOR CONTAINER 40' DOUBLE DOOR CONTAINER | 0 | 0 |  | TR456 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | TR456 40' DOUBLE DOOR CONTAINER 40' DOUBLE DOOR CONTAINER | 0 | 0 |  | TR456 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4006 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR436 40' CONTAINER 40' CONTAINER | 0 | 0 |  | TR436 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR436 40' CONTAINER 40' CONTAINER | 0 | 0 |  | TR436 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR461 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR461 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR461 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR461 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR461 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR461 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR461 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR461 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR462 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR462 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR462 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR462 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR462 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR462 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR462 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR462 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR463 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR463 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR463 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR463 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR463 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR463 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR463 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR463 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR464 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR464 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR464 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR464 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR464 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR464 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR464 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR464 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR456 40' DOUBLE DOOR CONTAINER 40' DOUBLE DOOR CONTAINER | 0 | 0 |  | TR456 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR456 40' DOUBLE DOOR CONTAINER 40' DOUBLE DOOR CONTAINER | 0 | 0 |  | TR456 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR456 40' DOUBLE DOOR CONTAINER 40' DOUBLE DOOR CONTAINER | 0 | 0 |  | TR456 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR456 40' DOUBLE DOOR CONTAINER 40' DOUBLE DOOR CONTAINER | 0 | 0 |  | TR456 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | WLD133 JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS | 0 | 0 |  | WLD133 |  | 0 | 259.22 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | WLD133 JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS | 0 | 0 |  | WLD133 |  | 0 | 259.22 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | WLD133 JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS | 0 | 0 |  | WLD133 |  | 0 | 259.22 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | RT1242 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS | 0 | 0 |  | RT1242 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | RT1242 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS | 0 | 0 |  | RT1242 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | RT1242 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS | 0 | 0 |  | RT1242 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR436 40' CONTAINER 40' CONTAINER | 0 | 0 |  | TR436 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4006 | TR436 40' CONTAINER 40' CONTAINER | 0 | 0 |  | TR436 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4006 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4006 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4006 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4006 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4006 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4006 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4006 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4006 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4006 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4006 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4006 | TR461 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR461 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4006 | TR461 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR461 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4006 | TR462 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR462 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4006 | TR462 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR462 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4006 | TR463 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR463 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4006 | TR463 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR463 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4006 | TR464 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR464 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4006 | TR464 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR464 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4006 | TR456 40' DOUBLE DOOR CONTAINER 40' DOUBLE DOOR CONTAINER | 0 | 0 |  | TR456 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4006 | TR456 40' DOUBLE DOOR CONTAINER 40' DOUBLE DOOR CONTAINER | 0 | 0 |  | TR456 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4006 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4006 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4006 | WLD133 JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS | 0 | 0 |  | WLD133 |  | 0 | 259.22 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4006 | WLD133 JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS | 0 | 0 |  | WLD133 |  | 0 | 259.22 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4006 | RT1242 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS | 0 | 0 |  | RT1242 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4006 | RT1242 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS | 0 | 0 |  | RT1242 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4006 | TR436 40' CONTAINER 40' CONTAINER | 0 | 0 |  | TR436 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4006 | TR436 40' CONTAINER 40' CONTAINER | 0 | 0 |  | TR436 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR461 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR461 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR461 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR461 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR461 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR461 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR461 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR461 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR461 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR461 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR461 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR461 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR462 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR462 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR462 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR462 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR462 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR462 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR462 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR462 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR462 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR462 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR462 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR462 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR463 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR463 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR463 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR463 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR463 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR463 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR463 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR463 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR463 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR463 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR463 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR463 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR464 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR464 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR464 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR464 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR464 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR464 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR464 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR464 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR464 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR464 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR464 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR464 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR456 40' DOUBLE DOOR CONTAINER 40' DOUBLE DOOR CONTAINER | 0 | 0 |  | TR456 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR456 40' DOUBLE DOOR CONTAINER 40' DOUBLE DOOR CONTAINER | 0 | 0 |  | TR456 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR456 40' DOUBLE DOOR CONTAINER 40' DOUBLE DOOR CONTAINER | 0 | 0 |  | TR456 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR456 40' DOUBLE DOOR CONTAINER 40' DOUBLE DOOR CONTAINER | 0 | 0 |  | TR456 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR456 40' DOUBLE DOOR CONTAINER 40' DOUBLE DOOR CONTAINER | 0 | 0 |  | TR456 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR456 40' DOUBLE DOOR CONTAINER 40' DOUBLE DOOR CONTAINER | 0 | 0 |  | TR456 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | WLD133 JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS | 0 | 0 |  | WLD133 |  | 0 | 259.22 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | WLD133 JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS | 0 | 0 |  | WLD133 |  | 0 | 259.22 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | WLD133 JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS | 0 | 0 |  | WLD133 |  | 0 | 259.22 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | WLD133 JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS | 0 | 0 |  | WLD133 |  | 0 | 259.22 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | WLD133 JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS | 0 | 0 |  | WLD133 |  | 0 | 259.22 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | WLD133 JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS | 0 | 0 |  | WLD133 |  | 0 | 259.22 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | RT1242 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS | 0 | 0 |  | RT1242 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | RT1242 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS | 0 | 0 |  | RT1242 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | RT1242 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS | 0 | 0 |  | RT1242 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | RT1242 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS | 0 | 0 |  | RT1242 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | RT1242 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS | 0 | 0 |  | RT1242 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR436 40' CONTAINER 40' CONTAINER | 0 | 0 |  | TR436 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR436 40' CONTAINER 40' CONTAINER | 0 | 0 |  | TR436 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR436 40' CONTAINER 40' CONTAINER | 0 | 0 |  | TR436 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR436 40' CONTAINER 40' CONTAINER | 0 | 0 |  | TR436 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR436 40' CONTAINER 40' CONTAINER | 0 | 0 |  | TR436 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4006 | TR436 40' CONTAINER 40' CONTAINER | 0 | 0 |  | TR436 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR436 40' CONTAINER 40' CONTAINER | 0 | 0 |  | TR436 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR436 40' CONTAINER 40' CONTAINER | 0 | 0 |  | TR436 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR436 40' CONTAINER 40' CONTAINER | 0 | 0 |  | TR436 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR463 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR463 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR463 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR463 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR461 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR461 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR461 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR461 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR461 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR461 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR461 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR461 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR461 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR461 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR461 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR461 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR462 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR462 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR462 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR462 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR462 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR462 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR462 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR462 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR462 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR462 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR462 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR462 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR463 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR463 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR463 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR463 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR463 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR463 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR463 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR463 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR464 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR464 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR464 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR464 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR464 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR464 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR464 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR464 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR464 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR464 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR464 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR464 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR456 40' DOUBLE DOOR CONTAINER 40' DOUBLE DOOR CONTAINER | 0 | 0 |  | TR456 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR456 40' DOUBLE DOOR CONTAINER 40' DOUBLE DOOR CONTAINER | 0 | 0 |  | TR456 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR456 40' DOUBLE DOOR CONTAINER 40' DOUBLE DOOR CONTAINER | 0 | 0 |  | TR456 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR456 40' DOUBLE DOOR CONTAINER 40' DOUBLE DOOR CONTAINER | 0 | 0 |  | TR456 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR456 40' DOUBLE DOOR CONTAINER 40' DOUBLE DOOR CONTAINER | 0 | 0 |  | TR456 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR456 40' DOUBLE DOOR CONTAINER 40' DOUBLE DOOR CONTAINER | 0 | 0 |  | TR456 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | WLD133 JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS | 0 | 0 |  | WLD133 |  | 0 | 259.22 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | WLD133 JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS | 0 | 0 |  | WLD133 |  | 0 | 259.22 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | WLD133 JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS | 0 | 0 |  | WLD133 |  | 0 | 259.22 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | WLD133 JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS | 0 | 0 |  | WLD133 |  | 0 | 259.22 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | WLD133 JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS | 0 | 0 |  | WLD133 |  | 0 | 259.22 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | WLD133 JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS | 0 | 0 |  | WLD133 |  | 0 | 259.22 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | RT1242 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS | 0 | 0 |  | RT1242 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | RT1242 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS | 0 | 0 |  | RT1242 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | RT1242 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS | 0 | 0 |  | RT1242 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | RT1242 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS | 0 | 0 |  | RT1242 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR436 40' CONTAINER 40' CONTAINER | 0 | 0 |  | TR436 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR436 40' CONTAINER 40' CONTAINER | 0 | 0 |  | TR436 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4006 | TR436 40' CONTAINER 40' CONTAINER | 0 | 0 |  | TR436 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR436 40' CONTAINER 40' CONTAINER | 0 | 0 |  | TR436 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR436 40' CONTAINER 40' CONTAINER | 0 | 0 |  | TR436 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR436 40' CONTAINER 40' CONTAINER | 0 | 0 |  | TR436 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR436 40' CONTAINER 40' CONTAINER | 0 | 0 |  | TR436 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR436 40' CONTAINER 40' CONTAINER | 0 | 0 |  | TR436 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR436 40' CONTAINER 40' CONTAINER | 0 | 0 |  | TR436 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR419 LONESTAR 6.5X16' ENCLOSED CARGO TRAILER LONESTAR 6.5X16' ENCLOSED CARGO TRAILER | 0 | 0 |  | TR419 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR461 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR461 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR461 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR461 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR461 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR461 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR461 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR461 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR461 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR461 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR461 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR461 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR462 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR462 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR462 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR462 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR462 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR462 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR462 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR462 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR462 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR462 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR462 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR462 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR463 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR463 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR463 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR463 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR463 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR463 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR463 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR463 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR463 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR463 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR463 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR463 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR464 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR464 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR464 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR464 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR464 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR464 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR464 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR464 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR464 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR464 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR464 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR464 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR456 40' DOUBLE DOOR CONTAINER 40' DOUBLE DOOR CONTAINER | 0 | 0 |  | TR456 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR456 40' DOUBLE DOOR CONTAINER 40' DOUBLE DOOR CONTAINER | 0 | 0 |  | TR456 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR456 40' DOUBLE DOOR CONTAINER 40' DOUBLE DOOR CONTAINER | 0 | 0 |  | TR456 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR456 40' DOUBLE DOOR CONTAINER 40' DOUBLE DOOR CONTAINER | 0 | 0 |  | TR456 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR456 40' DOUBLE DOOR CONTAINER 40' DOUBLE DOOR CONTAINER | 0 | 0 |  | TR456 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | TR456 40' DOUBLE DOOR CONTAINER 40' DOUBLE DOOR CONTAINER | 0 | 0 |  | TR456 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | WLD133 JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS | 0 | 0 |  | WLD133 |  | 0 | 259.22 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | WLD133 JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS | 0 | 0 |  | WLD133 |  | 0 | 259.22 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | WLD133 JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS | 0 | 0 |  | WLD133 |  | 0 | 259.22 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | WLD133 JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS | 0 | 0 |  | WLD133 |  | 0 | 259.22 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | WLD133 JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS | 0 | 0 |  | WLD133 |  | 0 | 259.22 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | WLD133 JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS JCB 512-56 12K TELEHANDLER W/ 96" PALLET FORKS | 0 | 0 |  | WLD133 |  | 0 | 259.22 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | RT1242 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS | 0 | 0 |  | RT1242 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | RT1242 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS | 0 | 0 |  | RT1242 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | RT1242 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS | 0 | 0 |  | RT1242 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4006 | RT1242 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS | 0 | 0 |  | RT1242 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-12 |  | 0-4006 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RAT447 4WD CLUB CAR CARRYALL 1700 D 4WD CLUB CAR CARRYALL 1700 D | 0 | 0 |  | RAT447 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RAT447 4WD CLUB CAR CARRYALL 1700 D 4WD CLUB CAR CARRYALL 1700 D | 0 | 0 |  | RAT447 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-19 |  | 0-4006 | RAT447 4WD CLUB CAR CARRYALL 1700 D 4WD CLUB CAR CARRYALL 1700 D | 0 | 0 |  | RAT447 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RAT447 4WD CLUB CAR CARRYALL 1700 D 4WD CLUB CAR CARRYALL 1700 D | 0 | 0 |  | RAT447 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RAT447 4WD CLUB CAR CARRYALL 1700 D 4WD CLUB CAR CARRYALL 1700 D | 0 | 0 |  | RAT447 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RAT447 4WD CLUB CAR CARRYALL 1700 D 4WD CLUB CAR CARRYALL 1700 D | 0 | 0 |  | RAT447 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RAT447 4WD CLUB CAR CARRYALL 1700 D 4WD CLUB CAR CARRYALL 1700 D | 0 | 0 |  | RAT447 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RAT447 4WD CLUB CAR CARRYALL 1700 D 4WD CLUB CAR CARRYALL 1700 D | 0 | 0 |  | RAT447 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-26 |  | 0-4006 | RAT447 4WD CLUB CAR CARRYALL 1700 D 4WD CLUB CAR CARRYALL 1700 D | 0 | 0 |  | RAT447 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-30 |  | 0-4006 | RAT447 4WD CLUB CAR CARRYALL 1700 D 4WD CLUB CAR CARRYALL 1700 D | 0 | 0 |  | RAT447 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-30 |  | 0-4006 | RAT447 4WD CLUB CAR CARRYALL 1700 D 4WD CLUB CAR CARRYALL 1700 D | 0 | 0 |  | RAT447 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-30 |  | 0-4006 | RAT447 4WD CLUB CAR CARRYALL 1700 D 4WD CLUB CAR CARRYALL 1700 D | 0 | 0 |  | RAT447 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-04-30 |  | 0-4006 | RAT447 4WD CLUB CAR CARRYALL 1700 D 4WD CLUB CAR CARRYALL 1700 D | 0 | 0 |  | RAT447 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-03 |  | 0-4006 | RAT447 4WD CLUB CAR CARRYALL 1700 D 4WD CLUB CAR CARRYALL 1700 D | 0 | 0 |  | RAT447 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-03 |  | 0-4006 | RAT447 4WD CLUB CAR CARRYALL 1700 D 4WD CLUB CAR CARRYALL 1700 D | 0 | 0 |  | RAT447 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-10 |  | 0-4006 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-10 |  | 0-4006 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-10 |  | 0-4006 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-10 |  | 0-4006 | RAT447 4WD CLUB CAR CARRYALL 1700 D 4WD CLUB CAR CARRYALL 1700 D | 0 | 0 |  | RAT447 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-10 |  | 0-4006 | RAT447 4WD CLUB CAR CARRYALL 1700 D 4WD CLUB CAR CARRYALL 1700 D | 0 | 0 |  | RAT447 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-10 |  | 0-4006 | RAT447 4WD CLUB CAR CARRYALL 1700 D 4WD CLUB CAR CARRYALL 1700 D | 0 | 0 |  | RAT447 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-10 |  | 0-4006 | RAT447 4WD CLUB CAR CARRYALL 1700 D 4WD CLUB CAR CARRYALL 1700 D | 0 | 0 |  | RAT447 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-10 |  | 0-4006 | RAT447 4WD CLUB CAR CARRYALL 1700 D 4WD CLUB CAR CARRYALL 1700 D | 0 | 0 |  | RAT447 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-10 |  | 0-4006 | RAT447 4WD CLUB CAR CARRYALL 1700 D 4WD CLUB CAR CARRYALL 1700 D | 0 | 0 |  | RAT447 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-10 |  | 0-4006 | RLD0303 CATERPILLAR 950 WHEEL LOADER CATERPILLAR 950 WHEEL LOADER | 0 | 0 |  | RLD0303 |  | 0 | 437.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-10 |  | 0-4006 | RLD0303 CATERPILLAR 950 WHEEL LOADER CATERPILLAR 950 WHEEL LOADER | 0 | 0 |  | RLD0303 |  | 0 | 437.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-10 |  | 0-4006 | RGN0302 CATERPILLAR 200KW DIESEL GENERATOR CATERPILLAR 200KW DIESEL GENERATOR | 0 | 0 |  | RGN0302 |  | 0 | 659.72 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-10 |  | 0-4006 | RGN0302 CATERPILLAR 200KW DIESEL GENERATOR CATERPILLAR 200KW DIESEL GENERATOR | 0 | 0 |  | RGN0302 |  | 0 | 659.72 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-10 |  | 0-4006 | RGN0302 CATERPILLAR 200KW DIESEL GENERATOR CATERPILLAR 200KW DIESEL GENERATOR | 0 | 0 |  | RGN0302 |  | 0 | 659.72 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-17 |  | 0-4006 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-17 |  | 0-4006 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-17 |  | 0-4006 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-17 |  | 0-4006 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-17 |  | 0-4006 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-17 |  | 0-4006 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-17 |  | 0-4006 | RAT447 4WD CLUB CAR CARRYALL 1700 D 4WD CLUB CAR CARRYALL 1700 D | 0 | 0 |  | RAT447 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-17 |  | 0-4006 | RAT447 4WD CLUB CAR CARRYALL 1700 D 4WD CLUB CAR CARRYALL 1700 D | 0 | 0 |  | RAT447 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-17 |  | 0-4006 | RAT447 4WD CLUB CAR CARRYALL 1700 D 4WD CLUB CAR CARRYALL 1700 D | 0 | 0 |  | RAT447 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-17 |  | 0-4006 | RAT447 4WD CLUB CAR CARRYALL 1700 D 4WD CLUB CAR CARRYALL 1700 D | 0 | 0 |  | RAT447 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-17 |  | 0-4006 | RAT447 4WD CLUB CAR CARRYALL 1700 D 4WD CLUB CAR CARRYALL 1700 D | 0 | 0 |  | RAT447 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-17 |  | 0-4006 | RAT447 4WD CLUB CAR CARRYALL 1700 D 4WD CLUB CAR CARRYALL 1700 D | 0 | 0 |  | RAT447 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-17 |  | 0-4006 | RLD0303 CATERPILLAR 950 WHEEL LOADER CATERPILLAR 950 WHEEL LOADER | 0 | 0 |  | RLD0303 |  | 0 | 437.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-17 |  | 0-4006 | RLD0303 CATERPILLAR 950 WHEEL LOADER CATERPILLAR 950 WHEEL LOADER | 0 | 0 |  | RLD0303 |  | 0 | 437.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-17 |  | 0-4006 | RLD0303 CATERPILLAR 950 WHEEL LOADER CATERPILLAR 950 WHEEL LOADER | 0 | 0 |  | RLD0303 |  | 0 | 437.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-17 |  | 0-4006 | RGN0302 CATERPILLAR 200KW DIESEL GENERATOR CATERPILLAR 200KW DIESEL GENERATOR | 0 | 0 |  | RGN0302 |  | 0 | 659.72 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-17 |  | 0-4006 | RGN0302 CATERPILLAR 200KW DIESEL GENERATOR CATERPILLAR 200KW DIESEL GENERATOR | 0 | 0 |  | RGN0302 |  | 0 | 659.72 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-17 |  | 0-4006 | RGN0302 CATERPILLAR 200KW DIESEL GENERATOR CATERPILLAR 200KW DIESEL GENERATOR | 0 | 0 |  | RGN0302 |  | 0 | 659.72 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-17 |  | 0-4006 | RGN0302 CATERPILLAR 200KW DIESEL GENERATOR CATERPILLAR 200KW DIESEL GENERATOR | 0 | 0 |  | RGN0302 |  | 0 | 659.72 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-17 |  | 0-4006 | RGN0302 CATERPILLAR 200KW DIESEL GENERATOR CATERPILLAR 200KW DIESEL GENERATOR | 0 | 0 |  | RGN0302 |  | 0 | 659.72 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-17 |  | 0-4006 | RGN0302 CATERPILLAR 200KW DIESEL GENERATOR CATERPILLAR 200KW DIESEL GENERATOR | 0 | 0 |  | RGN0302 |  | 0 | 659.72 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RAT447 4WD CLUB CAR CARRYALL 1700 D 4WD CLUB CAR CARRYALL 1700 D | 0 | 0 |  | RAT447 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RAT447 4WD CLUB CAR CARRYALL 1700 D 4WD CLUB CAR CARRYALL 1700 D | 0 | 0 |  | RAT447 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RAT447 4WD CLUB CAR CARRYALL 1700 D 4WD CLUB CAR CARRYALL 1700 D | 0 | 0 |  | RAT447 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RAT447 4WD CLUB CAR CARRYALL 1700 D 4WD CLUB CAR CARRYALL 1700 D | 0 | 0 |  | RAT447 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RAT447 4WD CLUB CAR CARRYALL 1700 D 4WD CLUB CAR CARRYALL 1700 D | 0 | 0 |  | RAT447 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RAT447 4WD CLUB CAR CARRYALL 1700 D 4WD CLUB CAR CARRYALL 1700 D | 0 | 0 |  | RAT447 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RLD0303 CATERPILLAR 950 WHEEL LOADER CATERPILLAR 950 WHEEL LOADER | 0 | 0 |  | RLD0303 |  | 0 | 437.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RLD0303 CATERPILLAR 950 WHEEL LOADER CATERPILLAR 950 WHEEL LOADER | 0 | 0 |  | RLD0303 |  | 0 | 437.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RLD0303 CATERPILLAR 950 WHEEL LOADER CATERPILLAR 950 WHEEL LOADER | 0 | 0 |  | RLD0303 |  | 0 | 437.5 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RGN0302 CATERPILLAR 200KW DIESEL GENERATOR CATERPILLAR 200KW DIESEL GENERATOR | 0 | 0 |  | RGN0302 |  | 0 | 659.72 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RGN0302 CATERPILLAR 200KW DIESEL GENERATOR CATERPILLAR 200KW DIESEL GENERATOR | 0 | 0 |  | RGN0302 |  | 0 | 659.72 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RGN0302 CATERPILLAR 200KW DIESEL GENERATOR CATERPILLAR 200KW DIESEL GENERATOR | 0 | 0 |  | RGN0302 |  | 0 | 659.72 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RGN0302 CATERPILLAR 200KW DIESEL GENERATOR CATERPILLAR 200KW DIESEL GENERATOR | 0 | 0 |  | RGN0302 |  | 0 | 659.72 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RGN0302 CATERPILLAR 200KW DIESEL GENERATOR CATERPILLAR 200KW DIESEL GENERATOR | 0 | 0 |  | RGN0302 |  | 0 | 659.72 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RGN0302 CATERPILLAR 200KW DIESEL GENERATOR CATERPILLAR 200KW DIESEL GENERATOR | 0 | 0 |  | RGN0302 |  | 0 | 659.72 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RLT1295 SOLAR SURVEILLANCE TRAILER SOLAR SURVEILLANCE TRAILER | 0 | 0 |  | RLT1295 |  | 0 | 115.91 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RLT1295 SOLAR SURVEILLANCE TRAILER SOLAR SURVEILLANCE TRAILER | 0 | 0 |  | RLT1295 |  | 0 | 115.91 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RLT1295 SOLAR SURVEILLANCE TRAILER SOLAR SURVEILLANCE TRAILER | 0 | 0 |  | RLT1295 |  | 0 | 115.91 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RLT1295 SOLAR SURVEILLANCE TRAILER SOLAR SURVEILLANCE TRAILER | 0 | 0 |  | RLT1295 |  | 0 | 115.91 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RLT1295 SOLAR SURVEILLANCE TRAILER SOLAR SURVEILLANCE TRAILER | 0 | 0 |  | RLT1295 |  | 0 | 115.91 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RLT1295 SOLAR SURVEILLANCE TRAILER SOLAR SURVEILLANCE TRAILER | 0 | 0 |  | RLT1295 |  | 0 | 115.91 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RLT1296 SOLAR SURVEILLANCE TRAILER SOLAR SURVEILLANCE TRAILER | 0 | 0 |  | RLT1296 |  | 0 | 115.91 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RLT1296 SOLAR SURVEILLANCE TRAILER SOLAR SURVEILLANCE TRAILER | 0 | 0 |  | RLT1296 |  | 0 | 115.91 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RLT1296 SOLAR SURVEILLANCE TRAILER SOLAR SURVEILLANCE TRAILER | 0 | 0 |  | RLT1296 |  | 0 | 115.91 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RLT1296 SOLAR SURVEILLANCE TRAILER SOLAR SURVEILLANCE TRAILER | 0 | 0 |  | RLT1296 |  | 0 | 115.91 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RLT1296 SOLAR SURVEILLANCE TRAILER SOLAR SURVEILLANCE TRAILER | 0 | 0 |  | RLT1296 |  | 0 | 115.91 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RLT1296 SOLAR SURVEILLANCE TRAILER SOLAR SURVEILLANCE TRAILER | 0 | 0 |  | RLT1296 |  | 0 | 115.91 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RLT1297 SOLAR SURVEILLANCE TRAILER SOLAR SURVEILLANCE TRAILER | 0 | 0 |  | RLT1297 |  | 0 | 115.91 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RLT1297 SOLAR SURVEILLANCE TRAILER SOLAR SURVEILLANCE TRAILER | 0 | 0 |  | RLT1297 |  | 0 | 115.91 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RLT1297 SOLAR SURVEILLANCE TRAILER SOLAR SURVEILLANCE TRAILER | 0 | 0 |  | RLT1297 |  | 0 | 115.91 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RLT1297 SOLAR SURVEILLANCE TRAILER SOLAR SURVEILLANCE TRAILER | 0 | 0 |  | RLT1297 |  | 0 | 115.91 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RLT1297 SOLAR SURVEILLANCE TRAILER SOLAR SURVEILLANCE TRAILER | 0 | 0 |  | RLT1297 |  | 0 | 115.91 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RLT1297 SOLAR SURVEILLANCE TRAILER SOLAR SURVEILLANCE TRAILER | 0 | 0 |  | RLT1297 |  | 0 | 115.91 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RLT1298 SOLAR SURVEILLANCE TRAILER SOLAR SURVEILLANCE TRAILER | 0 | 0 |  | RLT1298 |  | 0 | 115.91 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RLT1298 SOLAR SURVEILLANCE TRAILER SOLAR SURVEILLANCE TRAILER | 0 | 0 |  | RLT1298 |  | 0 | 115.91 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RLT1298 SOLAR SURVEILLANCE TRAILER SOLAR SURVEILLANCE TRAILER | 0 | 0 |  | RLT1298 |  | 0 | 115.91 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RLT1298 SOLAR SURVEILLANCE TRAILER SOLAR SURVEILLANCE TRAILER | 0 | 0 |  | RLT1298 |  | 0 | 115.91 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RLT1298 SOLAR SURVEILLANCE TRAILER SOLAR SURVEILLANCE TRAILER | 0 | 0 |  | RLT1298 |  | 0 | 115.91 | 0 | 0
ttJTrans | 0-4006 | ER |  | ER |  |  | 2026-05-24 |  | 0-4006 | RLT1298 SOLAR SURVEILLANCE TRAILER SOLAR SURVEILLANCE TRAILER | 0 | 0 |  | RLT1298 |  | 0 | 115.91 | 0 | 0
ttJTrans | 0-4006 | LA |  | LA |  |  | 2026-03-12 |  | 0-4006 | PR P0COST 000521 (PR) Summary | 0 | 0 |  |  |  | 0 | 645.04 | 0 | 11.02
ttJTrans | 0-4006 | LA |  | LA |  |  | 2026-03-12 |  | 0-4006 | PR P0COST 000521 (PR) Summary | 0 | 0 |  |  |  | 0 | 645.06 | 0 | 11
ttJTrans | 0-4006 | LA |  | LA |  |  | 2026-03-19 |  | 0-4006 | PR P0COST 000522 (PR) Summary | 0 | 0 |  |  |  | 0 | 629.58 | 0 | 11.52
ttJTrans | 0-4006 | LA |  | LA |  |  | 2026-04-16 |  | 0-4006 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 289.27 | 0 | 8
ttJTrans | 0-4006 | LA |  | LA |  |  | 2026-04-16 |  | 0-4006 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 289.27 | 0 | 8
ttJTrans | 0-4006 | LA |  | LA |  |  | 2026-05-07 |  | 0-4006 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 2623.41 | 0 | 32
ttJTrans | 0-4006 | LA |  | LA |  |  | 2026-05-07 |  | 0-4006 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 3461.46 | 0 | 74
ttJTrans | 0-4006 | LA |  | LA |  |  | 2026-04-30 |  | 0-4006 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 2244.94 | 0 | 50
ttJTrans | 0-4006 | LA |  | LA |  |  | 2026-04-30 |  | 0-4006 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 4564.14 | 0 | 80
ttJTrans | 0-4006 | LA |  | LA |  |  | 2026-04-30 |  | 0-4006 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 969.68 | 0 | 17.02
ttJTrans | 0-4006 | LA |  | LA |  |  | 2026-04-30 |  | 0-4006 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 969.68 | 0 | 17.3
ttJTrans | 0-4006 | LA |  | LA |  |  | 2026-04-30 |  | 0-4006 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 309.28 | 0 | 8
ttJTrans | 0-4006 | LA |  | LA |  |  | 2026-05-08 |  | 0-4006 | COST CODE TRANSFER 25-4005 | 0 | 0 |  |  |  | 0 | 10283.53 | 0 | 194.86
ttJTrans | 0-4006 | LA |  | LA |  |  | 2026-05-08 |  | 0-4006 | COST CODE TRANSFER 25-4005 | 0 | 0 |  |  |  | 0 | 20501.43 | 0 | 340
ttJTrans | 0-4006 | LA |  | LA |  |  | 2026-05-07 |  | 0-4006 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 776.27 | 0 | 16
ttJTrans | 0-4006 | LA |  | LA |  |  | 2026-05-07 |  | 0-4006 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 3340.08 | 0 | 72
ttJTrans | 0-4006 | LA |  | LA |  |  | 2026-05-07 |  | 0-4006 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 2295.09 | 0 | 40
ttJTrans | 0-4006 | LA |  | LA |  |  | 2026-05-07 |  | 0-4006 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 3604.43 | 0 | 74.02
ttJTrans | 0-4006 | LA |  | LA |  |  | 2026-05-07 |  | 0-4006 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 3971.83 | 0 | 81.98
ttJTrans | 0-4006 | LA |  | LA |  |  | 2026-05-14 |  | 0-4006 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 194.54 | 0 | 2
ttJTrans | 0-4006 | LA |  | LA |  |  | 2026-05-14 |  | 0-4006 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 1781.02 | 0 | 25
ttJTrans | 0-4006 | LA |  | LA |  |  | 2026-05-14 |  | 0-4006 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 1824.98 | 0 | 32
ttJTrans | 0-4006 | LA |  | LA |  |  | 2026-05-14 |  | 0-4006 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 2063.05 | 0 | 46
ttJTrans | 0-4006 | LA |  | LA |  |  | 2026-05-14 |  | 0-4006 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 943.69 | 0 | 16
ttJTrans | 0-4006 | LA |  | LA |  |  | 2026-05-14 |  | 0-4006 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 1063.43 | 0 | 18
ttJTrans | 0-4006 | LA |  | LA |  |  | 2026-05-14 |  | 0-4006 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 392.52 | 0 | 6
ttJTrans | 0-4006 | LA |  | LA |  |  | 2026-05-14 |  | 0-4006 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 178.79 | 0 | 5
ttJTrans | 0-4006 | LA |  | LA |  |  | 2026-05-21 |  | 0-4006 | PR P0COST 000531 (PR) Summary | 0 | 0 |  |  |  | 0 | 1885.95 | 0 | 31
ttJTrans | 0-4006 | LA |  | LA |  |  | 2026-05-21 |  | 0-4006 | PR P0COST 000531 (PR) Summary | 0 | 0 |  |  |  | 0 | 2401.16 | 0 | 50
ttJTrans | 0-4006 | LA |  | LA |  |  | 2026-05-21 |  | 0-4006 | PR P0COST 000531 (PR) Summary | 0 | 0 |  |  |  | 0 | 2033.83 | 0 | 40
ttJTrans | 0-4006 | LA |  | LA |  |  | 2026-05-21 |  | 0-4006 | PR P0COST 000531 (PR) Summary | 0 | 0 |  |  |  | 0 | 1980.92 | 0 | 32
ttJTrans | 0-4006 | LA |  | LA |  |  | 2026-05-21 |  | 0-4006 | PR P0COST 000531 (PR) Summary | 0 | 0 |  |  |  | 0 | 776.99 | 0 | 20
ttJTrans | 0-4006 | OC | MA1010495 | OC | MA1010495 | 2026-03-10 | 2026-04-07 | 1 | 0-4006 | Toilets on trailer, single toilets, handwash | 1 | 55500 | PO:COMMIT | 18517 | CENTURY SANITATION, LLC | 0 | 0 | 55500 | 0
ttJTrans | 0-4006 | OC | MA1010495 | OC | MA1010495 | 2026-03-10 | 2026-04-07 | 1 | 0-4006 | Toilets on trailer, single toilets, handwash | 1 | 55500 | INVOICE:ADJ-COMMIT | 18517 | CENTURY SANITATION, LLC | 0 | 0 | -1004.57 | 0
ttJTrans | 0-4006 | OC | MA1010495 | OC | MA1010495 | 2026-03-10 | 2026-04-07 | 1 | 0-4006 | Toilets on trailer, single toilets, handwash | 1 | 55500 | INVOICE:ADJ-COMMIT | 18517 | CENTURY SANITATION, LLC | 0 | 0 | -4252.02 | 0
ttJTrans | 0-4006 | OC | MA1010495 | OC | MA1010495 | 46091 | 2026-05-20 | 1 | 0-4006 | Toilets on trailer, single toilets, handwash | 1 | 55500 | INVOICE | 18517 | CENTURY SANITATION, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | OC | MA1010495 | OC | MA1010495 | 46091 | 2026-04-09 | 1 | 0-4006 | Toilets on trailer, single toilets, handwash | 1 | 55500 | INVOICE | 18517 | CENTURY SANITATION, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 46112 | 2026-05-20 | 14 | 0-4006 | 12x60 S Plex Inside B | 18 | 17982 | INVOICE | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 46112 | 2026-05-20 | 10 | 0-4006 | Standard Setup | 6 | 11548.44 | INVOICE | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 46112 | 2026-05-20 | 8 | 0-4006 | PPT Recovery | 18 | 3196.8 | INVOICE | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 46112 | 2026-05-20 | 1 | 0-4006 | 12x60 S Plex Outside A | 18 | 17982 | INVOICE | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 46112 | 2026-05-20 | 2 | 0-4006 | 12x60 S Plex Inside B | 18 | 17982 | INVOICE | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 46112 | 2026-05-20 | 3 | 0-4006 | 12x60 S Plex Inside B | 18 | 17982 | INVOICE | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 46112 | 2026-05-20 | 4 | 0-4006 | 12x60 S Plex Inside B | 18 | 17982 | INVOICE | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 2026-03-31 | 2026-05-20 | 5 | 0-4006 | 12x60 S Plex Outside D | 18 | 17982 | INVOICE | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 2026-03-31 | 2026-05-20 | 11 | 0-4006 | Setup Material | 6 | 6660 | INVOICE | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 2026-03-31 | 2026-05-20 | 6 | 0-4006 | Steps - Rental | 18 | 1698.3 | INVOICE | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 2026-03-31 | 2026-05-20 | 9 | 0-4006 | Delivery | 6 | 5328 | INVOICE | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 2026-03-31 | 2026-04-24 | 12 | 0-4006 | Dismantle @ Return | 6 | 10656 | PO:COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 10656 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 2026-03-31 | 2026-04-24 | 13 | 0-4006 | Pickup @ Return | 6 | 5328 | PO:COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 5328 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 2026-03-31 | 2026-04-24 | 8 | 0-4006 | PPT Recovery | 18 | 3196.8 | PO:COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 3196.8 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 2026-03-31 | 2026-04-24 | 9 | 0-4006 | Delivery | 6 | 5328 | PO:COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 5328 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 2026-03-31 | 2026-04-24 | 10 | 0-4006 | Standard Setup | 6 | 11548.44 | PO:COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 11548.44 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 2026-03-31 | 2026-04-24 | 14 | 0-4006 | 12x60 S Plex Inside B | 18 | 17982 | PO:COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 17982 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 46112 | 2026-04-24 | 1 | 0-4006 | 12x60 S Plex Outside A | 18 | 17982 | PO:COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 17982 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 46112 | 2026-04-24 | 2 | 0-4006 | 12x60 S Plex Inside B | 18 | 17982 | PO:COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 17982 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 46112 | 2026-04-24 | 4 | 0-4006 | 12x60 S Plex Inside B | 18 | 17982 | PO:COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 17982 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 46112 | 2026-04-24 | 3 | 0-4006 | 12x60 S Plex Inside B | 18 | 17982 | PO:COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 17982 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 46112 | 2026-04-24 | 6 | 0-4006 | Steps - Rental | 18 | 1698.3 | PO:COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 1698.3 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 46112 | 2026-04-24 | 7 | 0-4006 | Steps - Rental | 18 | 1698.3 | PO:COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 1698.3 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 46112 | 2026-04-24 | 11 | 0-4006 | Setup Material | 6 | 6660 | PO:COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 6660 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 2026-03-31 | 2026-04-24 | 4 | 0-4006 | 12x60 S Plex Inside B | 18 | 17982 | INVOICE:ADJ-COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | -999 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 2026-03-31 | 2026-04-24 | 3 | 0-4006 | 12x60 S Plex Inside B | 18 | 17982 | INVOICE:ADJ-COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | -999 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 2026-03-31 | 2026-04-24 | 2 | 0-4006 | 12x60 S Plex Inside B | 18 | 17982 | INVOICE:ADJ-COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | -999 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 2026-03-31 | 2026-04-24 | 1 | 0-4006 | 12x60 S Plex Outside A | 18 | 17982 | INVOICE:ADJ-COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | -999 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 2026-03-31 | 2026-04-24 | 8 | 0-4006 | PPT Recovery | 18 | 3196.8 | INVOICE:ADJ-COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | -177.6 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 2026-03-31 | 2026-04-24 | 10 | 0-4006 | Standard Setup | 6 | 11548.44 | INVOICE:ADJ-COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | -11548.44 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 2026-03-31 | 2026-04-24 | 11 | 0-4006 | Setup Material | 6 | 6660 | INVOICE:ADJ-COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | -6660 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 2026-03-31 | 2026-04-24 | 9 | 0-4006 | Delivery | 6 | 5328 | INVOICE:ADJ-COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | -4440 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 2026-03-31 | 2026-04-24 | 14 | 0-4006 | 12x60 S Plex Inside B | 18 | 17982 | INVOICE:ADJ-COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | -999 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 2026-03-31 | 2026-04-24 | 5 | 0-4006 | 12x60 S Plex Outside D | 18 | 17982 | INVOICE:ADJ-COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | -999 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 2026-03-31 | 2026-04-24 | 5 | 0-4006 | 12x60 S Plex Outside D | 18 | 17982 | PO:COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 17982 | 0
ttJTrans | 0-4006 | OC | MA1010887 | OC | MA1010887 | 2026-03-31 | 2026-04-24 | 6 | 0-4006 | Steps - Rental | 18 | 1698.3 | INVOICE:ADJ-COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | -188.7 | 0
ttJTrans | 0-4006 | OC | MA1011149 | OC | MA1011149 | 2026-04-13 | 2026-04-13 | 1 | 0-4006 | 30 Yard dumpsters Metal, aluminum, coper, | 1 | 22200 | PO:COMMIT | 21388 | TEXAS GULF RECYCLING.COM, INC. | 0 | 0 | 22200 | 0
ttJTrans | 0-4006 | OC | MA1011557 | OC | MA1011557 | 2026-04-29 | 2026-05-27 | 8 | 0-4006 | Dismantle @ Return | 1 | 310.8 | PO:COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 310.8 | 0
ttJTrans | 0-4006 | OC | MA1011557 | OC | MA1011557 | 2026-04-29 | 2026-05-27 | 10 | 0-4006 | Basic Office Package | 18 | 3796.2 | PO:COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 3796.2 | 0
ttJTrans | 0-4006 | OC | MA1011557 | OC | MA1011557 | 2026-04-29 | 2026-05-27 | 3 | 0-4006 | PPT Recovery | 18 | 399.6 | PO:COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 399.6 | 0
ttJTrans | 0-4006 | OC | MA1011557 | OC | MA1011557 | 2026-04-29 | 2026-05-27 | 4 | 0-4006 | Delivery | 1 | 1110 | PO:COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 1110 | 0
ttJTrans | 0-4006 | OC | MA1011557 | OC | MA1011557 | 2026-04-29 | 2026-05-27 | 5 | 0-4006 | Standard Setup w/Jack Stands | 1 | 592.74 | PO:COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 592.74 | 0
ttJTrans | 0-4006 | OC | MA1011557 | OC | MA1011557 | 2026-04-29 | 2026-05-27 | 6 | 0-4006 | Anchors Install | 8 | 728.16 | PO:COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 728.16 | 0
ttJTrans | 0-4006 | OC | MA1011557 | OC | MA1011557 | 2026-04-29 | 2026-05-27 | 7 | 0-4006 | Anchors: Removal @ Return | 8 | 728.16 | PO:COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 728.16 | 0
ttJTrans | 0-4006 | OC | MA1011557 | OC | MA1011557 | 2026-04-29 | 2026-05-27 | 1 | 0-4006 | 12x60 Mobile Office W/RR | 18 | 17982 | PO:COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 17982 | 0
ttJTrans | 0-4006 | OC | MA1011557 | OC | MA1011557 | 2026-04-29 | 2026-05-27 | 9 | 0-4006 | Pickup @ Return | 1 | 1110 | PO:COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 1110 | 0
ttJTrans | 0-4006 | OC | MA1011557 | OC | MA1011557 | 2026-04-29 | 2026-05-27 | 2 | 0-4006 | Steps - Rental | 18 | 3396.6 | PO:COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 3396.6 | 0
ttJTrans | 0-4006 | OC | MA1011589 | OC | MA1011589 | 2026-04-29 | 2026-05-05 | 1 | 0-4006 | 24x60 Doublewide Office w/RR | 12 | 25308 | PO:COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 25308 | 0
ttJTrans | 0-4006 | OC | MA1011589 | OC | MA1011589 | 2026-04-29 | 2026-05-05 | 8 | 0-4006 | Dismantle @ Return | 2 | 3552 | PO:COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 3552 | 0
ttJTrans | 0-4006 | OC | MA1011589 | OC | MA1011589 | 2026-04-29 | 2026-05-05 | 2 | 0-4006 | Steps - Rental | 12 | 2264.4 | PO:COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 2264.4 | 0
ttJTrans | 0-4006 | OC | MA1011589 | OC | MA1011589 | 2026-04-29 | 2026-05-05 | 5 | 0-4006 | Standard Setup w/ 8 Anchors | 2 | 3849.48 | PO:COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 3849.48 | 0
ttJTrans | 0-4006 | OC | MA1011589 | OC | MA1011589 | 2026-04-29 | 2026-05-05 | 6 | 0-4006 | Setup Material | 2 | 2220 | PO:COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 2220 | 0
ttJTrans | 0-4006 | OC | MA1011589 | OC | MA1011589 | 2026-04-29 | 2026-05-05 | 3 | 0-4006 | PPT Recovery | 12 | 1065.6 | PO:COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 1065.6 | 0
ttJTrans | 0-4006 | OC | MA1011589 | OC | MA1011589 | 2026-04-29 | 2026-05-05 | 4 | 0-4006 | Delivery | 2 | 2220 | PO:COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 2220 | 0
ttJTrans | 0-4006 | OC | MA1011589 | OC | MA1011589 | 2026-04-29 | 2026-05-05 | 7 | 0-4006 | Pickup @ Return | 2 | 2220 | PO:COMMIT | 13196 | SATELLITE SHELTERS, INC. | 0 | 0 | 2220 | 0
ttJTrans | 0-4006 | OC | MA1011944 | OC | MA1011944 | 2026-05-15 | 2026-05-17 | 8 | 0-4006 | Paper towels | 1 | 34.95 | PO:COMMIT | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | 34.95 | 0
ttJTrans | 0-4006 | OC | MA1011944 | OC | MA1011944 | 2026-05-15 | 2026-05-17 | 1 | 0-4006 | Toilet Paper | 5 | 314.8 | PO:COMMIT | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | 314.8 | 0
ttJTrans | 0-4006 | OC | MA1011944 | OC | MA1011944 | 2026-05-15 | 2026-05-17 | 5 | 0-4006 | 55 Gal trash bags | 10 | 299.37 | PO:COMMIT | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | 299.37 | 0
ttJTrans | 0-4006 | OC | MA1011944 | OC | MA1011944 | 2026-05-15 | 2026-05-17 | 4 | 0-4006 | Foaming soap | 1 | 23.18 | PO:COMMIT | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | 23.18 | 0
ttJTrans | 0-4006 | OC | MA1011944 | OC | MA1011944 | 2026-05-15 | 2026-05-17 | 3 | 0-4006 | Keurig K155 Office Pro | 1 | 386.17 | PO:COMMIT | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | 386.17 | 0
ttJTrans | 0-4006 | OC | MA1011944 | OC | MA1011944 | 2026-05-15 | 2026-05-17 | 2 | 0-4006 | 8 Gallon trash bags | 5 | 60.99 | PO:COMMIT | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | 60.99 | 0
ttJTrans | 0-4006 | OC | MA1011944 | OC | MA1011944 | 2026-05-15 | 2026-05-17 | 6 | 0-4006 | Febreeze air mist | 3 | 59.84 | PO:COMMIT | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | 59.84 | 0
ttJTrans | 0-4006 | OC | MA1011944 | OC | MA1011944 | 2026-05-15 | 2026-05-17 | 7 | 0-4006 | Clorox wipes | 5 | 70.93 | PO:COMMIT | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | 70.93 | 0
ttJTrans | 0-4006 | OC | MA1012024 | OC | MA1012024 | 2026-05-19 | 2026-05-20 | 1 | 0-4006 | Uline Boot Scraper | 5 | 327.45 | PO:COMMIT | 13343 | ULINE INC. | 0 | 0 | 327.45 | 0
ttJTrans | 0-4006 | OC | MA1012024 | OC | MA1012024 | 2026-05-19 | 2026-05-20 | 3 | 0-4006 | Shipping | 1 | 110.09 | PO:COMMIT | 13343 | ULINE INC. | 0 | 0 | 110.09 | 0
ttJTrans | 0-4006 | OC | MA1012024 | OC | MA1012024 | 2026-05-19 | 2026-05-20 | 2 | 0-4006 | Mud Master Carpet Mat - 4 x 6', Charcoal | 8 | 976.8 | PO:COMMIT | 13343 | ULINE INC. | 0 | 0 | 976.8 | 0
ttJTrans | 0-4006 | OC | MA1012115 | OC | MA1012115 | 2026-05-22 | 2026-05-25 | 1 | 0-4006 | MONTHLY RECURRING CHARGES. 12 MONTHS AT | 12 | 4089.24 | PO:COMMIT | 21206 | SPECTROTEL | 0 | 0 | 4089.24 | 0
ttJTrans | 0-4006 | OC | MA1012115 | OC | MA1012115 | 2026-05-22 | 2026-05-25 | 2 | 0-4006 | NON-RECURRING CHARGES | 1 | 277.5 | PO:COMMIT | 21206 | SPECTROTEL | 0 | 0 | 277.5 | 0
ttJTrans | 0-4006 | OC |  | OC |  |  | 2026-04-09 |  | 0-4006 | TOILETS TRAILERS HANDWASH STATIONS BULK PO FOR ALL SERVICES | 0 | 0 |  | 18517 | CENTURY SANITATION, LLC | 0 | 979.68 | 0 | 0
ttJTrans | 0-4006 | OC |  | OC |  |  | 2026-05-18 |  | 0-4006 | SITE OFFICE POWER 25-4005 | 0 | 0 |  | 11293 | CENTERPOINT ENERGY | 0 | 2004 | 0 | 0
ttJTrans | 0-4006 | OC |  | OC |  |  | 2026-05-20 |  | 0-4006 | 5/8-6/4 6plex office trailer approved by Eugene & John | 0 | 0 |  | 13196 | SATELLITE SHELTERS | 0 | 984.82 | 0 | 0
ttJTrans | 0-4006 | OC |  | OC |  |  | 2026-05-20 |  | 0-4006 | 5/8-6/4 6plex office trailer approved by Eugene & John | 0 | 0 |  | 13196 | SATELLITE SHELTERS | 0 | 27305.24 | 0 | 0
ttJTrans | 0-4006 | OC |  | OC |  |  | 2026-05-20 |  | 0-4006 | APRIL 2026 TOILETS TRAILERS HANDWASH STATIONS BULK PO FOR ALL SERVICES | 0 | 0 |  | 18517 | CENTURY SANITATION, LLC | 0 | 4146.68 | 0 | 0
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-26 |  | 0-4005 | PR P0COST 000523 (PR) Summary | 0 | 0 |  |  |  | 0 | 889.84 | 0 | 8
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-08 |  | 0-4005 | COST CODE TRANSFER 25-4005 | 0 | 0 |  |  |  | 0 | -889.84 | 0 | -8
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-07 |  | 0-4005 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 197 | 0 | 2
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-07 |  | 0-4005 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 397.47 | 0 | 6
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-13 | 14 | 0-4008 | CLIP GLOVE PLASTIC | 50 | 120.99 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 120.99 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 2026-02-12 | 2026-02-13 | 10 | 0-4008 | GLOVE MAXIFLEX CUT A2 SM | 4 | 468.86 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 468.86 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 2026-02-12 | 2026-02-13 | 11 | 0-4008 | GLOVE MAXIFLEX CUT A2 MD | 4 | 468.86 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 468.86 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 2026-02-12 | 2026-02-13 | 12 | 0-4008 | GLOVE MAXIFLEX CUT A2 L | 3 | 351.65 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 351.65 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 2026-02-12 | 2026-02-13 | 13 | 0-4008 | GLOVE MAXIFEX CUT A2 XL | 2 | 234.43 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 234.43 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 2026-02-12 | 2026-02-13 | 5 | 0-4008 | GLOVES SML KNUCKLEHEAD IMPACT | 36 | 653.75 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 653.75 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 2026-02-12 | 2026-02-13 | 6 | 0-4008 | GLOVES MED KNUCKLEHEAD IMPACT | 48 | 871.66 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 871.66 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-13 | 7 | 0-4008 | GLOVES LRG KNUCKLEHEAD IMPACT | 36 | 653.75 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 653.75 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-13 | 8 | 0-4008 | GLOVES XL KNUCKLEHEAD IMPACT | 24 | 435.83 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 435.83 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-13 | 9 | 0-4008 | GLOVES 2X KNUCKLEHEAD IMPACT | 24 | 435.83 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 435.83 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-13 | 2 | 0-4008 | GLASSES SAFETY SMOKE RAD-SEQUE | 108 | 239.76 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 239.76 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-13 | 3 | 0-4008 | GLASSES SAFETY IN/OUT W BLACK | 84 | 606.06 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 606.06 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-13 | 4 | 0-4008 | SIDESHIELD VISION AID CLEAR 60 | 60 | 181.82 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 181.82 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-13 | 1 | 0-4008 | GLASSES SAFETY CLEAR RAD-SEQUE | 84 | 166.9 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 166.9 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-13 | 1 | 0-4008 | GLASSES SAFETY CLEAR RAD-SEQUE | 84 | 166.9 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -166.9 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-13 | 2 | 0-4008 | GLASSES SAFETY SMOKE RAD-SEQUE | 108 | 239.76 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -239.76 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-13 | 3 | 0-4008 | GLASSES SAFETY IN/OUT W BLACK | 84 | 606.06 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -606.06 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-13 | 4 | 0-4008 | SIDESHIELD VISION AID CLEAR 60 | 60 | 181.82 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -181.82 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-13 | 11 | 0-4008 | GLOVE MAXIFLEX CUT A2 MD | 4 | 468.86 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -468.86 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-13 | 12 | 0-4008 | GLOVE MAXIFLEX CUT A2 L | 3 | 351.65 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -351.65 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-13 | 6 | 0-4008 | GLOVES MED KNUCKLEHEAD IMPACT | 48 | 871.66 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -871.66 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-13 | 7 | 0-4008 | GLOVES LRG KNUCKLEHEAD IMPACT | 36 | 653.75 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -653.75 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-13 | 8 | 0-4008 | GLOVES XL KNUCKLEHEAD IMPACT | 24 | 435.83 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -435.83 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-13 | 9 | 0-4008 | GLOVES 2X KNUCKLEHEAD IMPACT | 24 | 435.83 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -435.83 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-13 | 10 | 0-4008 | GLOVE MAXIFLEX CUT A2 SM | 4 | 468.86 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -468.86 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-13 | 13 | 0-4008 | GLOVE MAXIFEX CUT A2 XL | 2 | 234.43 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -234.43 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-13 | 14 | 0-4008 | CLIP GLOVE PLASTIC | 50 | 120.99 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -120.99 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-13 | 5 | 0-4008 | GLOVES SML KNUCKLEHEAD IMPACT | 36 | 653.75 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -653.75 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-25 | 7 | 0-4008 | GLOVES LRG KNUCKLEHEAD IMPACT | 36 | 653.75 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-25 | 1 | 0-4008 | GLASSES SAFETY CLEAR RAD-SEQUE | 84 | 166.9 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-25 | 2 | 0-4008 | GLASSES SAFETY SMOKE RAD-SEQUE | 108 | 239.76 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-25 | 3 | 0-4008 | GLASSES SAFETY IN/OUT W BLACK | 84 | 606.06 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-25 | 4 | 0-4008 | SIDESHIELD VISION AID CLEAR 60 | 60 | 181.82 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-25 | 11 | 0-4008 | GLOVE MAXIFLEX CUT A2 MD | 4 | 468.86 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-25 | 12 | 0-4008 | GLOVE MAXIFLEX CUT A2 L | 3 | 351.65 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-25 | 6 | 0-4008 | GLOVES MED KNUCKLEHEAD IMPACT | 48 | 871.66 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-25 | 5 | 0-4008 | GLOVES SML KNUCKLEHEAD IMPACT | 36 | 653.75 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-25 | 9 | 0-4008 | GLOVES 2X KNUCKLEHEAD IMPACT | 24 | 435.83 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-25 | 8 | 0-4008 | GLOVES XL KNUCKLEHEAD IMPACT | 24 | 435.83 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-25 | 14 | 0-4008 | CLIP GLOVE PLASTIC | 50 | 120.99 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-25 | 13 | 0-4008 | GLOVE MAXIFEX CUT A2 XL | 2 | 234.43 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010074 | OC | MA1010074 | 46065 | 2026-02-25 | 10 | 0-4008 | GLOVE MAXIFLEX CUT A2 SM | 4 | 468.86 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010382 | OC | MA1010382 | 46083 | 2026-03-25 | 1 | 0-4008 | 48'' Rollups Non Reflective | 9 | 684.32 | INVOICE | 12177 | TRAFFIC CONTROL PRODUCTS OF LOUISIANA CO. INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010382 | OC | MA1010382 | 46083 | 2026-03-25 | 2 | 0-4008 | 48'' Rollups Non Reflective Trucks | 9 | 684.32 | INVOICE | 12177 | TRAFFIC CONTROL PRODUCTS OF LOUISIANA CO. INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010382 | OC | MA1010382 | 46083 | 2026-03-25 | 5 | 0-4008 | SHIPPING COSTS | 1 | 166.5 | INVOICE | 12177 | TRAFFIC CONTROL PRODUCTS OF LOUISIANA CO. INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010382 | OC | MA1010382 | 46083 | 2026-03-25 | 4 | 0-4008 | Empty Sand Bags White | 100 | 166.5 | INVOICE | 12177 | TRAFFIC CONTROL PRODUCTS OF LOUISIANA CO. INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010382 | OC | MA1010382 | 46083 | 2026-03-25 | 3 | 0-4008 | 48'' Rollups Non Reflective Be | 9 | 684.32 | INVOICE | 12177 | TRAFFIC CONTROL PRODUCTS OF LOUISIANA CO. INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010382 | OC | MA1010382 | 46083 | 2026-03-03 | 1 | 0-4008 | 48'' Rollups Non Reflective | 9 | 684.32 | PO:COMMIT | 12177 | TRAFFIC CONTROL PRODUCTS OF LOUISIANA CO. INC. | 684.32 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010382 | OC | MA1010382 | 46083 | 2026-03-03 | 4 | 0-4008 | Empty Sand Bags White | 100 | 166.5 | PO:COMMIT | 12177 | TRAFFIC CONTROL PRODUCTS OF LOUISIANA CO. INC. | 166.5 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010382 | OC | MA1010382 | 46083 | 2026-03-03 | 5 | 0-4008 | SHIPPING COSTS | 1 | 166.5 | PO:COMMIT | 12177 | TRAFFIC CONTROL PRODUCTS OF LOUISIANA CO. INC. | 166.5 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010382 | OC | MA1010382 | 46083 | 2026-03-03 | 2 | 0-4008 | 48'' Rollups Non Reflective Trucks | 9 | 684.32 | PO:COMMIT | 12177 | TRAFFIC CONTROL PRODUCTS OF LOUISIANA CO. INC. | 684.32 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010382 | OC | MA1010382 | 46083 | 2026-03-03 | 3 | 0-4008 | 48'' Rollups Non Reflective Be | 9 | 684.32 | PO:COMMIT | 12177 | TRAFFIC CONTROL PRODUCTS OF LOUISIANA CO. INC. | 684.32 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010382 | OC | MA1010382 | 46083 | 2026-03-03 | 2 | 0-4008 | 48'' Rollups Non Reflective Trucks | 9 | 684.32 | INVOICE:ADJ-ACCRUAL | 12177 | TRAFFIC CONTROL PRODUCTS OF LOUISIANA CO. INC. | -684.32 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010382 | OC | MA1010382 | 46083 | 2026-03-03 | 5 | 0-4008 | SHIPPING COSTS | 1 | 166.5 | INVOICE:ADJ-ACCRUAL | 12177 | TRAFFIC CONTROL PRODUCTS OF LOUISIANA CO. INC. | -166.5 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010382 | OC | MA1010382 | 46083 | 2026-03-03 | 1 | 0-4008 | 48'' Rollups Non Reflective | 9 | 684.32 | INVOICE:ADJ-ACCRUAL | 12177 | TRAFFIC CONTROL PRODUCTS OF LOUISIANA CO. INC. | -684.32 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010382 | OC | MA1010382 | 46083 | 2026-03-03 | 4 | 0-4008 | Empty Sand Bags White | 100 | 166.5 | INVOICE:ADJ-ACCRUAL | 12177 | TRAFFIC CONTROL PRODUCTS OF LOUISIANA CO. INC. | -166.5 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010382 | OC | MA1010382 | 46083 | 2026-03-03 | 3 | 0-4008 | 48'' Rollups Non Reflective Be | 9 | 684.32 | INVOICE:ADJ-ACCRUAL | 12177 | TRAFFIC CONTROL PRODUCTS OF LOUISIANA CO. INC. | -684.32 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010423 | OC | MA1010423 | 46085 | 2026-03-05 | 1 | 0-4008 | SAFETY SUPPLIES - QUOTE ATTACHED | 1 | 2064.77 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 2064.77 | 0
ttJTrans | 0-4008 | OC | MA1010423 | OC | MA1010423 | 46085 | 2026-03-05 | 1 | 0-4008 | SAFETY SUPPLIES - QUOTE ATTACHED | 1 | 2064.77 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -2064.77 | 0
ttJTrans | 0-4008 | OC | MA1010423 | OC | MA1010423 | 46085 | 2026-03-31 | 1 | 0-4008 | SAFETY SUPPLIES - QUOTE ATTACHED | 1 | 2064.77 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010467 | OC | MA1010467 | 46092 | 2026-04-01 | 1 | 0-4008 | LEASE 18 DIGGING MATS FOR 14 DAYS | 18 | 576.45 | INVOICE | 20401 | RDC HOLDINGS LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010467 | OC | MA1010467 | 46092 | 2026-04-01 | 2 | 0-4008 | FREIGHT IN AND OUT | 18 | 2209.73 | INVOICE | 20401 | RDC HOLDINGS LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010467 | OC | MA1010467 | 46092 | 2026-03-06 | 2 | 0-4008 | FREIGHT IN AND OUT | 18 | 2209.73 | INVOICE:ADJ-COMMIT | 20401 | RDC HOLDINGS LLC | 0 | 0 | -2135 | 0
ttJTrans | 0-4008 | OC | MA1010467 | OC | MA1010467 | 46092 | 2026-03-06 | 1 | 0-4008 | LEASE 18 DIGGING MATS FOR 14 DAYS | 18 | 576.45 | PO:COMMIT | 20401 | RDC HOLDINGS LLC | 0 | 0 | 576.45 | 0
ttJTrans | 0-4008 | OC | MA1010467 | OC | MA1010467 | 46092 | 2026-03-06 | 2 | 0-4008 | FREIGHT IN AND OUT | 18 | 2209.73 | PO:COMMIT | 20401 | RDC HOLDINGS LLC | 0 | 0 | 2209.73 | 0
ttJTrans | 0-4008 | OC | MA1010467 | OC | MA1010467 | 46092 | 2026-03-06 | 1 | 0-4008 | LEASE 18 DIGGING MATS FOR 14 DAYS | 18 | 576.45 | INVOICE:ADJ-COMMIT | 20401 | RDC HOLDINGS LLC | 0 | 0 | -576.45 | 0
ttJTrans | 0-4008 | OC | MA1010533 | OC | MA1010533 | 46092 | 2026-03-12 | 2 | 0-4008 | DEMAND FLOW REGULATOR | 1 | 111 | PO:COMMIT | 12287 | 24 HOUR SAFETY LLC | 0 | 0 | 111 | 0
ttJTrans | 0-4008 | OC | MA1010533 | OC | MA1010533 | 46092 | 2026-03-12 | 1 | 0-4008 | GAS ALERT MAX XT | 4 | 2442 | PO:COMMIT | 12287 | 24 HOUR SAFETY LLC | 0 | 0 | 2442 | 0
ttJTrans | 0-4008 | OC | MA1010533 | OC | MA1010533 | 46092 | 2026-03-12 | 3 | 0-4008 | CAL GAS 25PPM H2S 100PPM CO 2.5% CH4 18% O2 | 1 | 287.82 | PO:COMMIT | 12287 | 24 HOUR SAFETY LLC | 0 | 0 | 287.82 | 0
ttJTrans | 0-4008 | OC | MA1010533 | OC | MA1010533 | 46092 | 2026-03-12 | 2 | 0-4008 | DEMAND FLOW REGULATOR | 1 | 111 | INVOICE:ADJ-COMMIT | 12287 | 24 HOUR SAFETY LLC | 0 | 0 | -111 | 0
ttJTrans | 0-4008 | OC | MA1010533 | OC | MA1010533 | 46092 | 2026-03-12 | 3 | 0-4008 | CAL GAS 25PPM H2S 100PPM CO 2.5% CH4 18% O2 | 1 | 287.82 | INVOICE:ADJ-COMMIT | 12287 | 24 HOUR SAFETY LLC | 0 | 0 | -287.82 | 0
ttJTrans | 0-4008 | OC | MA1010533 | OC | MA1010533 | 46092 | 2026-03-12 | 1 | 0-4008 | GAS ALERT MAX XT | 4 | 2442 | INVOICE:ADJ-COMMIT | 12287 | 24 HOUR SAFETY LLC | 0 | 0 | -2442 | 0
ttJTrans | 0-4008 | OC | MA1010533 | OC | MA1010533 | 46092 | 2026-05-19 | 1 | 0-4008 | GAS ALERT MAX XT | 4 | 2442 | INVOICE | 12287 | 24 HOUR SAFETY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010533 | OC | MA1010533 | 46092 | 2026-05-19 | 2 | 0-4008 | DEMAND FLOW REGULATOR | 1 | 111 | INVOICE | 12287 | 24 HOUR SAFETY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010533 | OC | MA1010533 | 46092 | 2026-05-19 | 3 | 0-4008 | CAL GAS 25PPM H2S 100PPM CO 2.5% CH4 18% O2 | 1 | 287.82 | INVOICE | 12287 | 24 HOUR SAFETY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010561 | OC | MA1010561 | 46093 | 2026-04-01 | 2 | 0-4008 | DIAGONAL PLIRS BLK/RD 7" | 1 | 16.64 | INVOICE | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010561 | OC | MA1010561 | 46093 | 2026-04-01 | 3 | 0-4008 | LINESMAN PLIRS BLK/RD 8" | 1 | 19.97 | INVOICE | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010561 | OC | MA1010561 | 46093 | 2026-04-01 | 4 | 0-4008 | HI LEVRAGE CUT PLIER 3PC | 1 | 38.84 | INVOICE | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010561 | OC | MA1010561 | 46093 | 2026-04-01 | 5 | 0-4008 | TIRE WIRE 16GA 340 FT | 1 | 8.87 | INVOICE | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010561 | OC | MA1010561 | 46093 | 2026-04-01 | 9 | 0-4008 | POST DRIVER W/2 HANDLE HD | 1 | 52.16 | INVOICE | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010561 | OC | MA1010561 | 46093 | 2026-03-13 | 4 | 0-4008 | HI LEVRAGE CUT PLIER 3PC | 1 | 38.84 | INVOICE:ADJ-COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | -38.84 | 0
ttJTrans | 0-4008 | OC | MA1010561 | OC | MA1010561 | 46093 | 2026-03-13 | 3 | 0-4008 | LINESMAN PLIRS BLK/RD 8" | 1 | 19.97 | INVOICE:ADJ-COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | -19.97 | 0
ttJTrans | 0-4008 | OC | MA1010561 | OC | MA1010561 | 46093 | 2026-03-13 | 9 | 0-4008 | POST DRIVER W/2 HANDLE HD | 1 | 52.16 | INVOICE:ADJ-COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | -52.16 | 0
ttJTrans | 0-4008 | OC | MA1010561 | OC | MA1010561 | 46093 | 2026-03-13 | 2 | 0-4008 | DIAGONAL PLIRS BLK/RD 7" | 1 | 16.64 | INVOICE:ADJ-COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | -16.64 | 0
ttJTrans | 0-4008 | OC | MA1010561 | OC | MA1010561 | 46093 | 2026-03-13 | 5 | 0-4008 | TIRE WIRE 16GA 340 FT | 1 | 8.87 | INVOICE:ADJ-COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | -8.87 | 0
ttJTrans | 0-4008 | OC | MA1010561 | OC | MA1010561 | 46093 | 2026-03-13 | 5 | 0-4008 | TIRE WIRE 16GA 340 FT | 1 | 8.87 | PO:COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 8.87 | 0
ttJTrans | 0-4008 | OC | MA1010561 | OC | MA1010561 | 46093 | 2026-03-13 | 3 | 0-4008 | LINESMAN PLIRS BLK/RD 8" | 1 | 19.97 | PO:COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 19.97 | 0
ttJTrans | 0-4008 | OC | MA1010561 | OC | MA1010561 | 46093 | 2026-03-13 | 9 | 0-4008 | POST DRIVER W/2 HANDLE HD | 1 | 52.16 | PO:COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 52.16 | 0
ttJTrans | 0-4008 | OC | MA1010561 | OC | MA1010561 | 46093 | 2026-03-13 | 4 | 0-4008 | HI LEVRAGE CUT PLIER 3PC | 1 | 38.84 | PO:COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 38.84 | 0
ttJTrans | 0-4008 | OC | MA1010561 | OC | MA1010561 | 46093 | 2026-03-13 | 2 | 0-4008 | DIAGONAL PLIRS BLK/RD 7" | 1 | 16.64 | PO:COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 16.64 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-01 | 14 | 0-4008 | CAP T-POST SLIP-ON SOFT 25/BAG | 8 | 180.71 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 180.71 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-01 | 13 | 0-4008 | T-POST 6FT GREEN 1-1/4# W KIC | 400 | 2819.4 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 2819.4 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-01 | 10 | 0-4008 | ZIP TIE 8IN UV BLK 1000/PK 75L | 4 | 124.32 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 124.32 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-01 | 9 | 0-4008 | 1/2IN X 50FT AIR HOSE | 2 | 144.3 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 144.3 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-01 | 8 | 0-4008 | 7/16 X 5/8 STAPLE W/CAP 2000/B | 40 | 2775 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 2775 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-01 | 7 | 0-4008 | STINGER NAIL GUN | 5 | 1692.75 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 1692.75 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-01 | 6 | 0-4008 | CAP T-POST SLIP-ON SOFT 25/BAG | 16 | 361.42 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 361.42 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-01 | 5 | 0-4008 | T-POST 4FT NO KICK PLATE META | 400 | 1309.8 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 1309.8 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-01 | 12 | 0-4008 | ROPE POLY 3/8INX600FT YELLOW | 5 | 218 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -218 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-01 | 6 | 0-4008 | CAP T-POST SLIP-ON SOFT 25/BAG | 16 | 361.42 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -45.18 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-01 | 5 | 0-4008 | T-POST 4FT NO KICK PLATE META | 400 | 1309.8 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -1309.8 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-01 | 7 | 0-4008 | STINGER NAIL GUN | 5 | 1692.75 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -677.1 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-01 | 21 | 0-4008 | FREIGHT EST TBD | 1 | 3330 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -3330 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-01 | 9 | 0-4008 | 1/2IN X 50FT AIR HOSE | 2 | 144.3 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -144.3 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-01 | 8 | 0-4008 | 7/16 X 5/8 STAPLE W/CAP 2000/B | 40 | 2775 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -2636.25 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-01 | 10 | 0-4008 | ZIP TIE 8IN UV BLK 1000/PK 75L | 4 | 124.32 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -124.32 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-01 | 17 | 0-4008 | STAPLE FENCE 1-1/2IN HG 9GA 1L | 10 | 46.95 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 46.95 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-01 | 18 | 0-4008 | STAND ALONE FENCE/BARRIER 8-1/2X40' | 5 | 943.5 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 943.5 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-01 | 21 | 0-4008 | FREIGHT EST TBD | 1 | 3330 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 1110 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-01 | 13 | 0-4008 | T-POST 6FT GREEN 1-1/4# W KIC | 400 | 2819.4 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -2819.4 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-01 | 15 | 0-4008 | TAPE DUCT 2IN X 60YD BLACK 24/ | 96 | 507.23 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 507.23 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-01 | 12 | 0-4008 | ROPE POLY 3/8INX600FT YELLOW | 5 | 218 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 218 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-01 | 17 | 0-4008 | STAPLE FENCE 1-1/2IN HG 9GA 1L | 10 | 46.95 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -46.95 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-01 | 15 | 0-4008 | TAPE DUCT 2IN X 60YD BLACK 24/ | 96 | 507.23 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -507.23 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-01 | 18 | 0-4008 | STAND ALONE FENCE/BARRIER 8-1/2X40' | 5 | 943.5 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -943.5 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-01 | 21 | 0-4008 | FREIGHT EST TBD | 1 | 3330 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 2220 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-07 | 8 | 0-4008 | 7/16 X 5/8 STAPLE W/CAP 2000/B | 40 | 2775 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-07 | 9 | 0-4008 | 1/2IN X 50FT AIR HOSE | 2 | 144.3 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-07 | 21 | 0-4008 | FREIGHT EST TBD | 1 | 3330 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-07 | 6 | 0-4008 | CAP T-POST SLIP-ON SOFT 25/BAG | 16 | 361.42 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-07 | 12 | 0-4008 | ROPE POLY 3/8INX600FT YELLOW | 5 | 218 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-07 | 13 | 0-4008 | T-POST 6FT GREEN 1-1/4# W KIC | 400 | 2819.4 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-07 | 15 | 0-4008 | TAPE DUCT 2IN X 60YD BLACK 24/ | 96 | 507.23 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-07 | 17 | 0-4008 | STAPLE FENCE 1-1/2IN HG 9GA 1L | 10 | 46.95 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-07 | 18 | 0-4008 | STAND ALONE FENCE/BARRIER 8-1/2X40' | 5 | 943.5 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-07 | 5 | 0-4008 | T-POST 4FT NO KICK PLATE META | 400 | 1309.8 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-07 | 7 | 0-4008 | STINGER NAIL GUN | 5 | 1692.75 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010837 | OC | MA1010837 | 46140 | 2026-05-07 | 10 | 0-4008 | ZIP TIE 8IN UV BLK 1000/PK 75L | 4 | 124.32 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010901 | OC | MA1010901 | 46112 | 2026-05-07 | 1 | 0-4008 | WHC HATS | 1 | 5165.66 | INVOICE | 12311 | ACTION SPECIALTIES, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010901 | OC | MA1010901 | 46112 | 2026-03-31 | 1 | 0-4008 | WHC HATS | 1 | 5165.66 | INVOICE:ADJ-COMMIT | 12311 | ACTION SPECIALTIES, LLC | 0 | 0 | -5165.66 | 0
ttJTrans | 0-4008 | OC | MA1010901 | OC | MA1010901 | 46112 | 2026-03-31 | 1 | 0-4008 | WHC HATS | 1 | 5165.66 | PO:COMMIT | 12311 | ACTION SPECIALTIES, LLC | 0 | 0 | 5165.66 | 0
ttJTrans | 0-4008 | OC | MA1010987 | OC | MA1010987 | 46118 | 2026-04-07 | 2 | 0-4008 | REVERSE PARKING ONLY - 24" X 12" DOUBLE | 40 | 532.8 | INVOICE:ADJ-COMMIT | 21346 | LOWRY'S SIGN SHOP | 0 | 0 | -532.8 | 0
ttJTrans | 0-4008 | OC | MA1010987 | OC | MA1010987 | 46118 | 2026-04-07 | 4 | 0-4008 | STOP ON WHC ACCESS - 24" X 24" DOUBLE SIDED | 20 | 710.4 | PO:COMMIT | 21346 | LOWRY'S SIGN SHOP | 0 | 0 | 710.4 | 0
ttJTrans | 0-4008 | OC | MA1010987 | OC | MA1010987 | 46118 | 2026-04-07 | 5 | 0-4008 | BOX/HANDLING | 1 | 27.75 | PO:COMMIT | 21346 | LOWRY'S SIGN SHOP | 0 | 0 | 27.75 | 0
ttJTrans | 0-4008 | OC | MA1010987 | OC | MA1010987 | 46118 | 2026-04-07 | 4 | 0-4008 | STOP ON WHC ACCESS - 24" X 24" DOUBLE SIDED | 20 | 710.4 | INVOICE:ADJ-COMMIT | 21346 | LOWRY'S SIGN SHOP | 0 | 0 | -710.4 | 0
ttJTrans | 0-4008 | OC | MA1010987 | OC | MA1010987 | 46118 | 2026-04-07 | 2 | 0-4008 | REVERSE PARKING ONLY - 24" X 12" DOUBLE | 40 | 532.8 | PO:COMMIT | 21346 | LOWRY'S SIGN SHOP | 0 | 0 | 532.8 | 0
ttJTrans | 0-4008 | OC | MA1010987 | OC | MA1010987 | 46118 | 2026-04-07 | 1 | 0-4008 | DANGER OVERHEAD POWER LINES ARROW UP - 24" X | 30 | 915.75 | PO:COMMIT | 21346 | LOWRY'S SIGN SHOP | 0 | 0 | 915.75 | 0
ttJTrans | 0-4008 | OC | MA1010987 | OC | MA1010987 | 46118 | 2026-04-07 | 6 | 0-4008 | ESTIMATED GROUND SHIPPING TO LAKE CHARLES, LA | 1 | 61.05 | PO:COMMIT | 21346 | LOWRY'S SIGN SHOP | 0 | 0 | 61.05 | 0
ttJTrans | 0-4008 | OC | MA1010987 | OC | MA1010987 | 46118 | 2026-04-07 | 6 | 0-4008 | ESTIMATED GROUND SHIPPING TO LAKE CHARLES, LA | 1 | 61.05 | INVOICE:ADJ-COMMIT | 21346 | LOWRY'S SIGN SHOP | 0 | 0 | -61.05 | 0
ttJTrans | 0-4008 | OC | MA1010987 | OC | MA1010987 | 46118 | 2026-04-07 | 3 | 0-4008 | WHC ACCESS - 24" X 24" DOUBLE SIDED SIGNS ON | 20 | 710.4 | PO:COMMIT | 21346 | LOWRY'S SIGN SHOP | 0 | 0 | 710.4 | 0
ttJTrans | 0-4008 | OC | MA1010987 | OC | MA1010987 | 46118 | 2026-04-07 | 1 | 0-4008 | DANGER OVERHEAD POWER LINES ARROW UP - 24" X | 30 | 915.75 | INVOICE:ADJ-COMMIT | 21346 | LOWRY'S SIGN SHOP | 0 | 0 | -915.75 | 0
ttJTrans | 0-4008 | OC | MA1010987 | OC | MA1010987 | 46118 | 2026-04-07 | 3 | 0-4008 | WHC ACCESS - 24" X 24" DOUBLE SIDED SIGNS ON | 20 | 710.4 | INVOICE:ADJ-COMMIT | 21346 | LOWRY'S SIGN SHOP | 0 | 0 | -710.4 | 0
ttJTrans | 0-4008 | OC | MA1010987 | OC | MA1010987 | 46118 | 2026-04-07 | 5 | 0-4008 | BOX/HANDLING | 1 | 27.75 | INVOICE:ADJ-COMMIT | 21346 | LOWRY'S SIGN SHOP | 0 | 0 | -27.75 | 0
ttJTrans | 0-4008 | OC | MA1010987 | OC | MA1010987 | 46118 | 2026-05-08 | 4 | 0-4008 | STOP ON WHC ACCESS - 24" X 24" DOUBLE SIDED | 20 | 710.4 | INVOICE | 21346 | LOWRY'S SIGN SHOP | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010987 | OC | MA1010987 | 46118 | 2026-05-08 | 3 | 0-4008 | WHC ACCESS - 24" X 24" DOUBLE SIDED SIGNS ON | 20 | 710.4 | INVOICE | 21346 | LOWRY'S SIGN SHOP | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010987 | OC | MA1010987 | 46118 | 2026-05-08 | 2 | 0-4008 | REVERSE PARKING ONLY - 24" X 12" DOUBLE | 40 | 532.8 | INVOICE | 21346 | LOWRY'S SIGN SHOP | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010987 | OC | MA1010987 | 46118 | 2026-05-08 | 6 | 0-4008 | ESTIMATED GROUND SHIPPING TO LAKE CHARLES, LA | 1 | 61.05 | INVOICE | 21346 | LOWRY'S SIGN SHOP | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010987 | OC | MA1010987 | 46118 | 2026-05-08 | 5 | 0-4008 | BOX/HANDLING | 1 | 27.75 | INVOICE | 21346 | LOWRY'S SIGN SHOP | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1010987 | OC | MA1010987 | 46118 | 2026-05-08 | 1 | 0-4008 | DANGER OVERHEAD POWER LINES ARROW UP - 24" X | 30 | 915.75 | INVOICE | 21346 | LOWRY'S SIGN SHOP | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011009 | OC | MA1011009 | 46118 | 2026-04-23 | 2 | 0-4008 | FREIGHT | 1 | 49.95 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011009 | OC | MA1011009 | 46118 | 2026-04-23 | 1 | 0-4008 | SHADE HARDHAT W REFL TAPE 50/B | 100 | 749.25 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011009 | OC | MA1011009 | 46118 | 2026-04-07 | 1 | 0-4008 | SHADE HARDHAT W REFL TAPE 50/B | 100 | 749.25 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -749.25 | 0
ttJTrans | 0-4008 | OC | MA1011009 | OC | MA1011009 | 46118 | 2026-04-07 | 2 | 0-4008 | FREIGHT | 1 | 49.95 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 49.95 | 0
ttJTrans | 0-4008 | OC | MA1011009 | OC | MA1011009 | 46118 | 2026-04-07 | 2 | 0-4008 | FREIGHT | 1 | 49.95 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -49.95 | 0
ttJTrans | 0-4008 | OC | MA1011009 | OC | MA1011009 | 46118 | 2026-04-07 | 1 | 0-4008 | SHADE HARDHAT W REFL TAPE 50/B | 100 | 749.25 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 749.25 | 0
ttJTrans | 0-4008 | OC | MA1011041 | OC | MA1011041 | 46119 | 2026-04-07 | 1 | 0-4008 | TAPE ELEC BLACK 3/4INX60YD 10/ | 100 | 97.68 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -97.68 | 0
ttJTrans | 0-4008 | OC | MA1011041 | OC | MA1011041 | 46119 | 2026-04-07 | 2 | 0-4008 | TAPE ELECTRICAL 3/4IN RED | 100 | 97.68 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -97.68 | 0
ttJTrans | 0-4008 | OC | MA1011041 | OC | MA1011041 | 46119 | 2026-04-07 | 7 | 0-4008 | PORTABLE FOLDING TABLE 6FT | 6 | 487.18 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 487.18 | 0
ttJTrans | 0-4008 | OC | MA1011041 | OC | MA1011041 | 46119 | 2026-04-07 | 3 | 0-4008 | TAPE ELECTRIAL 3/4IN BLUE | 100 | 97.68 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 97.68 | 0
ttJTrans | 0-4008 | OC | MA1011041 | OC | MA1011041 | 46119 | 2026-04-07 | 4 | 0-4008 | BALL MARKER LOCATOR 5 FT RANGE | 60 | 1756.24 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -1756.24 | 0
ttJTrans | 0-4008 | OC | MA1011041 | OC | MA1011041 | 46119 | 2026-04-07 | 6 | 0-4008 | TENT CANOPY BLUE 12X12 BLUE | 6 | 799.2 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 799.2 | 0
ttJTrans | 0-4008 | OC | MA1011041 | OC | MA1011041 | 46119 | 2026-04-07 | 5 | 0-4008 | TAPE ELEC SUPER 33 3/4INX52FT | 100 | 759.24 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 759.24 | 0
ttJTrans | 0-4008 | OC | MA1011041 | OC | MA1011041 | 46119 | 2026-04-07 | 9 | 0-4008 | Freight | 1 | 133.2 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -133.2 | 0
ttJTrans | 0-4008 | OC | MA1011041 | OC | MA1011041 | 46119 | 2026-04-07 | 8 | 0-4008 | PORTABLE SAW HORSE 2PK | 6 | 365.3 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -365.3 | 0
ttJTrans | 0-4008 | OC | MA1011041 | OC | MA1011041 | 46119 | 2026-04-07 | 7 | 0-4008 | PORTABLE FOLDING TABLE 6FT | 6 | 487.18 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -487.18 | 0
ttJTrans | 0-4008 | OC | MA1011041 | OC | MA1011041 | 46119 | 2026-04-07 | 6 | 0-4008 | TENT CANOPY BLUE 12X12 BLUE | 6 | 799.2 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -799.2 | 0
ttJTrans | 0-4008 | OC | MA1011041 | OC | MA1011041 | 46119 | 2026-04-07 | 5 | 0-4008 | TAPE ELEC SUPER 33 3/4INX52FT | 100 | 759.24 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -759.24 | 0
ttJTrans | 0-4008 | OC | MA1011041 | OC | MA1011041 | 46119 | 2026-04-07 | 1 | 0-4008 | TAPE ELEC BLACK 3/4INX60YD 10/ | 100 | 97.68 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 97.68 | 0
ttJTrans | 0-4008 | OC | MA1011041 | OC | MA1011041 | 46119 | 2026-04-07 | 3 | 0-4008 | TAPE ELECTRIAL 3/4IN BLUE | 100 | 97.68 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -97.68 | 0
ttJTrans | 0-4008 | OC | MA1011041 | OC | MA1011041 | 46119 | 2026-04-07 | 9 | 0-4008 | Freight | 1 | 133.2 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 133.2 | 0
ttJTrans | 0-4008 | OC | MA1011041 | OC | MA1011041 | 46119 | 2026-04-07 | 4 | 0-4008 | BALL MARKER LOCATOR 5 FT RANGE | 60 | 1756.24 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 1756.24 | 0
ttJTrans | 0-4008 | OC | MA1011041 | OC | MA1011041 | 46119 | 2026-04-07 | 8 | 0-4008 | PORTABLE SAW HORSE 2PK | 6 | 365.3 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 365.3 | 0
ttJTrans | 0-4008 | OC | MA1011041 | OC | MA1011041 | 46119 | 2026-04-07 | 2 | 0-4008 | TAPE ELECTRICAL 3/4IN RED | 100 | 97.68 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 97.68 | 0
ttJTrans | 0-4008 | OC | MA1011041 | OC | MA1011041 | 46119 | 2026-04-29 | 2 | 0-4008 | TAPE ELECTRICAL 3/4IN RED | 100 | 97.68 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011041 | OC | MA1011041 | 46119 | 2026-04-29 | 1 | 0-4008 | TAPE ELEC BLACK 3/4INX60YD 10/ | 100 | 97.68 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011041 | OC | MA1011041 | 46119 | 2026-04-29 | 6 | 0-4008 | TENT CANOPY BLUE 12X12 BLUE | 6 | 799.2 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011041 | OC | MA1011041 | 46119 | 2026-04-29 | 9 | 0-4008 | Freight | 1 | 133.2 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011041 | OC | MA1011041 | 46119 | 2026-04-29 | 8 | 0-4008 | PORTABLE SAW HORSE 2PK | 6 | 365.3 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011041 | OC | MA1011041 | 46119 | 2026-04-29 | 7 | 0-4008 | PORTABLE FOLDING TABLE 6FT | 6 | 487.18 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011041 | OC | MA1011041 | 46119 | 2026-04-29 | 5 | 0-4008 | TAPE ELEC SUPER 33 3/4INX52FT | 100 | 759.24 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011041 | OC | MA1011041 | 46119 | 2026-04-29 | 4 | 0-4008 | BALL MARKER LOCATOR 5 FT RANGE | 60 | 1756.24 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011041 | OC | MA1011041 | 46119 | 2026-04-29 | 3 | 0-4008 | TAPE ELECTRIAL 3/4IN BLUE | 100 | 97.68 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011064 | OC | MA1011064 | 46120 | 2026-04-23 | 2 | 0-4008 | Shipping | 1 | 15.08 | INVOICE | 12747 | GRAINGER, INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011064 | OC | MA1011064 | 46120 | 2026-04-23 | 1 | 0-4008 | Spill containment patches | 6 | 233.5 | INVOICE | 12747 | GRAINGER, INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011064 | OC | MA1011064 | 46120 | 2026-04-08 | 1 | 0-4008 | Spill containment patches | 6 | 233.5 | PO:COMMIT | 12747 | GRAINGER, INC. | 0 | 0 | 233.5 | 0
ttJTrans | 0-4008 | OC | MA1011064 | OC | MA1011064 | 46120 | 2026-04-08 | 1 | 0-4008 | Spill containment patches | 6 | 233.5 | INVOICE:ADJ-COMMIT | 12747 | GRAINGER, INC. | 0 | 0 | -233.5 | 0
ttJTrans | 0-4008 | OC | MA1011064 | OC | MA1011064 | 46120 | 2026-04-08 | 2 | 0-4008 | Shipping | 1 | 15.08 | INVOICE:ADJ-COMMIT | 12747 | GRAINGER, INC. | 0 | 0 | -15.08 | 0
ttJTrans | 0-4008 | OC | MA1011064 | OC | MA1011064 | 46120 | 2026-04-08 | 2 | 0-4008 | Shipping | 1 | 15.08 | PO:COMMIT | 12747 | GRAINGER, INC. | 0 | 0 | 15.08 | 0
ttJTrans | 0-4008 | OC | MA1011067 | OC | MA1011067 | 46120 | 2026-04-08 | 1 | 0-4008 | 42" Truck safety light bars | 10 | 598.96 | PO:COMMIT | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | 598.96 | 0
ttJTrans | 0-4008 | OC | MA1011067 | OC | MA1011067 | 46120 | 2026-04-08 | 1 | 0-4008 | 42" Truck safety light bars | 10 | 598.96 | INVOICE:ADJ-COMMIT | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | -598.96 | 0
ttJTrans | 0-4008 | OC | MA1011067 | OC | MA1011067 | 46120 | 2026-04-16 | 1 | 0-4008 | 42" Truck safety light bars | 10 | 598.96 | INVOICE | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011085 | OC | MA1011085 | 46121 | 2026-04-27 | 1 | 0-4008 | Pallet water | 84 | 344.06 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011085 | OC | MA1011085 | 46121 | 2026-04-27 | 2 | 0-4008 | Freight | 1 | 88.8 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011085 | OC | MA1011085 | 46121 | 2026-04-10 | 1 | 0-4008 | Pallet water | 84 | 344.06 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 344.06 | 0
ttJTrans | 0-4008 | OC | MA1011085 | OC | MA1011085 | 46121 | 2026-04-10 | 2 | 0-4008 | Freight | 1 | 88.8 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -88.8 | 0
ttJTrans | 0-4008 | OC | MA1011085 | OC | MA1011085 | 46121 | 2026-04-10 | 2 | 0-4008 | Freight | 1 | 88.8 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 88.8 | 0
ttJTrans | 0-4008 | OC | MA1011085 | OC | MA1011085 | 46121 | 2026-04-10 | 1 | 0-4008 | Pallet water | 84 | 344.06 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -344.06 | 0
ttJTrans | 0-4008 | OC | MA1011088 | OC | MA1011088 | 46121 | 2026-04-10 | 6 | 0-4008 | THREAD SEAL TPE 1/2X260" | 1 | 1.99 | INVOICE:ADJ-COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | -1.99 | 0
ttJTrans | 0-4008 | OC | MA1011088 | OC | MA1011088 | 46121 | 2026-04-10 | 2 | 0-4008 | AIR PLUG "I/M" 3/8"MPT | 1 | 3.98 | INVOICE:ADJ-COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | -3.98 | 0
ttJTrans | 0-4008 | OC | MA1011088 | OC | MA1011088 | 46121 | 2026-04-10 | 3 | 0-4008 | AIR COUPLER"I/M"3/8"MNPT | 1 | 19.97 | INVOICE:ADJ-COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | -19.97 | 0
ttJTrans | 0-4008 | OC | MA1011088 | OC | MA1011088 | 46121 | 2026-04-10 | 7 | 0-4008 | BUSHING HEX GALV3/8X1/4" | 1 | 5.09 | INVOICE:ADJ-COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | -5.09 | 0
ttJTrans | 0-4008 | OC | MA1011088 | OC | MA1011088 | 46121 | 2026-04-10 | 5 | 0-4008 | BUSHING HEX GALV3/8X1/4" | 1 | 5.09 | INVOICE:ADJ-COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | -5.09 | 0
ttJTrans | 0-4008 | OC | MA1011088 | OC | MA1011088 | 46121 | 2026-04-10 | 6 | 0-4008 | THREAD SEAL TPE 1/2X260" | 1 | 1.99 | PO:COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 1.99 | 0
ttJTrans | 0-4008 | OC | MA1011088 | OC | MA1011088 | 46121 | 2026-04-10 | 4 | 0-4008 | COUPLE REDC 1/2X3/8"FIP | 1 | 3.32 | PO:COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 3.32 | 0
ttJTrans | 0-4008 | OC | MA1011088 | OC | MA1011088 | 46121 | 2026-04-10 | 3 | 0-4008 | AIR COUPLER"I/M"3/8"MNPT | 1 | 19.97 | PO:COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 19.97 | 0
ttJTrans | 0-4008 | OC | MA1011088 | OC | MA1011088 | 46121 | 2026-04-10 | 1 | 0-4008 | COUPLER/PLUG SET 1/4"I/M | 1 | 11.09 | INVOICE:ADJ-COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | -11.09 | 0
ttJTrans | 0-4008 | OC | MA1011088 | OC | MA1011088 | 46121 | 2026-04-10 | 8 | 0-4008 | RED COUPLNG GLV 1/2X1/4" | 1 | 3.32 | INVOICE:ADJ-COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | -3.32 | 0
ttJTrans | 0-4008 | OC | MA1011088 | OC | MA1011088 | 2026-04-09 | 2026-04-10 | 7 | 0-4008 | BUSHING HEX GALV3/8X1/4" | 1 | 5.09 | PO:COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 5.09 | 0
ttJTrans | 0-4008 | OC | MA1011088 | OC | MA1011088 | 2026-04-09 | 2026-04-10 | 2 | 0-4008 | AIR PLUG "I/M" 3/8"MPT | 1 | 3.98 | PO:COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 3.98 | 0
ttJTrans | 0-4008 | OC | MA1011088 | OC | MA1011088 | 2026-04-09 | 2026-04-10 | 5 | 0-4008 | BUSHING HEX GALV3/8X1/4" | 1 | 5.09 | PO:COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 5.09 | 0
ttJTrans | 0-4008 | OC | MA1011088 | OC | MA1011088 | 2026-04-09 | 2026-04-10 | 1 | 0-4008 | COUPLER/PLUG SET 1/4"I/M | 1 | 11.09 | PO:COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 11.09 | 0
ttJTrans | 0-4008 | OC | MA1011088 | OC | MA1011088 | 2026-04-09 | 2026-04-10 | 4 | 0-4008 | COUPLE REDC 1/2X3/8"FIP | 1 | 3.32 | INVOICE:ADJ-COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | -3.32 | 0
ttJTrans | 0-4008 | OC | MA1011088 | OC | MA1011088 | 2026-04-09 | 2026-04-10 | 8 | 0-4008 | RED COUPLNG GLV 1/2X1/4" | 1 | 3.32 | PO:COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 3.32 | 0
ttJTrans | 0-4008 | OC | MA1011088 | OC | MA1011088 | 2026-04-09 | 2026-04-16 | 3 | 0-4008 | AIR COUPLER"I/M"3/8"MNPT | 1 | 19.97 | INVOICE | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011088 | OC | MA1011088 | 2026-04-09 | 2026-04-16 | 5 | 0-4008 | BUSHING HEX GALV3/8X1/4" | 1 | 5.09 | INVOICE | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011088 | OC | MA1011088 | 46121 | 2026-04-16 | 1 | 0-4008 | COUPLER/PLUG SET 1/4"I/M | 1 | 11.09 | INVOICE | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011088 | OC | MA1011088 | 46121 | 2026-04-16 | 2 | 0-4008 | AIR PLUG "I/M" 3/8"MPT | 1 | 3.98 | INVOICE | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011088 | OC | MA1011088 | 46121 | 2026-04-16 | 6 | 0-4008 | THREAD SEAL TPE 1/2X260" | 1 | 1.99 | INVOICE | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011088 | OC | MA1011088 | 46121 | 2026-04-16 | 7 | 0-4008 | BUSHING HEX GALV3/8X1/4" | 1 | 5.09 | INVOICE | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011088 | OC | MA1011088 | 46121 | 2026-04-16 | 8 | 0-4008 | RED COUPLNG GLV 1/2X1/4" | 1 | 3.32 | INVOICE | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011088 | OC | MA1011088 | 46121 | 2026-04-16 | 4 | 0-4008 | COUPLE REDC 1/2X3/8"FIP | 1 | 3.32 | INVOICE | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011103 | OC | MA1011103 | 46121 | 2026-04-10 | 1 | 0-4008 | Annual Fire Extinguisher Inspection - 27 | 1 | 388.5 | PO:COMMIT | 21395 | ALLIED FIRE PROTECTION, LLC | 0 | 0 | 388.5 | 0
ttJTrans | 0-4008 | OC | MA1011112 | OC | MA1011112 | 46121 | 2026-04-10 | 2 | 0-4008 | 1IN NAIL PAC W CAPS | 40 | 8880 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 8880 | 0
ttJTrans | 0-4008 | OC | MA1011112 | OC | MA1011112 | 46121 | 2026-04-10 | 3 | 0-4008 | FREIGHT EST TBD SUBJECT TO CHANGE | 1 | 499.5 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 499.5 | 0
ttJTrans | 0-4008 | OC | MA1011112 | OC | MA1011112 | 46121 | 2026-04-10 | 1 | 0-4008 | STINGER NAIL GUN | 5 | 2358.75 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 2358.75 | 0
ttJTrans | 0-4008 | OC | MA1011112 | OC | MA1011112 | 46121 | 2026-04-10 | 3 | 0-4008 | FREIGHT EST TBD SUBJECT TO CHANGE | 1 | 499.5 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -349.65 | 0
ttJTrans | 0-4008 | OC | MA1011112 | OC | MA1011112 | 46121 | 2026-04-10 | 2 | 0-4008 | 1IN NAIL PAC W CAPS | 40 | 8880 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -8880 | 0
ttJTrans | 0-4008 | OC | MA1011112 | OC | MA1011112 | 46121 | 2026-04-10 | 1 | 0-4008 | STINGER NAIL GUN | 5 | 2358.75 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -2358.75 | 0
ttJTrans | 0-4008 | OC | MA1011112 | OC | MA1011112 | 46121 | 2026-04-29 | 1 | 0-4008 | STINGER NAIL GUN | 5 | 2358.75 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011112 | OC | MA1011112 | 46121 | 2026-04-29 | 2 | 0-4008 | 1IN NAIL PAC W CAPS | 40 | 8880 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011112 | OC | MA1011112 | 46121 | 2026-04-29 | 3 | 0-4008 | FREIGHT EST TBD SUBJECT TO CHANGE | 1 | 499.5 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011124 | OC | MA1011124 | 46122 | 2026-04-27 | 4 | 0-4008 | FILTER PARTICULATE 3M P100 - 2 | 20 | 200.69 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011124 | OC | MA1011124 | 46122 | 2026-04-27 | 5 | 0-4008 | EARMUFF OVER THE NECK HONEYWEL | 20 | 568.99 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011124 | OC | MA1011124 | 46122 | 2026-04-27 | 2 | 0-4008 | RESPIRATOR HALF FACE MED 6000 | 5 | 93.24 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011124 | OC | MA1011124 | 46122 | 2026-04-27 | 3 | 0-4008 | RESPIRATOR HALF FACE LRG 6000 | 3 | 63 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011124 | OC | MA1011124 | 46122 | 2026-04-27 | 6 | 0-4008 | FRIEGHT | 1 | 133.2 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011124 | OC | MA1011124 | 46122 | 2026-04-27 | 1 | 0-4008 | GOGGLES CHEMICAL CLEAR 12/BX | 10 | 27.53 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011124 | OC | MA1011124 | 46122 | 2026-04-10 | 4 | 0-4008 | FILTER PARTICULATE 3M P100 - 2 | 20 | 200.69 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 200.69 | 0
ttJTrans | 0-4008 | OC | MA1011124 | OC | MA1011124 | 46122 | 2026-04-10 | 3 | 0-4008 | RESPIRATOR HALF FACE LRG 6000 | 3 | 63 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 63 | 0
ttJTrans | 0-4008 | OC | MA1011124 | OC | MA1011124 | 46122 | 2026-04-10 | 6 | 0-4008 | FRIEGHT | 1 | 133.2 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 133.2 | 0
ttJTrans | 0-4008 | OC | MA1011124 | OC | MA1011124 | 46122 | 2026-04-10 | 6 | 0-4008 | FRIEGHT | 1 | 133.2 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -133.2 | 0
ttJTrans | 0-4008 | OC | MA1011124 | OC | MA1011124 | 46122 | 2026-04-10 | 4 | 0-4008 | FILTER PARTICULATE 3M P100 - 2 | 20 | 200.69 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -200.69 | 0
ttJTrans | 0-4008 | OC | MA1011124 | OC | MA1011124 | 46122 | 2026-04-10 | 5 | 0-4008 | EARMUFF OVER THE NECK HONEYWEL | 20 | 568.99 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -568.99 | 0
ttJTrans | 0-4008 | OC | MA1011124 | OC | MA1011124 | 46122 | 2026-04-10 | 3 | 0-4008 | RESPIRATOR HALF FACE LRG 6000 | 3 | 63 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -63 | 0
ttJTrans | 0-4008 | OC | MA1011124 | OC | MA1011124 | 46122 | 2026-04-10 | 2 | 0-4008 | RESPIRATOR HALF FACE MED 6000 | 5 | 93.24 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -93.24 | 0
ttJTrans | 0-4008 | OC | MA1011124 | OC | MA1011124 | 46122 | 2026-04-10 | 5 | 0-4008 | EARMUFF OVER THE NECK HONEYWEL | 20 | 568.99 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 568.99 | 0
ttJTrans | 0-4008 | OC | MA1011124 | OC | MA1011124 | 46122 | 2026-04-10 | 1 | 0-4008 | GOGGLES CHEMICAL CLEAR 12/BX | 10 | 27.53 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 27.53 | 0
ttJTrans | 0-4008 | OC | MA1011124 | OC | MA1011124 | 46122 | 2026-04-10 | 2 | 0-4008 | RESPIRATOR HALF FACE MED 6000 | 5 | 93.24 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 93.24 | 0
ttJTrans | 0-4008 | OC | MA1011124 | OC | MA1011124 | 2026-04-10 | 2026-04-10 | 1 | 0-4008 | GOGGLES CHEMICAL CLEAR 12/BX | 10 | 27.53 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -27.53 | 0
ttJTrans | 0-4008 | OC | MA1011185 | OC | MA1011185 | 2026-04-13 | 2026-04-15 | 3 | 0-4008 | Bag 48 Lath | 1 | 98.04 | PO:COMMIT | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | 98.04 | 0
ttJTrans | 0-4008 | OC | MA1011185 | OC | MA1011185 | 2026-04-13 | 2026-04-15 | 2 | 0-4008 | Tape Pocket 25 x 1 tenth inches | 1 | 16.32 | PO:COMMIT | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | 16.32 | 0
ttJTrans | 0-4008 | OC | MA1011185 | OC | MA1011185 | 46125 | 2026-04-15 | 2 | 0-4008 | Tape Pocket 25 x 1 tenth inches | 1 | 16.32 | INVOICE:ADJ-COMMIT | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | -16.32 | 0
ttJTrans | 0-4008 | OC | MA1011185 | OC | MA1011185 | 2026-04-13 | 2026-04-15 | 3 | 0-4008 | Bag 48 Lath | 1 | 98.04 | INVOICE:ADJ-COMMIT | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | -98.04 | 0
ttJTrans | 0-4008 | OC | MA1011185 | OC | MA1011185 | 46125 | 2026-04-15 | 4 | 0-4008 | Red paint | 1 | 60.15 | INVOICE:ADJ-COMMIT | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | -60.15 | 0
ttJTrans | 0-4008 | OC | MA1011185 | OC | MA1011185 | 46125 | 2026-04-15 | 5 | 0-4008 | Pink paint | 1 | 60.15 | INVOICE:ADJ-COMMIT | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | -60.15 | 0
ttJTrans | 0-4008 | OC | MA1011185 | OC | MA1011185 | 46125 | 2026-04-15 | 1 | 0-4008 | 1/2" X 2, 48 Stakes | 48 | 2873.53 | INVOICE:ADJ-COMMIT | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | -2873.53 | 0
ttJTrans | 0-4008 | OC | MA1011185 | OC | MA1011185 | 46125 | 2026-04-15 | 1 | 0-4008 | 1/2" X 2, 48 Stakes | 48 | 2873.53 | PO:COMMIT | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | 2873.53 | 0
ttJTrans | 0-4008 | OC | MA1011185 | OC | MA1011185 | 46125 | 2026-04-15 | 6 | 0-4008 | Rebar stakes 5/8 X 24 | 1 | 47.82 | INVOICE:ADJ-COMMIT | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | -47.82 | 0
ttJTrans | 0-4008 | OC | MA1011185 | OC | MA1011185 | 46125 | 2026-04-15 | 5 | 0-4008 | Pink paint | 1 | 60.15 | PO:COMMIT | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | 60.15 | 0
ttJTrans | 0-4008 | OC | MA1011185 | OC | MA1011185 | 46125 | 2026-04-15 | 6 | 0-4008 | Rebar stakes 5/8 X 24 | 1 | 47.82 | PO:COMMIT | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | 47.82 | 0
ttJTrans | 0-4008 | OC | MA1011185 | OC | MA1011185 | 2026-04-13 | 2026-04-15 | 4 | 0-4008 | Red paint | 1 | 60.15 | PO:COMMIT | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | 60.15 | 0
ttJTrans | 0-4008 | OC | MA1011185 | OC | MA1011185 | 2026-04-13 | 2026-04-28 | 5 | 0-4008 | Pink paint | 1 | 60.15 | INVOICE | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011185 | OC | MA1011185 | 2026-04-13 | 2026-04-28 | 4 | 0-4008 | Red paint | 1 | 60.15 | INVOICE | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011185 | OC | MA1011185 | 46125 | 2026-04-28 | 3 | 0-4008 | Bag 48 Lath | 1 | 98.04 | INVOICE | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011185 | OC | MA1011185 | 46125 | 2026-04-28 | 2 | 0-4008 | Tape Pocket 25 x 1 tenth inches | 1 | 16.32 | INVOICE | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011185 | OC | MA1011185 | 46125 | 2026-04-28 | 6 | 0-4008 | Rebar stakes 5/8 X 24 | 1 | 47.82 | INVOICE | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011185 | OC | MA1011185 | 46125 | 2026-04-28 | 1 | 0-4008 | 1/2" X 2, 48 Stakes | 48 | 2873.53 | INVOICE | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011202 | OC | MA1011202 | 46126 | 2026-04-29 | 3 | 0-4008 | Freight | 1 | 133.2 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011202 | OC | MA1011202 | 46126 | 2026-04-29 | 2 | 0-4008 | Steel drums | 4 | 472.82 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011202 | OC | MA1011202 | 46126 | 2026-04-29 | 1 | 0-4008 | Absorbent pads | 2 | 45.89 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011202 | OC | MA1011202 | 46126 | 2026-04-15 | 2 | 0-4008 | Steel drums | 4 | 472.82 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -472.82 | 0
ttJTrans | 0-4008 | OC | MA1011202 | OC | MA1011202 | 46126 | 2026-04-15 | 3 | 0-4008 | Freight | 1 | 133.2 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -133.2 | 0
ttJTrans | 0-4008 | OC | MA1011202 | OC | MA1011202 | 46126 | 2026-04-15 | 1 | 0-4008 | Absorbent pads | 2 | 45.89 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 45.89 | 0
ttJTrans | 0-4008 | OC | MA1011202 | OC | MA1011202 | 46126 | 2026-04-15 | 2 | 0-4008 | Steel drums | 4 | 472.82 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 472.82 | 0
ttJTrans | 0-4008 | OC | MA1011202 | OC | MA1011202 | 46126 | 2026-04-15 | 3 | 0-4008 | Freight | 1 | 133.2 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 133.2 | 0
ttJTrans | 0-4008 | OC | MA1011202 | OC | MA1011202 | 46126 | 2026-04-15 | 1 | 0-4008 | Absorbent pads | 2 | 45.89 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -45.89 | 0
ttJTrans | 0-4008 | OC | MA1011230 | OC | MA1011230 | 46127 | 2026-04-15 | 1 | 0-4008 | Replace 12 Fire extinguishers and inspection | 1 | 1219.89 | PO:COMMIT | 21395 | ALLIED FIRE PROTECTION, LLC | 0 | 0 | 1219.89 | 0
ttJTrans | 0-4008 | OC | MA1011235 | OC | MA1011235 | 46127 | 2026-04-15 | 2 | 0-4008 | FREIGHT | 1 | 44.4 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 44.4 | 0
ttJTrans | 0-4008 | OC | MA1011235 | OC | MA1011235 | 46127 | 2026-04-15 | 1 | 0-4008 | SPEED LIMIT SIGN 10MPH 12"X18" | 20 | 769.67 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -769.67 | 0
ttJTrans | 0-4008 | OC | MA1011235 | OC | MA1011235 | 46127 | 2026-04-15 | 2 | 0-4008 | FREIGHT | 1 | 44.4 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -44.4 | 0
ttJTrans | 0-4008 | OC | MA1011235 | OC | MA1011235 | 46127 | 2026-04-15 | 1 | 0-4008 | SPEED LIMIT SIGN 10MPH 12"X18" | 20 | 769.67 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 769.67 | 0
ttJTrans | 0-4008 | OC | MA1011235 | OC | MA1011235 | 46127 | 2026-04-29 | 1 | 0-4008 | SPEED LIMIT SIGN 10MPH 12"X18" | 20 | 769.67 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011235 | OC | MA1011235 | 46127 | 2026-04-29 | 2 | 0-4008 | FREIGHT | 1 | 44.4 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011252 | OC | MA1011252 | 46127 | 2026-04-29 | 2 | 0-4008 | 2" X 20' PVC | 20 | 5073.37 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011252 | OC | MA1011252 | 46127 | 2026-04-29 | 1 | 0-4008 | Orange Paint | 60 | 329.67 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011252 | OC | MA1011252 | 46127 | 2026-04-29 | 6 | 0-4008 | Glass cleaner | 24 | 100.17 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011252 | OC | MA1011252 | 46127 | 2026-04-29 | 7 | 0-4008 | Vis queen | 5 | 660.84 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011252 | OC | MA1011252 | 46127 | 2026-04-29 | 5 | 0-4008 | Rags | 3 | 107.76 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011252 | OC | MA1011252 | 46127 | 2026-04-29 | 4 | 0-4008 | Def fluid | 96 | 1737.99 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011252 | OC | MA1011252 | 46127 | 2026-04-16 | 2 | 0-4008 | 2" X 20' PVC | 20 | 5073.37 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -5073.37 | 0
ttJTrans | 0-4008 | OC | MA1011252 | OC | MA1011252 | 46127 | 2026-04-16 | 4 | 0-4008 | Def fluid | 96 | 1737.99 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -1737.99 | 0
ttJTrans | 0-4008 | OC | MA1011252 | OC | MA1011252 | 46127 | 2026-04-16 | 7 | 0-4008 | Vis queen | 5 | 660.84 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -660.84 | 0
ttJTrans | 0-4008 | OC | MA1011252 | OC | MA1011252 | 46127 | 2026-04-16 | 6 | 0-4008 | Glass cleaner | 24 | 100.17 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -100.17 | 0
ttJTrans | 0-4008 | OC | MA1011252 | OC | MA1011252 | 46127 | 2026-04-16 | 1 | 0-4008 | Orange Paint | 60 | 329.67 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -329.67 | 0
ttJTrans | 0-4008 | OC | MA1011252 | OC | MA1011252 | 46127 | 2026-04-16 | 1 | 0-4008 | Orange Paint | 60 | 329.67 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 329.67 | 0
ttJTrans | 0-4008 | OC | MA1011252 | OC | MA1011252 | 46127 | 2026-04-16 | 5 | 0-4008 | Rags | 3 | 107.76 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -107.76 | 0
ttJTrans | 0-4008 | OC | MA1011252 | OC | MA1011252 | 46127 | 2026-04-16 | 4 | 0-4008 | Def fluid | 96 | 1737.99 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 1737.99 | 0
ttJTrans | 0-4008 | OC | MA1011252 | OC | MA1011252 | 46127 | 2026-04-16 | 7 | 0-4008 | Vis queen | 5 | 660.84 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 660.84 | 0
ttJTrans | 0-4008 | OC | MA1011252 | OC | MA1011252 | 46127 | 2026-04-16 | 6 | 0-4008 | Glass cleaner | 24 | 100.17 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 100.17 | 0
ttJTrans | 0-4008 | OC | MA1011252 | OC | MA1011252 | 46127 | 2026-04-16 | 5 | 0-4008 | Rags | 3 | 107.76 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 107.76 | 0
ttJTrans | 0-4008 | OC | MA1011252 | OC | MA1011252 | 46127 | 2026-04-16 | 2 | 0-4008 | 2" X 20' PVC | 20 | 5073.37 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 5073.37 | 0
ttJTrans | 0-4008 | OC | MA1011341 | OC | MA1011341 | 46132 | 2026-04-21 | 1 | 0-4008 | Delineator Post with Base - 45", Lime | 30 | 1098.9 | INVOICE:ADJ-COMMIT | 13343 | ULINE INC. | 0 | 0 | -1098.9 | 0
ttJTrans | 0-4008 | OC | MA1011341 | OC | MA1011341 | 46132 | 2026-04-21 | 2 | 0-4008 | Shipping | 1 | 219.76 | INVOICE:ADJ-COMMIT | 13343 | ULINE INC. | 0 | 0 | -219.76 | 0
ttJTrans | 0-4008 | OC | MA1011341 | OC | MA1011341 | 46132 | 2026-04-21 | 2 | 0-4008 | Shipping | 1 | 219.76 | PO:COMMIT | 13343 | ULINE INC. | 0 | 0 | 219.76 | 0
ttJTrans | 0-4008 | OC | MA1011341 | OC | MA1011341 | 46132 | 2026-04-21 | 1 | 0-4008 | Delineator Post with Base - 45", Lime | 30 | 1098.9 | PO:COMMIT | 13343 | ULINE INC. | 0 | 0 | 1098.9 | 0
ttJTrans | 0-4008 | OC | MA1011341 | OC | MA1011341 | 46132 | 2026-04-29 | 1 | 0-4008 | Delineator Post with Base - 45", Lime | 30 | 1098.9 | INVOICE | 13343 | ULINE INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011341 | OC | MA1011341 | 46132 | 2026-04-29 | 2 | 0-4008 | Shipping | 1 | 219.76 | INVOICE | 13343 | ULINE INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011382 | OC | MA1011382 | 46133 | 2026-05-07 | 1 | 0-4008 | Seagate expansion 22TB hard drive - For | 1 | 665.93 | INVOICE | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011382 | OC | MA1011382 | 46133 | 2026-05-07 | 2 | 0-4008 | Sandisk 256GB microSD card - For Manny | 1 | 64.16 | INVOICE | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011382 | OC | MA1011382 | 46133 | 2026-04-27 | 1 | 0-4008 | Seagate expansion 22TB hard drive - For | 1 | 665.93 | PO:COMMIT | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | 665.93 | 0
ttJTrans | 0-4008 | OC | MA1011382 | OC | MA1011382 | 46133 | 2026-04-27 | 2 | 0-4008 | Sandisk 256GB microSD card - For Manny | 1 | 64.16 | PO:COMMIT | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | 64.16 | 0
ttJTrans | 0-4008 | OC | MA1011382 | OC | MA1011382 | 46133 | 2026-04-27 | 2 | 0-4008 | Sandisk 256GB microSD card - For Manny | 1 | 64.16 | INVOICE:ADJ-COMMIT | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | -64.16 | 0
ttJTrans | 0-4008 | OC | MA1011382 | OC | MA1011382 | 46133 | 2026-04-27 | 1 | 0-4008 | Seagate expansion 22TB hard drive - For | 1 | 665.93 | INVOICE:ADJ-COMMIT | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | -665.93 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 46134 | 2026-04-24 | 25 | 0-4008 | TDB EST FREIGHT | 1 | 333 | PO:COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 333 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 46134 | 2026-04-24 | 23 | 0-4008 | 34IN WHEELER HAND HELD MARKING | 1 | 40.61 | PO:COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 40.61 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 46134 | 2026-04-24 | 18 | 0-4008 | 11IN CORN WHISK BROOM | 6 | 25.57 | PO:COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 25.57 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 46134 | 2026-04-24 | 19 | 0-4008 | 11IN BLACK CABLE TIE 50LBS | 1 | 6.39 | PO:COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 6.39 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 46134 | 2026-04-24 | 20 | 0-4008 | UL #S-25690 BLUE MICROFIBER | 1 | 83.25 | PO:COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 83.25 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 46134 | 2026-04-24 | 21 | 0-4008 | WHITE PAINT MARKER | 12 | 53.68 | PO:COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 53.68 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 46134 | 2026-04-24 | 22 | 0-4008 | 17OZ FLUORESENT ORANGE SOLVENT | 12 | 70.86 | PO:COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 70.86 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 46134 | 2026-04-24 | 16 | 0-4008 | 25LB NEAR WHITE RAGS | 1 | 29.6 | PO:COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 29.6 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 46134 | 2026-04-24 | 17 | 0-4008 | 18OZ GLASS CLEANER | 12 | 84.72 | PO:COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 84.72 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 46134 | 2026-04-24 | 12 | 0-4008 | 44-7/8IN 14/18T PORTABLE BAND | 5 | 34.52 | PO:COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 34.52 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 46134 | 2026-04-24 | 13 | 0-4008 | 2IN X 60YD SILVER DUCT TAPE | 48 | 312.22 | PO:COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 312.22 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 46134 | 2026-04-24 | 14 | 0-4008 | TYTVT3460311B | 100 | 95.46 | PO:COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 95.46 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 46134 | 2026-04-24 | 8 | 0-4008 | SC #ZCS2511 1/2IN KELLUM GRIP | 6 | 589.68 | PO:COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 589.68 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 46134 | 2026-04-24 | 9 | 0-4008 | SC #ZCS2520 3/4IN KELLUM GRIP | 6 | 769.76 | PO:COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 769.76 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 46134 | 2026-04-24 | 10 | 0-4008 | 7/8IN SCREW PIN ANCHOR SHACKLE | 15 | 501 | PO:COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 501 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 46134 | 2026-04-24 | 11 | 0-4008 | 3/4X50FT DOUBLE BRAID EYES | 30 | 6474.19 | PO:COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 6474.19 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 46134 | 2026-04-24 | 24 | 0-4008 | 1IN X 35FT POWERLOCK TAPE | 9 | 254.94 | PO:COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 254.94 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 46134 | 2026-04-24 | 7 | 0-4008 | SC #ZCS2517 2-1/2-3IN KELLUM | 30 | 4020.64 | INVOICE:ADJ-COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | -4020.64 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 46134 | 2026-04-24 | 9 | 0-4008 | SC #ZCS2520 3/4IN KELLUM GRIP | 6 | 769.76 | INVOICE:ADJ-COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | -769.76 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 46134 | 2026-04-24 | 3 | 0-4008 | SC #ZCS3508 1-1/2-2IN KELLUM | 9 | 2390.91 | INVOICE:ADJ-COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | -2390.91 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 46134 | 2026-04-24 | 5 | 0-4008 | SC #ZCS2515 1-1/2-2IN KELLUM | 30 | 3380.95 | PO:COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 3380.95 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 46134 | 2026-04-24 | 1 | 0-4008 | SC #ZCS3506 KELLUM GRIP | 3 | 528.9 | PO:COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 528.9 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 46134 | 2026-04-24 | 1 | 0-4008 | SC #ZCS3506 KELLUM GRIP | 3 | 528.9 | INVOICE:ADJ-COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | -528.9 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 46134 | 2026-04-24 | 11 | 0-4008 | 3/4X50FT DOUBLE BRAID EYES | 30 | 6474.19 | INVOICE:ADJ-COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | -6474.19 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 46134 | 2026-04-24 | 6 | 0-4008 | SC #ZCS2523 2-2-1/2 KELLUM | 30 | 4607.06 | PO:COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 4607.06 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 46134 | 2026-04-24 | 2 | 0-4008 | SC #ZCS3507 1-1-1/2 KELLUM | 9 | 2327.77 | PO:COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 2327.77 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-04-24 | 6 | 0-4008 | SC #ZCS2523 2-2-1/2 KELLUM | 30 | 4607.06 | INVOICE:ADJ-COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | -3992.79 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 46134 | 2026-04-24 | 5 | 0-4008 | SC #ZCS2515 1-1/2-2IN KELLUM | 30 | 3380.95 | INVOICE:ADJ-COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | -3380.95 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 46134 | 2026-04-24 | 2 | 0-4008 | SC #ZCS3507 1-1-1/2 KELLUM | 9 | 2327.77 | INVOICE:ADJ-COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | -2327.77 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-04-24 | 22 | 0-4008 | 17OZ FLUORESENT ORANGE SOLVENT | 12 | 70.86 | INVOICE:ADJ-COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | -70.86 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-04-24 | 21 | 0-4008 | WHITE PAINT MARKER | 12 | 53.68 | INVOICE:ADJ-COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | -53.68 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-04-24 | 20 | 0-4008 | UL #S-25690 BLUE MICROFIBER | 1 | 83.25 | INVOICE:ADJ-COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | -83.25 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-04-24 | 19 | 0-4008 | 11IN BLACK CABLE TIE 50LBS | 1 | 6.39 | INVOICE:ADJ-COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | -6.39 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-04-24 | 4 | 0-4008 | SC #ZCS3509 2-2-3/4 KELLUM | 9 | 2550.25 | PO:COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 2550.25 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-04-24 | 3 | 0-4008 | SC #ZCS3508 1-1/2-2IN KELLUM | 9 | 2390.91 | PO:COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 2390.91 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-04-24 | 7 | 0-4008 | SC #ZCS2517 2-1/2-3IN KELLUM | 30 | 4020.64 | PO:COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 4020.64 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-04-24 | 23 | 0-4008 | 34IN WHEELER HAND HELD MARKING | 1 | 40.61 | INVOICE:ADJ-COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | -40.61 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 46134 | 2026-04-24 | 24 | 0-4008 | 1IN X 35FT POWERLOCK TAPE | 9 | 254.94 | INVOICE:ADJ-COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | -254.94 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 46134 | 2026-04-24 | 13 | 0-4008 | 2IN X 60YD SILVER DUCT TAPE | 48 | 312.22 | INVOICE:ADJ-COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | -312.22 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-04-24 | 14 | 0-4008 | TYTVT3460311B | 100 | 95.46 | INVOICE:ADJ-COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | -95.46 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-04-24 | 16 | 0-4008 | 25LB NEAR WHITE RAGS | 1 | 29.6 | INVOICE:ADJ-COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | -29.6 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-04-24 | 17 | 0-4008 | 18OZ GLASS CLEANER | 12 | 84.72 | INVOICE:ADJ-COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | -84.72 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-04-24 | 25 | 0-4008 | TDB EST FREIGHT | 1 | 333 | INVOICE:ADJ-COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | -333 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-04-24 | 10 | 0-4008 | 7/8IN SCREW PIN ANCHOR SHACKLE | 15 | 501 | INVOICE:ADJ-COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | -501 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-04-24 | 12 | 0-4008 | 44-7/8IN 14/18T PORTABLE BAND | 5 | 34.52 | INVOICE:ADJ-COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | -34.52 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-04-24 | 18 | 0-4008 | 11IN CORN WHISK BROOM | 6 | 25.57 | INVOICE:ADJ-COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | -25.57 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-05-07 | 22 | 0-4008 | 17OZ FLUORESENT ORANGE SOLVENT | 12 | 70.86 | INVOICE | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-05-14 | 9 | 0-4008 | SC #ZCS2520 3/4IN KELLUM GRIP | 6 | 769.76 | INVOICE | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-05-14 | 5 | 0-4008 | SC #ZCS2515 1-1/2-2IN KELLUM | 30 | 3380.95 | INVOICE | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-05-14 | 6 | 0-4008 | SC #ZCS2523 2-2-1/2 KELLUM | 30 | 4607.06 | INVOICE | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-05-14 | 7 | 0-4008 | SC #ZCS2517 2-1/2-3IN KELLUM | 30 | 4020.64 | INVOICE | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-05-14 | 2 | 0-4008 | SC #ZCS3507 1-1-1/2 KELLUM | 9 | 2327.77 | INVOICE | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-05-14 | 3 | 0-4008 | SC #ZCS3508 1-1/2-2IN KELLUM | 9 | 2390.91 | INVOICE | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-05-14 | 1 | 0-4008 | SC #ZCS3506 KELLUM GRIP | 3 | 528.9 | INVOICE | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-05-20 | 11 | 0-4008 | 3/4X50FT DOUBLE BRAID EYES | 30 | 6474.19 | INVOICE | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-05-07 | 21 | 0-4008 | WHITE PAINT MARKER | 12 | 53.68 | INVOICE | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-05-07 | 20 | 0-4008 | UL #S-25690 BLUE MICROFIBER | 1 | 83.25 | INVOICE | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-05-07 | 19 | 0-4008 | 11IN BLACK CABLE TIE 50LBS | 1 | 6.39 | INVOICE | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-05-07 | 18 | 0-4008 | 11IN CORN WHISK BROOM | 6 | 25.57 | INVOICE | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-05-07 | 12 | 0-4008 | 44-7/8IN 14/18T PORTABLE BAND | 5 | 34.52 | INVOICE | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-05-07 | 10 | 0-4008 | 7/8IN SCREW PIN ANCHOR SHACKLE | 15 | 501 | INVOICE | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-05-07 | 25 | 0-4008 | TDB EST FREIGHT | 1 | 333 | INVOICE | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-05-07 | 17 | 0-4008 | 18OZ GLASS CLEANER | 12 | 84.72 | INVOICE | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-05-07 | 16 | 0-4008 | 25LB NEAR WHITE RAGS | 1 | 29.6 | INVOICE | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-05-07 | 14 | 0-4008 | TYTVT3460311B | 100 | 95.46 | INVOICE | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-05-07 | 13 | 0-4008 | 2IN X 60YD SILVER DUCT TAPE | 48 | 312.22 | INVOICE | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-05-07 | 24 | 0-4008 | 1IN X 35FT POWERLOCK TAPE | 9 | 254.94 | INVOICE | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-05-07 | 23 | 0-4008 | 34IN WHEELER HAND HELD MARKING | 1 | 40.61 | INVOICE | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011405 | OC | MA1011405 | 2026-04-22 | 2026-04-30 | 1 | 0-4008 | Box cutters W/ pouch | 20 | 210.01 | INVOICE | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011405 | OC | MA1011405 | 2026-04-22 | 2026-04-24 | 1 | 0-4008 | Box cutters W/ pouch | 20 | 210.01 | INVOICE:ADJ-COMMIT | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | -210.01 | 0
ttJTrans | 0-4008 | OC | MA1011405 | OC | MA1011405 | 2026-04-22 | 2026-04-24 | 1 | 0-4008 | Box cutters W/ pouch | 20 | 210.01 | PO:COMMIT | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | 210.01 | 0
ttJTrans | 0-4008 | OC | MA1011410 | OC | MA1011410 | 2026-04-22 | 2026-04-24 | 1 | 0-4008 | Replace (6) 2.5# ABC’s fire extinguishers | 1 | 1219.89 | PO:COMMIT | 21395 | ALLIED FIRE PROTECTION, LLC | 0 | 0 | 1219.89 | 0
ttJTrans | 0-4008 | OC | MA1011411 | OC | MA1011411 | 2026-04-22 | 2026-04-27 | 2 | 0-4008 | IPad 11 inch case | 6 | 154.45 | PO:COMMIT | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | 154.45 | 0
ttJTrans | 0-4008 | OC | MA1011411 | OC | MA1011411 | 2026-04-22 | 2026-04-27 | 1 | 0-4008 | Apple iPad 11 inch | 6 | 3056.94 | INVOICE:ADJ-COMMIT | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | -3056.94 | 0
ttJTrans | 0-4008 | OC | MA1011411 | OC | MA1011411 | 2026-04-22 | 2026-04-27 | 1 | 0-4008 | Apple iPad 11 inch | 6 | 3056.94 | PO:COMMIT | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | 3056.94 | 0
ttJTrans | 0-4008 | OC | MA1011411 | OC | MA1011411 | 2026-04-22 | 2026-04-27 | 2 | 0-4008 | IPad 11 inch case | 6 | 154.45 | INVOICE:ADJ-COMMIT | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | -154.45 | 0
ttJTrans | 0-4008 | OC | MA1011411 | OC | MA1011411 | 2026-04-22 | 2026-04-30 | 2 | 0-4008 | IPad 11 inch case | 6 | 154.45 | INVOICE | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011411 | OC | MA1011411 | 2026-04-22 | 2026-04-30 | 1 | 0-4008 | Apple iPad 11 inch | 6 | 3056.94 | INVOICE | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011423 | OC | MA1011423 | 2026-04-22 | 2026-04-30 | 2 | 0-4008 | 3" 3 Ring binders | 3 | 113.05 | INVOICE | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011423 | OC | MA1011423 | 2026-04-22 | 2026-04-30 | 1 | 0-4008 | HP 952 Ink combo | 2 | 166.48 | INVOICE | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011423 | OC | MA1011423 | 2026-04-22 | 2026-04-24 | 1 | 0-4008 | HP 952 Ink combo | 2 | 166.48 | INVOICE:ADJ-COMMIT | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | -166.48 | 0
ttJTrans | 0-4008 | OC | MA1011423 | OC | MA1011423 | 2026-04-22 | 2026-04-24 | 1 | 0-4008 | HP 952 Ink combo | 2 | 166.48 | PO:COMMIT | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | 166.48 | 0
ttJTrans | 0-4008 | OC | MA1011423 | OC | MA1011423 | 2026-04-22 | 2026-04-24 | 2 | 0-4008 | 3" 3 Ring binders | 3 | 113.05 | PO:COMMIT | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | 113.05 | 0
ttJTrans | 0-4008 | OC | MA1011423 | OC | MA1011423 | 2026-04-22 | 2026-04-24 | 2 | 0-4008 | 3" 3 Ring binders | 3 | 113.05 | INVOICE:ADJ-COMMIT | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | -96.4 | 0
ttJTrans | 0-4008 | OC | MA1011457 | OC | MA1011457 | 2026-04-24 | 2026-04-27 | 1 | 0-4008 | Wrapper twine | 20 | 3885 | PO:COMMIT | 19286 | PREMIER TRUCK RENTAL, LLC | 3885 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011457 | OC | MA1011457 | 2026-04-24 | 2026-04-27 | 2 | 0-4008 | Freight | 1 | 471.75 | PO:COMMIT | 19286 | PREMIER TRUCK RENTAL, LLC | 471.75 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 2026-04-24 | 2026-04-27 | 21 | 0-4008 | SHACKLE 1-1/2IN S-209 17 TON | 2 | 464.27 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 464.27 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 2026-04-24 | 2026-04-27 | 5 | 0-4008 | AIR TOOL ACCESORY KIT | 1 | 13.32 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 13.32 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 2026-04-24 | 2026-04-27 | 4 | 0-4008 | 50FT AIR HOSE | 2 | 81.59 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 81.59 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 2026-04-24 | 2026-04-27 | 32 | 0-4008 | SHOVEL SQUARE PT 45IN WOOD HDL | 2 | 20.6 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 20.6 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 2026-04-24 | 2026-04-27 | 22 | 0-4008 | LADDER STEP FBRGLS 8FT 300LB C | 2 | 468.33 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 468.33 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 2026-04-24 | 2026-04-27 | 34 | 0-4008 | UTILITY WATER PUMP | 1 | 149.85 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 149.85 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 2026-04-24 | 2026-04-27 | 20 | 0-4008 | SHACKLE 1-1/4IN S-209 12T | 6 | 913.15 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 913.15 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 2026-04-24 | 2026-04-27 | 19 | 0-4008 | SHACKLE 7/8IN S-209 6.5 TON | 4 | 213.56 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 213.56 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 2026-04-24 | 2026-04-27 | 3 | 0-4008 | RIGID 6 GAL AIR COMPRESSOR | 1 | 183.15 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 183.15 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 2026-04-24 | 2026-04-27 | 2 | 0-4008 | 29/PC 3/4DR IMP SOCKETS | 1 | 782.55 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 782.55 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 2026-04-24 | 2026-04-27 | 9 | 0-4008 | 33T SOFT SHACKLE | 4 | 3263.4 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 3263.4 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 2026-04-24 | 2026-04-27 | 8 | 0-4008 | SAMSON 22T RECOVERY ROPE | 2 | 12765 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 12765 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 2026-04-24 | 2026-04-27 | 7 | 0-4008 | BANDSAW COMPACT M18 FUEL DUEL | 2 | 951.69 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 951.69 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 2026-04-24 | 2026-04-27 | 27 | 0-4008 | HAMMER SLEDGE 12LB WOOD | 1 | 42 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 42 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 2026-04-24 | 2026-04-27 | 17 | 0-4008 | SLING ROUND 7 X 10 BLUE | 2 | 140.08 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 140.08 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 2026-04-24 | 2026-04-27 | 16 | 0-4008 | SLING ROUND 7 X 8 BLUE | 2 | 114.55 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 114.55 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 2026-04-24 | 2026-04-27 | 15 | 0-4008 | SLING ROUND 7 X 6 BLUE | 2 | 92.6 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 92.6 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 2026-04-24 | 2026-04-27 | 14 | 0-4008 | PULLER, T POST COMPLETE | 2 | 167.01 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 167.01 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 2026-04-24 | 2026-04-27 | 13 | 0-4008 | RADIO MOTOROLA 2 WAY 2/PK | 10 | 832.5 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 832.5 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 2026-04-24 | 2026-04-27 | 12 | 0-4008 | TAPE MEASURE 1/2INX100FT FBGLS | 2 | 58.19 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 58.19 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 2026-04-24 | 2026-04-27 | 11 | 0-4008 | DRIVER POST GAS 3-1/8IN GUIDE | 2 | 4705.69 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 4705.69 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 2026-04-24 | 2026-04-27 | 10 | 0-4008 | GUN GREASE M18 2SPEED KIT 10K | 2 | 806.04 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 806.04 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 2026-04-24 | 2026-04-27 | 26 | 0-4008 | HAMMER SET | 1 | 79.92 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 79.92 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 2026-04-24 | 2026-04-27 | 25 | 0-4008 | 450/PC 1/4,3/8,1/2 TOOL SET | 1 | 333 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 333 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 2026-04-24 | 2026-04-27 | 24 | 0-4008 | MAT HOOK 11TON SWIVEL W/LATCH | 2 | 758.42 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 758.42 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 2026-04-24 | 2026-04-27 | 23 | 0-4008 | 3/PC SPUD WRENCH SET W CASE | 2 | 133.2 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 133.2 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 2026-04-24 | 2026-04-27 | 46 | 0-4008 | INFLATOR M18 36IN HOSE 150PSI | 1 | 219.42 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 219.42 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 2026-04-24 | 2026-04-27 | 45 | 0-4008 | M&W LIFT BEAM 10000LB CAPACITY | 1 | 3052.5 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 3052.5 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 2026-04-24 | 2026-04-27 | 44 | 0-4008 | 420/PC COTTER PIN SET | 1 | 27.75 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 27.75 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 2026-04-24 | 2026-04-27 | 6 | 0-4008 | UNDERGROUND CABLE CUTTER 3IN | 2 | 8769 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 8769 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 2026-04-24 | 2026-04-27 | 1 | 0-4008 | WRENCH IMPACT 3/4IN M18 FUEL | 1 | 771.45 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 771.45 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 2026-04-24 | 2026-04-27 | 39 | 0-4008 | STRAP RATCHET 2INX27FT W FLAT | 4 | 73.62 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 73.62 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 2026-04-24 | 2026-04-27 | 38 | 0-4008 | 42IN REFELCTIVE TRAFFIC CONE | 4 | 310.8 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 310.8 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 2026-04-24 | 2026-04-27 | 37 | 0-4008 | DIGGING BAR 70IN | 1 | 116.55 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 116.55 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 46136 | 2026-04-27 | 36 | 0-4008 | GENERATOR GP6500 6500W PULL ST | 1 | 943.5 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 943.5 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 46136 | 2026-04-27 | 43 | 0-4008 | CAN GAS SAFETY 5GAL RED METAL | 1 | 84.06 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 84.06 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 46136 | 2026-04-27 | 42 | 0-4008 | CHARGER MILWAUKEE M18 6-CAPACI | 2 | 332.42 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 332.42 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 46136 | 2026-04-27 | 41 | 0-4008 | BATTERY M18 XC8.0AH MILWAUKEE | 4 | 1211.41 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 1211.41 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 46136 | 2026-04-27 | 40 | 0-4008 | STRAP RATCHET 1INX15FT S-HOOK | 10 | 116.22 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 116.22 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 46136 | 2026-04-27 | 35 | 0-4008 | ELECTRIC PRESSURE WASHER | 1 | 416.25 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 416.25 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 46136 | 2026-04-27 | 29 | 0-4008 | DRILL M18 1/2 CHECK TOOL ONLY | 1 | 157.84 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 157.84 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 46136 | 2026-04-27 | 28 | 0-4008 | 3/PC PRY BAR SET | 1 | 33.3 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 33.3 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 46136 | 2026-04-27 | 30 | 0-4008 | SHOVEL SHARP SHOOTER D-HDL 6/B | 4 | 52.35 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 52.35 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 46136 | 2026-04-27 | 33 | 0-4008 | 65 GAL WATER STORAGE TANK | 1 | 360.75 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 360.75 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 46136 | 2026-04-27 | 18 | 0-4008 | SLING PROTECTOR 4INX12IN | 4 | 666 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 666 | 0
ttJTrans | 0-4008 | OC | MA1011474 | OC | MA1011474 | 46136 | 2026-04-27 | 31 | 0-4008 | SHOVEL ROUND PT 49" WOOD HDL | 2 | 32.43 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 32.43 | 0
ttJTrans | 0-4008 | OC | MA1011496 | OC | MA1011496 | 46139 | 2026-04-27 | 1 | 0-4008 | Gonex Snake Gaiters, Waterproof Snake Guards, | 15 | 532.63 | PO:COMMIT | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | 532.63 | 0
ttJTrans | 0-4008 | OC | MA1011496 | OC | MA1011496 | 46139 | 2026-04-27 | 1 | 0-4008 | Gonex Snake Gaiters, Waterproof Snake Guards, | 15 | 532.63 | INVOICE:ADJ-COMMIT | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | -532.63 | 0
ttJTrans | 0-4008 | OC | MA1011496 | OC | MA1011496 | 46139 | 2026-05-07 | 1 | 0-4008 | Gonex Snake Gaiters, Waterproof Snake Guards, | 15 | 532.63 | INVOICE | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011510 | OC | MA1011510 | 46139 | 2026-05-25 | 6 | 0-4008 | FREIGHT SHIP TO: W H C Energy Services CO/ | 1 | 32.91 | PO:COMMIT | 14828 | McMASTER-CARR SUPPLY CO. | 32.91 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011510 | OC | MA1011510 | 46139 | 2026-05-25 | 4 | 0-4008 | 92620A328 Zinc Yellow-Chromate Plated Hex | 8 | 262.76 | PO:COMMIT | 14828 | McMASTER-CARR SUPPLY CO. | 262.76 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011510 | OC | MA1011510 | 46139 | 2026-05-25 | 3 | 0-4008 | 94895A038 SAE Grade 8 High-Strength Steel | 1 | 26.01 | PO:COMMIT | 14828 | McMASTER-CARR SUPPLY CO. | 26.01 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011510 | OC | MA1011510 | 46139 | 2026-05-25 | 5 | 0-4008 | 94895A859 SAE Grade 8 High-Strength Steel | 2 | 55.37 | PO:COMMIT | 14828 | McMASTER-CARR SUPPLY CO. | 55.37 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011510 | OC | MA1011510 | 46139 | 2026-05-25 | 1 | 0-4008 | 91257A983 Zinc Yellow-Chromate Plated Hex | 5 | 111.44 | PO:COMMIT | 14828 | McMASTER-CARR SUPPLY CO. | 111.44 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011510 | OC | MA1011510 | 46139 | 2026-05-25 | 2 | 0-4008 | 91257A967 Zinc Yellow-Chromate Plated Hex | 5 | 79.64 | PO:COMMIT | 14828 | McMASTER-CARR SUPPLY CO. | 79.64 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011522 | OC | MA1011522 | 46140 | 2026-04-28 | 1 | 0-4008 | Mosquito spray | 24 | 292.77 | INVOICE:ADJ-COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | -292.77 | 0
ttJTrans | 0-4008 | OC | MA1011522 | OC | MA1011522 | 46140 | 2026-04-28 | 1 | 0-4008 | Mosquito spray | 24 | 292.77 | PO:COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 292.77 | 0
ttJTrans | 0-4008 | OC | MA1011522 | OC | MA1011522 | 46140 | 2026-05-07 | 1 | 0-4008 | Mosquito spray | 24 | 292.77 | INVOICE | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011569 | OC | MA1011569 | 46141 | 2026-04-29 | 1 | 0-4008 | 48'' Rollups Non Reflective | 6 | 456.21 | PO:COMMIT | 12177 | TRAFFIC CONTROL PRODUCTS OF LOUISIANA CO. INC. | 0 | 0 | 456.21 | 0
ttJTrans | 0-4008 | OC | MA1011569 | OC | MA1011569 | 46141 | 2026-04-29 | 2 | 0-4008 | 48'' Rollups Non Reflective Trucks | 6 | 456.21 | PO:COMMIT | 12177 | TRAFFIC CONTROL PRODUCTS OF LOUISIANA CO. INC. | 0 | 0 | 456.21 | 0
ttJTrans | 0-4008 | OC | MA1011569 | OC | MA1011569 | 46141 | 2026-04-29 | 3 | 0-4008 | 48'' Rollups Non Reflective Be | 6 | 456.21 | PO:COMMIT | 12177 | TRAFFIC CONTROL PRODUCTS OF LOUISIANA CO. INC. | 0 | 0 | 456.21 | 0
ttJTrans | 0-4008 | OC | MA1011569 | OC | MA1011569 | 46141 | 2026-04-29 | 4 | 0-4008 | Shipping: 520 SLake Ct Dr Lake | 1 | 166.5 | PO:COMMIT | 12177 | TRAFFIC CONTROL PRODUCTS OF LOUISIANA CO. INC. | 0 | 0 | 166.5 | 0
ttJTrans | 0-4008 | OC | MA1011594 | OC | MA1011594 | 46142 | 2026-05-01 | 1 | 0-4008 | HAUL OF 1 LOAD OF DIGGING MATS FROM MIDLAND | 1 | 1998 | PO:COMMIT | 12843 | JONES TRANSPORT, LLC | 0 | 0 | 1998 | 0
ttJTrans | 0-4008 | OC | MA1011594 | OC | MA1011594 | 2026-04-30 | 2026-05-01 | 1 | 0-4008 | HAUL OF 1 LOAD OF DIGGING MATS FROM MIDLAND | 1 | 1998 | INVOICE:ADJ-COMMIT | 12843 | JONES TRANSPORT, LLC | 0 | 0 | -1998 | 0
ttJTrans | 0-4008 | OC | MA1011594 | OC | MA1011594 | 2026-04-30 | 2026-05-14 | 1 | 0-4008 | HAUL OF 1 LOAD OF DIGGING MATS FROM MIDLAND | 1 | 1998 | INVOICE | 12843 | JONES TRANSPORT, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011641 | OC | MA1011641 | 2026-05-04 | 2026-05-12 | 1 | 0-4008 | Power Cable for Topcon GPS Power Stick | 1 | 33.29 | INVOICE | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011641 | OC | MA1011641 | 2026-05-04 | 2026-05-09 | 1 | 0-4008 | Power Cable for Topcon GPS Power Stick | 1 | 33.29 | PO:COMMIT | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | 33.29 | 0
ttJTrans | 0-4008 | OC | MA1011641 | OC | MA1011641 | 2026-05-04 | 2026-05-09 | 1 | 0-4008 | Power Cable for Topcon GPS Power Stick | 1 | 33.29 | INVOICE:ADJ-COMMIT | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | -33.29 | 0
ttJTrans | 0-4008 | OC | MA1011641 | OC | MA1011641 | 2026-05-04 | 2026-05-09 | 2 | 0-4008 | 10000mAh External RTK Battery Bar 12V 5-Pin | 1 | 158.72 | PO:COMMIT | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | 158.72 | 0
ttJTrans | 0-4008 | OC | MA1011644 | OC | MA1011644 | 2026-05-04 | 2026-05-05 | 5 | 0-4008 | 4' Light bulbs | 1 | 11.63 | PO:COMMIT | 12808 | HOME DEPOT CREDIT SERVICES | 11.63 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011644 | OC | MA1011644 | 2026-05-04 | 2026-05-05 | 2 | 0-4008 | Power inlet box | 2 | 144.08 | PO:COMMIT | 12808 | HOME DEPOT CREDIT SERVICES | 144.08 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011644 | OC | MA1011644 | 2026-05-04 | 2026-05-05 | 2 | 0-4008 | Power inlet box | 2 | 144.08 | INVOICE:ADJ-ACCRUAL | 12808 | HOME DEPOT CREDIT SERVICES | -144.08 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011644 | OC | MA1011644 | 2026-05-04 | 2026-05-05 | 4 | 0-4008 | 30 Amp 125/250 Plugs | 2 | 55.23 | INVOICE:ADJ-ACCRUAL | 12808 | HOME DEPOT CREDIT SERVICES | -55.23 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011644 | OC | MA1011644 | 2026-05-04 | 2026-05-05 | 5 | 0-4008 | 4' Light bulbs | 1 | 11.63 | INVOICE:ADJ-ACCRUAL | 12808 | HOME DEPOT CREDIT SERVICES | -11.63 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011644 | OC | MA1011644 | 2026-05-04 | 2026-05-05 | 1 | 0-4008 | 4' Lights tool fan | 5 | 221.83 | INVOICE:ADJ-ACCRUAL | 12808 | HOME DEPOT CREDIT SERVICES | -221.83 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011644 | OC | MA1011644 | 2026-05-04 | 2026-05-05 | 1 | 0-4008 | 4' Lights tool fan | 5 | 221.83 | PO:COMMIT | 12808 | HOME DEPOT CREDIT SERVICES | 221.83 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011644 | OC | MA1011644 | 2026-05-04 | 2026-05-05 | 3 | 0-4008 | Magnet swing hook | 2 | 40.8 | PO:COMMIT | 12808 | HOME DEPOT CREDIT SERVICES | 40.8 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011644 | OC | MA1011644 | 2026-05-04 | 2026-05-05 | 4 | 0-4008 | 30 Amp 125/250 Plugs | 2 | 55.23 | PO:COMMIT | 12808 | HOME DEPOT CREDIT SERVICES | 55.23 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011644 | OC | MA1011644 | 2026-05-04 | 2026-05-05 | 3 | 0-4008 | Magnet swing hook | 2 | 40.8 | INVOICE:ADJ-ACCRUAL | 12808 | HOME DEPOT CREDIT SERVICES | -40.8 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011644 | OC | MA1011644 | 2026-05-04 | 2026-05-12 | 2 | 0-4008 | Power inlet box | 2 | 144.08 | INVOICE | 12808 | HOME DEPOT CREDIT SERVICES | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011644 | OC | MA1011644 | 2026-05-04 | 2026-05-12 | 4 | 0-4008 | 30 Amp 125/250 Plugs | 2 | 55.23 | INVOICE | 12808 | HOME DEPOT CREDIT SERVICES | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011644 | OC | MA1011644 | 2026-05-04 | 2026-05-12 | 5 | 0-4008 | 4' Light bulbs | 1 | 11.63 | INVOICE | 12808 | HOME DEPOT CREDIT SERVICES | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011644 | OC | MA1011644 | 2026-05-04 | 2026-05-12 | 1 | 0-4008 | 4' Lights tool fan | 5 | 221.83 | INVOICE | 12808 | HOME DEPOT CREDIT SERVICES | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011644 | OC | MA1011644 | 2026-05-04 | 2026-05-12 | 3 | 0-4008 | Magnet swing hook | 2 | 40.8 | INVOICE | 12808 | HOME DEPOT CREDIT SERVICES | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011682 | OC | MA1011682 | 2026-05-05 | 2026-05-19 | 1 | 0-4008 | 55-GAL Steel drums | 3 | 354.61 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011682 | OC | MA1011682 | 2026-05-05 | 2026-05-19 | 2 | 0-4008 | T-Post Caps | 19 | 437.83 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011682 | OC | MA1011682 | 2026-05-05 | 2026-05-19 | 3 | 0-4008 | Freight | 2 | 222 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011682 | OC | MA1011682 | 2026-05-05 | 2026-05-09 | 5 | 0-4008 | Poly rope | 8 | 150.96 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -150.96 | 0
ttJTrans | 0-4008 | OC | MA1011682 | OC | MA1011682 | 2026-05-05 | 2026-05-09 | 1 | 0-4008 | 55-GAL Steel drums | 3 | 354.61 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 354.61 | 0
ttJTrans | 0-4008 | OC | MA1011682 | OC | MA1011682 | 2026-05-05 | 2026-05-09 | 1 | 0-4008 | 55-GAL Steel drums | 3 | 354.61 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -354.61 | 0
ttJTrans | 0-4008 | OC | MA1011682 | OC | MA1011682 | 2026-05-05 | 2026-05-09 | 4 | 0-4008 | Safety fence | 20 | 454.66 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 454.66 | 0
ttJTrans | 0-4008 | OC | MA1011682 | OC | MA1011682 | 2026-05-05 | 2026-05-09 | 2 | 0-4008 | T-Post Caps | 19 | 437.83 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -437.83 | 0
ttJTrans | 0-4008 | OC | MA1011682 | OC | MA1011682 | 2026-05-05 | 2026-05-09 | 2 | 0-4008 | T-Post Caps | 19 | 437.83 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 437.83 | 0
ttJTrans | 0-4008 | OC | MA1011682 | OC | MA1011682 | 2026-05-05 | 2026-05-09 | 5 | 0-4008 | Poly rope | 8 | 150.96 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 150.96 | 0
ttJTrans | 0-4008 | OC | MA1011682 | OC | MA1011682 | 2026-05-05 | 2026-05-09 | 3 | 0-4008 | Freight | 2 | 222 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 222 | 0
ttJTrans | 0-4008 | OC | MA1011682 | OC | MA1011682 | 2026-05-05 | 2026-05-09 | 3 | 0-4008 | Freight | 2 | 222 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -111 | 0
ttJTrans | 0-4008 | OC | MA1011682 | OC | MA1011682 | 2026-05-05 | 2026-05-09 | 4 | 0-4008 | Safety fence | 20 | 454.66 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -454.66 | 0
ttJTrans | 0-4008 | OC | MA1011759 | OC | MA1011759 | 2026-05-07 | 2026-05-13 | 2 | 0-4008 | Element Fuel | 1 | 122.41 | INVOICE:ADJ-ACCRUAL | 12806 | HOLT CAT | -122.41 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011759 | OC | MA1011759 | 2026-05-07 | 2026-05-13 | 1 | 0-4008 | Element Fuel | 1 | 53.46 | INVOICE:ADJ-ACCRUAL | 12806 | HOLT CAT | -53.46 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011759 | OC | MA1011759 | 2026-05-07 | 2026-05-13 | 2 | 0-4008 | Element Fuel | 1 | 122.41 | PO:COMMIT | 12806 | HOLT CAT | 122.41 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011759 | OC | MA1011759 | 2026-05-07 | 2026-05-13 | 1 | 0-4008 | Element Fuel | 1 | 53.46 | PO:COMMIT | 12806 | HOLT CAT | 53.46 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011759 | OC | MA1011759 | 2026-05-07 | 2026-05-19 | 1 | 0-4008 | Element Fuel | 1 | 53.46 | INVOICE | 12806 | HOLT CAT | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011759 | OC | MA1011759 | 2026-05-07 | 2026-05-19 | 2 | 0-4008 | Element Fuel | 1 | 122.41 | INVOICE | 12806 | HOLT CAT | 0 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011796 | OC | MA1011796 | 2026-05-08 | 2026-05-09 | 1 | 0-4008 | SATEL COMPACT PROOF, 1W, IP67 CLASSIFIED | 1 | 2525.25 | PO:COMMIT | 16688 | RDO EQUIPMENT CO. | 2525.25 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011796 | OC | MA1011796 | 2026-05-08 | 2026-05-09 | 2 | 0-4008 | SATEL USA KIT,SATEL 1W EXT RADIO W/CABLE | 1 | 3298.92 | PO:COMMIT | 16688 | RDO EQUIPMENT CO. | 3298.92 | 0 | 0 | 0
ttJTrans | 0-4008 | OC | MA1011831 | OC | MA1011831 | 2026-05-11 | 2026-05-21 | 4 | 0-4008 | CONTAINMENT BERM 21'X8'X1' | 1 | 621.6 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 621.6 | 0
ttJTrans | 0-4008 | OC | MA1011831 | OC | MA1011831 | 2026-05-11 | 2026-05-21 | 9 | 0-4008 | PADLOCK MASTER COMBO 2/14INX1I | 10 | 288.6 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 288.6 | 0
ttJTrans | 0-4008 | OC | MA1011831 | OC | MA1011831 | 2026-05-11 | 2026-05-21 | 6 | 0-4008 | BILLED FREIGHT | 1 | 166.5 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -166.5 | 0
ttJTrans | 0-4008 | OC | MA1011831 | OC | MA1011831 | 2026-05-11 | 2026-05-21 | 5 | 0-4008 | TIMBER LANDSCAPE 8' | 300 | 2074.59 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -2074.59 | 0
ttJTrans | 0-4008 | OC | MA1011831 | OC | MA1011831 | 2026-05-11 | 2026-05-21 | 9 | 0-4008 | PADLOCK MASTER COMBO 2/14INX1I | 10 | 288.6 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -288.6 | 0
ttJTrans | 0-4008 | OC | MA1011831 | OC | MA1011831 | 2026-05-11 | 2026-05-21 | 8 | 0-4008 | STAKE PINE 2X2X48 20/BDL | 135 | 5619.38 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -5619.38 | 0
ttJTrans | 0-4008 | OC | MA1011831 | OC | MA1011831 | 46153 | 2026-05-21 | 4 | 0-4008 | CONTAINMENT BERM 21'X8'X1' | 1 | 621.6 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -621.6 | 0
ttJTrans | 0-4008 | OC | MA1011831 | OC | MA1011831 | 46153 | 2026-05-21 | 3 | 0-4008 | CONTAINMENT BERM 8'X14'X1' | 1 | 555 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -555 | 0
ttJTrans | 0-4008 | OC | MA1011831 | OC | MA1011831 | 46153 | 2026-05-21 | 3 | 0-4008 | CONTAINMENT BERM 8'X14'X1' | 1 | 555 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 555 | 0
ttJTrans | 0-4008 | OC | MA1011831 | OC | MA1011831 | 46153 | 2026-05-21 | 8 | 0-4008 | STAKE PINE 2X2X48 20/BDL | 135 | 5619.38 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 5619.38 | 0
ttJTrans | 0-4008 | OC | MA1011831 | OC | MA1011831 | 46153 | 2026-05-21 | 5 | 0-4008 | TIMBER LANDSCAPE 8' | 300 | 2074.59 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 2074.59 | 0
ttJTrans | 0-4008 | OC | MA1011831 | OC | MA1011831 | 2026-05-11 | 2026-05-21 | 6 | 0-4008 | BILLED FREIGHT | 1 | 166.5 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 166.5 | 0
ttJTrans | 0-4008 | OC | MA1011831 | OC | MA1011831 | 2026-05-11 | 2026-05-21 | 7 | 0-4008 | #3 PLACKARDS | 4 | 20.56 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 20.56 | 0
ttJTrans | 0-4008 | OC | MA1011831 | OC | MA1011831 | 2026-05-11 | 2026-05-21 | 7 | 0-4008 | #3 PLACKARDS | 4 | 20.56 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -20.56 | 0
ttJTrans | 0-4008 | OC | MA1011831 | OC | MA1011831 | 2026-05-11 | 2026-05-21 | 1 | 0-4008 | TUB MIXING 36INX24INX8IN ALL P | 15 | 296.2 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 296.2 | 0
ttJTrans | 0-4008 | OC | MA1011831 | OC | MA1011831 | 2026-05-11 | 2026-05-21 | 2 | 0-4008 | WATER BOTTLED 24/PACK 84PK/PLT | 168 | 688.11 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 688.11 | 0
ttJTrans | 0-4008 | OC | MA1011831 | OC | MA1011831 | 2026-05-11 | 2026-05-21 | 1 | 0-4008 | TUB MIXING 36INX24INX8IN ALL P | 15 | 296.2 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -296.2 | 0
ttJTrans | 0-4008 | OC | MA1011831 | OC | MA1011831 | 2026-05-11 | 2026-05-21 | 2 | 0-4008 | WATER BOTTLED 24/PACK 84PK/PLT | 168 | 688.11 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -688.11 | 0
ttJTrans | 0-4008 | OC | MA1011992 | OC | MA1011992 | 2026-05-18 | 2026-05-20 | 2 | 0-4008 | ESTIMATED FREIGHT | 1 | 166.5 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 166.5 | 0
ttJTrans | 0-4008 | OC | MA1011992 | OC | MA1011992 | 2026-05-18 | 2026-05-20 | 1 | 0-4008 | GLASSES SAFETY CLEAR RAD-SEQUE | 72 | 143.06 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 143.06 | 0
ttJTrans | 0-4008 | OC | MA1012020 | OC | MA1012020 | 2026-05-19 | 2026-05-20 | 1 | 0-4008 | DELL 27" MONITORS | 8 | 1933 | PO:COMMIT | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | 1933 | 0
ttJTrans | 0-4008 | OC | MA1012020 | OC | MA1012020 | 2026-05-19 | 2026-05-20 | 2 | 0-4008 | DELL SMARTDOCK SD25 | 4 | 772.56 | PO:COMMIT | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | 772.56 | 0
ttJTrans | 0-4008 | OC | MA1012064 | OC | MA1012064 | 2026-05-20 | 2026-05-21 | 1 | 0-4008 | Mount mag tripler10 | 1 | 384.45 | PO:COMMIT | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | 384.45 | 0
ttJTrans | 0-4008 | OC | MA1012066 | OC | MA1012066 | 2026-05-20 | 2026-05-21 | 2 | 0-4008 | Tarp 12 x 20 | 1 | 77.69 | PO:COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 77.69 | 0
ttJTrans | 0-4008 | OC | MA1012066 | OC | MA1012066 | 2026-05-20 | 2026-05-21 | 3 | 0-4008 | 8 X 10 Treated lumber | 1 | 61.04 | PO:COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 61.04 | 0
ttJTrans | 0-4008 | OC | MA1012066 | OC | MA1012066 | 2026-05-20 | 2026-05-21 | 1 | 0-4008 | Tarp | 1 | 49.94 | PO:COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 49.94 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-01-22 |  | 0-4008 | DUSTIN HOPKINS EXPENSE REPORT | 0 | 0 |  | 21284 | HOPKINS, DUSTIN W. | 0 | 59.5 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-02-25 |  | 0-4008 | CHANCELLOR FRANKSON EXPENSE REPORT | 0 | 0 |  | 21212 | FRANKSON, CHANCELLOR R. | 0 | 171.32 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-02-25 |  | 0-4008 | SAFETY GLASSES/ SIDESHIELD VISION AID/ GLOVES/ CLIP GLOVE/ FREIGHT | 0 | 0 |  | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 5876.91 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-02-25 |  | 0-4008 | SAFETY GLASSES/ SIDESHIELD VISION AID/ GLOVES/ CLIP GLOVE/ FREIGHT | 0 | 0 |  | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 193.81 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-03-25 |  | 0-4008 | 48'' Rollups Non Reflective Construction Ahead | 0 | 0 |  | 12177 | TRAFFIC CONTROL PRODUCTS OF LOUISIANA CO. INC. | 0 | 2364.45 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-03-31 |  | 0-4008 | GLOVES/ FACESHIELD/ BRACKET/COVERALLS/ AIRHORN/ SIGNS/ EARPLUGS/ TRAFFIC CONE | 0 | 0 |  | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 2013.64 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-04-01 |  | 0-4008 | NICK SALINAS EXPENSE REPORT | 0 | 0 |  | 13193 | SALINAS, NICHOLAS A | 0 | 187.48 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-04-01 |  | 0-4008 | 18 8X4X18 LEASE 18 DIGGING MATS FOR 14 DAYS | 0 | 0 |  | 20401 | RDC HOLDINGS LLC | 0 | 2711.45 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-04-01 |  | 0-4008 | Fencing Supplies T-post Wire Fencing Approved by Eugene | 0 | 0 |  | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 82.23 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-04-01 |  | 0-4008 | Fencing Supplies T-post Wire Fencing Approved by Eugene | 0 | 0 |  | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 46.99 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-04-27 |  | 0-4008 | BOTTLED WATER S626048 | 0 | 0 |  | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 422.13 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-04-27 |  | 0-4008 | GOGGLES CHEMICAL CLEAR/ RESPIRATORS/ FILTERS/ EARMUFFSS626147 | 0 | 0 |  | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 1084.2 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-04-08 |  | 0-4008 | MARK BROUSSARD EXPENSE REPORTS | 0 | 0 |  | 12450 | BROUSSARD, MARK A | 0 | 5069.66 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-04-21 |  | 0-4008 | COMDATA 4/06/26 (EU) AUTOZONE #1358 3/29/26 | 0 | 0 |  | 2285 |  | 0 | 172.83 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-04-21 |  | 0-4008 | COMDATA 4/06/26 (EU) TRACTOR SUPPLY #2291 3/30/26 | 0 | 0 |  | 2285 |  | 0 | 61.65 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-04-21 |  | 0-4008 | COMDATA 4/06/26 (SW) NTE 5677 4/02/26 | 0 | 0 |  | 2285 |  | 0 | 76.81 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-04-21 |  | 0-4008 | COMDATA 4/06/26 (EU) AUTOZONE #1358 3/29/26 | 0 | 0 |  | 2285 |  | 0 | -82.99 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-04-14 |  | 0-4008 | COMDATA 3/23/26 (AS) TRACTOR SUPPLY #2291 3/20/26 | 0 | 0 |  | 2282 |  | 0 | 21.64 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-04-14 |  | 0-4008 | COMDATA 3/23/26 (AS) TRACTOR SUPPLY #2291 3/18/26 | 0 | 0 |  | 2282 |  | 0 | 81.12 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-04-15 |  | 0-4008 | COUPLER PLUG SET / AIR PLUG / BUSHING HEX GALV / BUSHING HEX / RED COUPLING | 0 | 0 |  | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 52.52 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-04-15 |  | 0-4008 | ROOF TOP STOBE BEACON LIGHT BAR | 0 | 0 |  | 20395 | AMAZON.COM SERVICES LLC | 0 | 584.1 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-04-17 |  | 0-4008 | 25-4005 MARCH USE TAX ADJ | 0 | 0 |  |  |  | 0 | 18.87 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-04-23 |  | 0-4008 | SHADE HARDHAT W REFL TAPE | 0 | 0 |  | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 797.4 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-04-23 |  | 0-4008 | REPAIR KIT | 0 | 0 |  | 12747 | GRAINGER, INC. | 0 | 242.53 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-04-22 |  | 0-4008 | CHANCELLOR FRANKSON EXPENSE REPORT | 0 | 0 |  | 21212 | FRANKSON, CHANCELLOR R. | 0 | 129.89 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-04-28 |  | 0-4008 | POPLAR LATH STAKE/ TAPE/ BAG/ RED PAINT/ PINK PAINT/ REBAR STAKE | 0 | 0 |  | 20746 | ALLTERRA CENTRAL, INC | 0 | 3089.3 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-04-29 |  | 0-4008 | ELECT TAPE/ BALL MARKER LOCATOR/ TENT CANOPY/ FOLDING TABLE/ SAW HORSES/ FRTS625873 | 0 | 0 |  | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 4479.6 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-04-29 |  | 0-4008 | STINGER NAIL GUN/ 1IN NAIL PAC W/CAPS / FRT | 0 | 0 |  | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 11301.32 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-04-29 |  | 0-4008 | ABSORBENT PAD OIL ONLY/ STEEL DRUM 55GAL S626349 | 0 | 0 |  | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 635.74 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-04-29 |  | 0-4008 | SPEED LIMIT SIGN/ FRT. S626453 | 0 | 0 |  | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 793.91 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-04-29 |  | 0-4008 | PAINT/ 2X20 PVC SCH80 / WATTLE STRAW/ DEF/ RAGS/ GLASS CLNR/ VISQUEEN | 0 | 0 |  | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 7811.34 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-04-29 |  | 0-4008 | Delineator Post with Base 45" Lime | 0 | 0 |  | 13343 | ULINE INC | 0 | 1285.99 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-04-30 |  | 0-4008 | STOCK CASE FOR IPAD / APPLE IPAD | 0 | 0 |  | 20395 | AMAZON.COM SERVICES LLC | 0 | 3131.82 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-04-30 |  | 0-4008 | 3 RING BINDER / INK | 0 | 0 |  | 20395 | AMAZON.COM SERVICES LLC | 0 | 252.82 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-04-30 |  | 0-4008 | SAFE RETRACTABLE BOX CUTTING KNIFE | 0 | 0 |  | 20395 | AMAZON.COM SERVICES LLC | 0 | 209.6 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-05-14 |  | 0-4008 | HAULING OF 1 LOAD OF DIGGING MATS FROM MIDLAND YARD TO WHARTON JOBSITE | 0 | 0 |  | 12843 | JONES TRANSPORT, LLC | 0 | 1800 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-05-10 |  | 0-4008 | FUEL | 0 | 0 |  | 12806 | HOLT CAT | 0 | 171.51 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-05-10 |  | 0-4008 | 55GAL STEEL DRUM/ CAP T-POST SLIP ON | 0 | 0 |  | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 881.04 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-05-05 |  | 0-4008 | SITL FENCE ERIOUSION CONTROL SUPPLIES S624996 LUKE | 0 | 0 |  | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 12484.86 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-05-05 |  | 0-4008 | SNAKE GAITERS | 0 | 0 |  | 20395 | AMAZON.COM SERVICES LLC | 0 | 519.45 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-05-05 |  | 0-4008 | EXTERNAL HARD DRIVE / MEMORY CARD | 0 | 0 |  | 20395 | AMAZON.COM SERVICES LLC | 0 | 536.15 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-05-05 |  | 0-4008 | BITTING INSECT REPELENT | 0 | 0 |  | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 285.52 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-05-05 |  | 0-4008 | WHC HATS | 0 | 0 |  | 12311 | ACTION SPECIALTIES, LLC | 0 | 5072.58 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-05-05 |  | 0-4008 | WHC HATS | 0 | 0 |  | 12311 | ACTION SPECIALTIES, LLC | 0 | 247.72 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-05-05 |  | 0-4008 | SCREW PIN ANCHOR SHACKLE/ PORTABLE BAND SAW BLADE/ DUCT TAPE/ ELECT TAPE/ TACKY RED GREASE/ RAGS/ GLASS CLNR/ BROOM/ CALBLE TIES/ PAINT MARKER/ TAPE MEASURE | 0 | 0 |  | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 1891.14 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-05-07 |  | 0-4008 | 25-4005 SIGNS | 0 | 0 |  | 21346 | LOWRY'S SIGN SHOP | 0 | 2844.9 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-05-07 |  | 0-4008 | 25-4005 SIGNS | 0 | 0 |  | 21346 | LOWRY'S SIGN SHOP | 0 | 65 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-05-11 |  | 0-4008 | LUMEN LED SHOPLIGHT / MAGNET SWING HOOK / CONNECTOR | 0 | 0 |  | 12808 | HOME DEPOT CREDIT SERVICES | 0 | 461.85 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-05-11 |  | 0-4008 | POWER CABLE | 0 | 0 |  | 20395 | AMAZON.COM SERVICES LLC | 0 | 32.46 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-05-14 |  | 0-4008 | KELLUM GRIPS | 0 | 0 |  | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 17097.99 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-05-10 |  | 0-4008 | GAS ALERT MAX XT/ CHARGER/ MONITOR PROBE/ DEMAND FLOW REGULATOR | 0 | 0 |  | 12287 | 24 HOUR SAFETY LLC | 0 | 2834.42 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-05-10 |  | 0-4008 | PARTIAL CREDIT FOR INVOICE 9872717419 FOR A REPAIR KIT | 0 | 0 |  | 12747 | GRAINGER, INC. | 0 | -227.7 | 0 | 0
ttJTrans | 0-4008 | OC |  | OC |  |  | 2026-05-17 |  | 0-4008 | KELLUM GRIPS/ 50FT DOUBLE BRAID ROPE | 0 | 0 |  | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 6357.53 | 0 | 0
ttJTrans | 0-4010 | OC | MA1010837 | OC | MA1010837 | 2026-04-28 | 2026-05-01 | 11 | 0-4010 | GREASE TUBE HIGH TEMP RED 14OZ | 5 | 342.88 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 342.88 | 0
ttJTrans | 0-4010 | OC | MA1010837 | OC | MA1010837 | 2026-04-28 | 2026-05-01 | 19 | 0-4010 | FUEL PREMIXED 50:1 1 GAL | 5 | 124.88 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 124.88 | 0
ttJTrans | 0-4010 | OC | MA1010837 | OC | MA1010837 | 2026-04-28 | 2026-05-01 | 20 | 0-4010 | BAR OIL | 2 | 44.4 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 44.4 | 0
ttJTrans | 0-4010 | OC | MA1010837 | OC | MA1010837 | 2026-04-28 | 2026-05-01 | 11 | 0-4010 | GREASE TUBE HIGH TEMP RED 14OZ | 5 | 342.88 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -342.88 | 0
ttJTrans | 0-4010 | OC | MA1010837 | OC | MA1010837 | 2026-04-28 | 2026-05-01 | 19 | 0-4010 | FUEL PREMIXED 50:1 1 GAL | 5 | 124.88 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -124.88 | 0
ttJTrans | 0-4010 | OC | MA1010837 | OC | MA1010837 | 2026-04-28 | 2026-05-01 | 20 | 0-4010 | BAR OIL | 2 | 44.4 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -44.4 | 0
ttJTrans | 0-4010 | OC | MA1010837 | OC | MA1010837 | 2026-04-28 | 2026-05-07 | 19 | 0-4010 | FUEL PREMIXED 50:1 1 GAL | 5 | 124.88 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4010 | OC | MA1010837 | OC | MA1010837 | 2026-04-28 | 2026-05-07 | 11 | 0-4010 | GREASE TUBE HIGH TEMP RED 14OZ | 5 | 342.88 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4010 | OC | MA1010837 | OC | MA1010837 | 2026-04-28 | 2026-05-07 | 20 | 0-4010 | BAR OIL | 2 | 44.4 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4010 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-05-07 | 15 | 0-4010 | EXTRA TACKY RED GREASE | 4 | 332.16 | INVOICE | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4010 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-04-24 | 15 | 0-4010 | EXTRA TACKY RED GREASE | 4 | 332.16 | PO:COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | 332.16 | 0
ttJTrans | 0-4010 | OC | MA1011403 | OC | MA1011403 | 2026-04-22 | 2026-04-24 | 15 | 0-4010 | EXTRA TACKY RED GREASE | 4 | 332.16 | INVOICE:ADJ-COMMIT | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 0 | -332.16 | 0
ttJTrans | 0-4010 | OC | MA1012139 | OC | MA1012139 | 2026-05-26 | 2026-05-28 | 1 | 0-4010 | Bulk Fuel | 1 | 333000 | INVOICE:ADJ-ACCRUAL | 16625 | BEARD OIL DISTRIBUTING | -19390.56 | 0 | 0 | 0
ttJTrans | 0-4010 | OC | MA1012139 | OC | MA1012139 | 2026-05-26 | 2026-05-28 | 1 | 0-4010 | Bulk Fuel | 1 | 333000 | INVOICE:ADJ-ACCRUAL | 16625 | BEARD OIL DISTRIBUTING | -21199.79 | 0 | 0 | 0
ttJTrans | 0-4010 | OC | MA1012139 | OC | MA1012139 | 2026-05-26 | 2026-05-28 | 1 | 0-4010 | Bulk Fuel | 1 | 333000 | INVOICE:ADJ-ACCRUAL | 16625 | BEARD OIL DISTRIBUTING | -21645.16 | 0 | 0 | 0
ttJTrans | 0-4010 | OC | MA1012139 | OC | MA1012139 | 2026-05-26 | 2026-05-28 | 1 | 0-4010 | Bulk Fuel | 1 | 333000 | INVOICE:ADJ-ACCRUAL | 16625 | BEARD OIL DISTRIBUTING | -1327.11 | 0 | 0 | 0
ttJTrans | 0-4010 | OC |  | OC |  |  | 2025-12-09 |  | 0-4010 | OCI SUNROPER LLC | 0 | 0 |  | 2197 |  | 0 | 557.07 | 0 | 0
ttJTrans | 0-4010 | OC |  | OC |  |  | 2026-01-10 |  | 0-4010 | OCI SUNROPER LLC | 0 | 0 |  | 2218 |  | 0 | 485.8 | 0 | 0
ttJTrans | 0-4010 | OC |  | OC |  |  | 2026-02-10 |  | 0-4010 | OCI SUNROPER LLC | 0 | 0 |  | 2233 |  | 0 | 149.84 | 0 | 0
ttJTrans | 0-4010 | OC |  | OC |  |  | 2026-03-13 |  | 0-4010 | OCI SUNROPER LLC | 0 | 0 |  | 2251 |  | 0 | 1230.72 | 0 | 0
ttJTrans | 0-4010 | OC |  | OC |  |  | 2026-04-13 |  | 0-4010 | OCI SUNROPER LLC | 0 | 0 |  | 2281 |  | 0 | 10471.97 | 0 | 0
ttJTrans | 0-4010 | OC |  | OC |  |  | 2026-05-11 |  | 0-4010 | OCI SUNROPER LLC | 0 | 0 |  | 2301 |  | 0 | 29204.33 | 0 | 0
ttJTrans | 0-4010 | OC |  | OC |  |  | 2026-05-05 |  | 0-4010 | SITL FENCE ERIOUSION CONTROL SUPPLIES S624996 LUKE | 0 | 0 |  | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 499.47 | 0 | 0
ttJTrans | 0-4010 | OC |  | OC |  |  | 2026-05-05 |  | 0-4010 | SCREW PIN ANCHOR SHACKLE/ PORTABLE BAND SAW BLADE/ DUCT TAPE/ ELECT TAPE/ TACKY RED GREASE/ RAGS/ GLASS CLNR/ BROOM/ CALBLE TIES/ PAINT MARKER/ TAPE MEASURE | 0 | 0 |  | 19480 | TOTAL TOOL SUPPLY LLC | 0 | 326.17 | 0 | 0
ttJTrans | 0-4004-01 | OC |  | OC |  |  | 2026-03-20 |  | 0-4004-01 | TEXAS COMPTROLLER OF PUBLIC FEBRUARY 2026 | 0 | 0 |  | 2253 |  | 0 | 1010151.51 | 0 | 0
ttJTrans | 0-4004-01 | OC |  | OC |  |  | 2026-05-18 |  | 0-4004-01 | TEXAS COMPTROLLER USE TAX APRIL 2026 | 0 | 0 |  | 2313 |  | 0 | 25350.91 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR260 2005 UTILITY BRAND TOOL VAN 2005 UTILITY BRAND TOOL VAN | 0 | 0 |  | TR260 |  | 0 | 75 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | RT1479 2025 FORD F150 CREW CAB 4X4 2025 FORD F150 CREW CAB 4X4 | 0 | 0 |  | RT1479 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR280 20' BIG TEX PI-20 20' BIG TEX PI-20 | 0 | 0 |  | TR280 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | WHV001 2025 PETERBILT 589 SLEEPER CAB 2025 PETERBILT 589 SLEEPER CAB | 0 | 0 |  | WHV001 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR473 LANDOLL 53FT LOWBOY LANDOLL 53FT LOWBOY | 0 | 0 |  | TR473 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR461 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR461 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR461 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR461 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR461 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR461 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR462 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR462 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR462 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR462 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR462 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR462 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR463 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR463 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR463 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR463 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR463 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR463 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR464 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR464 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR464 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR464 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR464 40' HIGH CUBE CONTAINERS 40' HIGH CUBE CONTAINERS | 0 | 0 |  | TR464 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR456 40' DOUBLE DOOR CONTAINER 40' DOUBLE DOOR CONTAINER | 0 | 0 |  | TR456 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR456 40' DOUBLE DOOR CONTAINER 40' DOUBLE DOOR CONTAINER | 0 | 0 |  | TR456 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | TR456 40' DOUBLE DOOR CONTAINER 40' DOUBLE DOOR CONTAINER | 0 | 0 |  | TR456 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4013-02 | WTL002 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY 2025 55 TON GOOSENECK EAGER BEAVER LOWBOY | 0 | 0 |  | WTL002 |  | 0 | 55 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | BH235 2023 KOMATSU PC88MR-11 EXCAVATOR 2023 KOMATSU PC88MR-11 EXCAVATOR | 0 | 0 |  | BH235 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | TR154 20' PARKER TRAILER #1000277 20' PARKER TRAILER #1000277 | 0 | 0 |  | TR154 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | BH235 2023 KOMATSU PC88MR-11 EXCAVATOR 2023 KOMATSU PC88MR-11 EXCAVATOR | 0 | 0 |  | BH235 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | BH235 2023 KOMATSU PC88MR-11 EXCAVATOR 2023 KOMATSU PC88MR-11 EXCAVATOR | 0 | 0 |  | BH235 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | SSRAKE03 TITAN SSL-84 GRAPPLE RAKE TITAN SSL-84 GRAPPLE RAKE | 0 | 0 |  | SSRAKE03 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | SSRAKE03 TITAN SSL-84 GRAPPLE RAKE TITAN SSL-84 GRAPPLE RAKE | 0 | 0 |  | SSRAKE03 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4013-02 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4013-02 | SSRAKE03 TITAN SSL-84 GRAPPLE RAKE TITAN SSL-84 GRAPPLE RAKE | 0 | 0 |  | SSRAKE03 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RAT440 POLARIS RANGER 1000 CREW CAB UTV POLARIS RANGER 1000 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RAT440 POLARIS RANGER 1000 CREW CAB UTV POLARIS RANGER 1000 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RAT440 POLARIS RANGER 1000 CREW CAB UTV POLARIS RANGER 1000 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-04-26 |  | 0-4013-02 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RAT440 POLARIS RANGER 1000 CREW CAB UTV POLARIS RANGER 1000 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RAT440 POLARIS RANGER 1000 CREW CAB UTV POLARIS RANGER 1000 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RMS2388 BUSH-HACKER 15' BRUSH CUTTER BUSH-HACKER 15' BRUSH CUTTER | 0 | 0 |  | RMS2388 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-03 |  | 0-4013-02 | RMS2388 BUSH-HACKER 15' BRUSH CUTTER BUSH-HACKER 15' BRUSH CUTTER | 0 | 0 |  | RMS2388 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RAT440 CAN AM HD11 CREW CAB UTV CAN AM HD11 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RAT440 CAN AM HD11 CREW CAB UTV CAN AM HD11 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RMS2388 BUSH-HACKER 15' BRUSH CUTTER BUSH-HACKER 15' BRUSH CUTTER | 0 | 0 |  | RMS2388 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-10 |  | 0-4013-02 | RMS2388 BUSH-HACKER 15' BRUSH CUTTER BUSH-HACKER 15' BRUSH CUTTER | 0 | 0 |  | RMS2388 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RAT440 CAN AM HD11 CREW CAB UTV CAN AM HD11 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RAT440 CAN AM HD11 CREW CAB UTV CAN AM HD11 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RAT440 CAN AM HD11 CREW CAB UTV CAN AM HD11 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RMS2318 BROCE RCT350 WHEEL SWEEPER BROCE RCT350 WHEEL SWEEPER | 0 | 0 |  | RMS2318 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RMS2388 BUSH-HACKER 15' BRUSH CUTTER BUSH-HACKER 15' BRUSH CUTTER | 0 | 0 |  | RMS2388 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RMS2388 BUSH-HACKER 15' BRUSH CUTTER BUSH-HACKER 15' BRUSH CUTTER | 0 | 0 |  | RMS2388 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RMS2388 BUSH-HACKER 15' BRUSH CUTTER BUSH-HACKER 15' BRUSH CUTTER | 0 | 0 |  | RMS2388 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RLV100049 CHEVROLET 15 PASSENGER VAN CHEVROLET 15 PASSENGER VAN | 0 | 0 |  | RLV100049 |  | 0 | 109.92 | 0 | 0
ttJTrans | 0-4013-02 | ER |  | ER |  |  | 2026-05-24 |  | 0-4013-02 | RLV100049 CHEVROLET 15 PASSENGER VAN CHEVROLET 15 PASSENGER VAN | 0 | 0 |  | RLV100049 |  | 0 | 109.92 | 0 | 0
ttJTrans | 0-4013-02 | LA |  | LA |  |  | 2026-04-23 |  | 0-4013-02 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 1558.07 | 0 | 14
ttJTrans | 0-4013-02 | LA |  | LA |  |  | 2026-04-23 |  | 0-4013-02 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 2309.18 | 0 | 28
ttJTrans | 0-4013-02 | LA |  | LA |  |  | 2026-04-23 |  | 0-4013-02 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 2309.18 | 0 | 28
ttJTrans | 0-4013-02 | LA |  | LA |  |  | 2026-04-23 |  | 0-4013-02 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 2090.36 | 0 | 24
ttJTrans | 0-4013-02 | LA |  | LA |  |  | 2026-04-23 |  | 0-4013-02 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 656.07 | 0 | 10.03
ttJTrans | 0-4013-02 | LA |  | LA |  |  | 2026-04-23 |  | 0-4013-02 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 608.75 | 0 | 10.34
ttJTrans | 0-4013-02 | LA |  | LA |  |  | 2026-04-23 |  | 0-4013-02 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 608.75 | 0 | 5
ttJTrans | 0-4013-02 | LA |  | LA |  |  | 2026-04-30 |  | 0-4013-02 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 2109.11 | 0 | 30
ttJTrans | 0-4013-02 | LA |  | LA |  |  | 2026-04-30 |  | 0-4013-02 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 2210.22 | 0 | 28
ttJTrans | 0-4013-02 | LA |  | LA |  |  | 2026-04-30 |  | 0-4013-02 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 1506.63 | 0 | 17.65
ttJTrans | 0-4013-02 | LA |  | LA |  |  | 2026-04-30 |  | 0-4013-02 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 1184.22 | 0 | 6
ttJTrans | 0-4013-02 | LA |  | LA |  |  | 2026-04-30 |  | 0-4013-02 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 700 | 0 | 0
ttJTrans | 0-4013-02 | LA |  | LA |  |  | 2026-05-21 |  | 0-4013-02 | PR P0COST 000531 (PR) Summary | 0 | 0 |  |  |  | 0 | 3605.6 | 0 | 44
ttJTrans | 0-4013-02 | LA |  | LA |  |  | 2026-05-21 |  | 0-4013-02 | PR P0COST 000531 (PR) Summary | 0 | 0 |  |  |  | 0 | 3115.72 | 0 | 38
ttJTrans | 0-4013-02 | LA |  | LA |  |  | 2026-05-21 |  | 0-4013-02 | PR P0COST 000531 (PR) Summary | 0 | 0 |  |  |  | 0 | 2889.24 | 0 | 34
ttJTrans | 0-4013-02 | LA |  | LA |  |  | 2026-05-21 |  | 0-4013-02 | PR P0COST 000531 (PR) Summary | 0 | 0 |  |  |  | 0 | 2317.98 | 0 | 40
ttJTrans | 0-4013-02 | LA |  | LA |  |  | 2026-05-21 |  | 0-4013-02 | PR P0COST 000531 (PR) Summary | 0 | 0 |  |  |  | 0 | 631.72 | 0 | 0
ttJTrans | 0-4013-02 | LA |  | LA |  |  | 2026-05-21 |  | 0-4013-02 | PR P0COST 000531 (PR) Summary | 0 | 0 |  |  |  | 0 | 501.62 | 0 | 8
ttJTrans | 0-4015 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4015 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4015 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4015 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4015 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4015 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4015 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4015 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4015 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4015 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4015 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4015 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4015 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4015 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4015 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4015 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4015 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4015 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4015 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4015 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4015 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4015 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4015 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4015 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4015 | ER |  | ER |  |  | 2026-03-22 |  | 0-4015 | RMS2259 IC-75 IHI MOROOKA CRAWLER CARRIER W/ VACUUM UNIT IC-75 IHI MOROOKA CRAWLER CARRIER W/ VACUUM UNIT | 0 | 0 |  | RMS2259 |  | 0 | 459.77 | 0 | 0
ttJTrans | 0-4015 | ER |  | ER |  |  | 2026-03-22 |  | 0-4015 | RMS2259 IC-75 IHI MOROOKA CRAWLER CARRIER W/ VACUUM UNIT IC-75 IHI MOROOKA CRAWLER CARRIER W/ VACUUM UNIT | 0 | 0 |  | RMS2259 |  | 0 | 459.77 | 0 | 0
ttJTrans | 0-4015 | ER |  | ER |  |  | 2026-03-22 |  | 0-4015 | RMV34 2000 GAL WATER TRUCK 2000 GAL WATER TRUCK | 0 | 0 |  | RMV34 |  | 0 | 198.28 | 0 | 0
ttJTrans | 0-4015 | ER |  | ER |  |  | 2026-03-22 |  | 0-4015 | RMV34 2000 GAL WATER TRUCK 2000 GAL WATER TRUCK | 0 | 0 |  | RMV34 |  | 0 | 198.28 | 0 | 0
ttJTrans | 0-4015 | ER |  | ER |  |  | 2026-03-22 |  | 0-4015 | RMV34 2000 GAL WATER TRUCK 2000 GAL WATER TRUCK | 0 | 0 |  | RMV34 |  | 0 | 198.28 | 0 | 0
ttJTrans | 0-4015 | ER |  | ER |  |  | 2026-03-22 |  | 0-4015 | RMV34 2000 GAL WATER TRUCK 2000 GAL WATER TRUCK | 0 | 0 |  | RMV34 |  | 0 | 198.28 | 0 | 0
ttJTrans | 0-4015 | ER |  | ER |  |  | 2026-03-22 |  | 0-4015 | RLD287 3600-4000 LB SKID STEER JOHN DEERE 333P 3600-4000 LB SKID STEER JOHN DEERE 333P | 0 | 0 |  | RLD287 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4015 | ER |  | ER |  |  | 2026-03-22 |  | 0-4015 | RLD287 3600-4000 LB SKID STEER JOHN DEERE 333P 3600-4000 LB SKID STEER JOHN DEERE 333P | 0 | 0 |  | RLD287 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4015 | ER |  | ER |  |  | 2026-03-22 |  | 0-4015 | RLD287 3600-4000 LB SKID STEER JOHN DEERE 333P 3600-4000 LB SKID STEER JOHN DEERE 333P | 0 | 0 |  | RLD287 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4015 | ER |  | ER |  |  | 2026-03-22 |  | 0-4015 | RLD287 3600-4000 LB SKID STEER JOHN DEERE 333P 3600-4000 LB SKID STEER JOHN DEERE 333P | 0 | 0 |  | RLD287 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4015 | ER |  | ER |  |  | 2026-03-22 |  | 0-4015 | RLD287 3600-4000 LB SKID STEER JOHN DEERE 333P 3600-4000 LB SKID STEER JOHN DEERE 333P | 0 | 0 |  | RLD287 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4015 | ER |  | ER |  |  | 2026-03-22 |  | 0-4015 | RMV34 2000 GAL WATER TRUCK 2000 GAL WATER TRUCK | 0 | 0 |  | RMV34 |  | 0 | 198.28 | 0 | 0
ttJTrans | 0-4015 | ER |  | ER |  |  | 2026-03-22 |  | 0-4015 | RMV34 2000 GAL WATER TRUCK 2000 GAL WATER TRUCK | 0 | 0 |  | RMV34 |  | 0 | 198.28 | 0 | 0
ttJTrans | 0-4015 | ER |  | ER |  |  | 2026-03-22 |  | 0-4015 | RMS2259 IC-75 IHI MOROOKA CRAWLER CARRIER W/ VACUUM UNIT IC-75 IHI MOROOKA CRAWLER CARRIER W/ VACUUM UNIT | 0 | 0 |  | RMS2259 |  | 0 | 459.77 | 0 | 0
ttJTrans | 0-4015 | ER |  | ER |  |  | 2026-03-22 |  | 0-4015 | RMS2259 IC-75 IHI MOROOKA CRAWLER CARRIER W/ VACUUM UNIT IC-75 IHI MOROOKA CRAWLER CARRIER W/ VACUUM UNIT | 0 | 0 |  | RMS2259 |  | 0 | 459.77 | 0 | 0
ttJTrans | 0-4015 | ER |  | ER |  |  | 2026-03-22 |  | 0-4015 | RMS2259 IC-75 IHI MOROOKA CRAWLER CARRIER W/ VACUUM UNIT IC-75 IHI MOROOKA CRAWLER CARRIER W/ VACUUM UNIT | 0 | 0 |  | RMS2259 |  | 0 | 459.77 | 0 | 0
ttJTrans | 0-4015 | ER |  | ER |  |  | 2026-03-22 |  | 0-4015 | RMS2259 IC-75 IHI MOROOKA CRAWLER CARRIER W/ VACUUM UNIT IC-75 IHI MOROOKA CRAWLER CARRIER W/ VACUUM UNIT | 0 | 0 |  | RMS2259 |  | 0 | 459.77 | 0 | 0
ttJTrans | 0-4015 | ER |  | ER |  |  | 2026-05-10 |  | 0-4015 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4015 | ER |  | ER |  |  | 2026-05-17 |  | 0-4015 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4015 | ER |  | ER |  |  | 2026-05-24 |  | 0-4015 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4015 | ER |  | ER |  |  | 2026-05-24 |  | 0-4015 | RMS1653 HIPER VR BASE & ROVER HIPER VR BASE & ROVER | 0 | 0 |  | RMS1653 |  | 0 | 191.57 | 0 | 0
ttJTrans | 0-4015 | ER |  | ER |  |  | 2026-05-24 |  | 0-4015 | RMS1653 HIPER VR BASE & ROVER HIPER VR BASE & ROVER | 0 | 0 |  | RMS1653 |  | 0 | 191.57 | 0 | 0
ttJTrans | 0-4015 | ER |  | ER |  |  | 2026-05-24 |  | 0-4015 | RMS1653 HIPER VR BASE & ROVER HIPER VR BASE & ROVER | 0 | 0 |  | RMS1653 |  | 0 | 191.57 | 0 | 0
ttJTrans | 0-4015 | ER |  | ER |  |  | 2026-05-24 |  | 0-4015 | RMS1653 HIPER VR BASE & ROVER HIPER VR BASE & ROVER | 0 | 0 |  | RMS1653 |  | 0 | 191.57 | 0 | 0
ttJTrans | 0-4015 | ER |  | ER |  |  | 2026-05-24 |  | 0-4015 | RMS1653 HIPER VR BASE & ROVER HIPER VR BASE & ROVER | 0 | 0 |  | RMS1653 |  | 0 | 191.57 | 0 | 0
ttJTrans | 0-4015 | ER |  | ER |  |  | 2026-05-24 |  | 0-4015 | RMS1653 HIPER VR BASE & ROVER HIPER VR BASE & ROVER | 0 | 0 |  | RMS1653 |  | 0 | 191.57 | 0 | 0
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-01-29 |  | 0-4015 | PR P0COST 000514 (PR) Summary | 0 | 0 |  |  |  | 0 | 453.92 | 0 | 7
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-01-29 |  | 0-4015 | PR P0COST 000514 (PR) Summary | 0 | 0 |  |  |  | 0 | 659.53 | 0 | 7
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-02-05 |  | 0-4015 | PR P0COST 000515 (PR) Summary | 0 | 0 |  |  |  | 0 | 2200.78 | 0 | 44
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-02-05 |  | 0-4015 | PR P0COST 000515 (PR) Summary | 0 | 0 |  |  |  | 0 | 2200.79 | 0 | 44
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-02-05 |  | 0-4015 | PR P0COST 000515 (PR) Summary | 0 | 0 |  |  |  | 0 | 1913.39 | 0 | 33
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-02-05 |  | 0-4015 | PR P0COST 000515 (PR) Summary | 0 | 0 |  |  |  | 0 | 759.95 | 0 | 7
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-02-05 |  | 0-4015 | PR P0COST 000515 (PR) Summary | 0 | 0 |  |  |  | 0 | 395.95 | 0 | 8
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-02-05 |  | 0-4015 | PR P0COST 000515 (PR) Summary | 0 | 0 |  |  |  | 0 | 460.9 | 0 | 11
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-02-05 |  | 0-4015 | PR P0COST 000515 (PR) Summary | 0 | 0 |  |  |  | 0 | 1053.81 | 0 | 20
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-03-12 |  | 0-4015 | PR P0COST 000521 (PR) Summary | 0 | 0 |  |  |  | 0 | 2683.91 | 0 | 60
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-03-12 |  | 0-4015 | PR P0COST 000521 (PR) Summary | 0 | 0 |  |  |  | 0 | 2683.91 | 0 | 60
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-03-12 |  | 0-4015 | PR P0COST 000521 (PR) Summary | 0 | 0 |  |  |  | 0 | 2683.92 | 0 | 60
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-03-12 |  | 0-4015 | PR P0COST 000521 (PR) Summary | 0 | 0 |  |  |  | 0 | 2575.93 | 0 | 55
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-03-12 |  | 0-4015 | PR P0COST 000521 (PR) Summary | 0 | 0 |  |  |  | 0 | 1531.96 | 0 | 5
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-03-12 |  | 0-4015 | PR P0COST 000521 (PR) Summary | 0 | 0 |  |  |  | 0 | 1379.97 | 0 | 0
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-03-12 |  | 0-4015 | PR P0COST 000521 (PR) Summary | 0 | 0 |  |  |  | 0 | 1512.54 | 0 | 35
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-03-12 |  | 0-4015 | PR P0COST 000521 (PR) Summary | 0 | 0 |  |  |  | 0 | 1716 | 0 | 40
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-03-19 |  | 0-4015 | PR P0COST 000522 (PR) Summary | 0 | 0 |  |  |  | 0 | 3712.11 | 0 | 81.02
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-03-19 |  | 0-4015 | PR P0COST 000522 (PR) Summary | 0 | 0 |  |  |  | 0 | 3712.11 | 0 | 81.02
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-03-19 |  | 0-4015 | PR P0COST 000522 (PR) Summary | 0 | 0 |  |  |  | 0 | 3712.12 | 0 | 81.02
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-03-19 |  | 0-4015 | PR P0COST 000522 (PR) Summary | 0 | 0 |  |  |  | 0 | 3082.54 | 0 | 70
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-03-19 |  | 0-4015 | PR P0COST 000522 (PR) Summary | 0 | 0 |  |  |  | 0 | 1994.8 | 0 | 11.5
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-03-19 |  | 0-4015 | PR P0COST 000522 (PR) Summary | 0 | 0 |  |  |  | 0 | 1994.77 | 0 | 6.02
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-03-19 |  | 0-4015 | PR P0COST 000522 (PR) Summary | 0 | 0 |  |  |  | 0 | 2178.9 | 0 | 45
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-03-19 |  | 0-4015 | PR P0COST 000522 (PR) Summary | 0 | 0 |  |  |  | 0 | 2336.84 | 0 | 50
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-03-30 |  | 0-4015 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 960.2 | 0 | 10
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-03-30 |  | 0-4015 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 960.18 | 0 | 10
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-03-30 |  | 0-4015 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 960.2 | 0 | 10
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-03-30 |  | 0-4015 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 960.2 | 0 | 10
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-03-30 |  | 0-4015 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 960.18 | 0 | 10
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-03-30 |  | 0-4015 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 960.2 | 0 | 10
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-03-26 |  | 0-4015 | PR P0COST 000523 (PR) Summary | 0 | 0 |  |  |  | 0 | 2984.07 | 0 | 60
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-03-26 |  | 0-4015 | PR P0COST 000523 (PR) Summary | 0 | 0 |  |  |  | 0 | 2984.07 | 0 | 60
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-03-26 |  | 0-4015 | PR P0COST 000523 (PR) Summary | 0 | 0 |  |  |  | 0 | 2015.31 | 0 | 30
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-03-26 |  | 0-4015 | PR P0COST 000523 (PR) Summary | 0 | 0 |  |  |  | 0 | 2015.31 | 0 | 30
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-03-26 |  | 0-4015 | PR P0COST 000523 (PR) Summary | 0 | 0 |  |  |  | 0 | 1485.9 | 0 | 0
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-03-26 |  | 0-4015 | PR P0COST 000523 (PR) Summary | 0 | 0 |  |  |  | 0 | 711.67 | 0 | 0
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-03-26 |  | 0-4015 | PR P0COST 000523 (PR) Summary | 0 | 0 |  |  |  | 0 | 406.83 | 0 | 5
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-04-02 |  | 0-4015 | PR P0COST 000524 (PR) Summary | 0 | 0 |  |  |  | 0 | 1516.01 | 0 | 20
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-04-02 |  | 0-4015 | PR P0COST 000524 (PR) Summary | 0 | 0 |  |  |  | 0 | 1516.01 | 0 | 20
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-04-02 |  | 0-4015 | PR P0COST 000524 (PR) Summary | 0 | 0 |  |  |  | 0 | 1516.03 | 0 | 20
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-04-02 |  | 0-4015 | PR P0COST 000524 (PR) Summary | 0 | 0 |  |  |  | 0 | 1516.04 | 0 | 20
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-04-09 |  | 0-4015 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 729.48 | 0 | 10
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-04-09 |  | 0-4015 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 1280.79 | 0 | 20
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-04-09 |  | 0-4015 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 1280.79 | 0 | 20
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-04-09 |  | 0-4015 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 1280.81 | 0 | 20
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-04-09 |  | 0-4015 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 1280.81 | 0 | 20
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-04-09 |  | 0-4015 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 774.21 | 0 | 0
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-04-16 |  | 0-4015 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 729.48 | 0 | 10
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-04-16 |  | 0-4015 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 2014.42 | 0 | 30
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-04-16 |  | 0-4015 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 2013.99 | 0 | 30
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-04-16 |  | 0-4015 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 2014.01 | 0 | 30
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-04-16 |  | 0-4015 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 2014.01 | 0 | 30
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-04-16 |  | 0-4015 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 1493.05 | 0 | 0
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-04-23 |  | 0-4015 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 527.65 | 0 | 8
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-04-23 |  | 0-4015 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 803.94 | 0 | 12
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-04-23 |  | 0-4015 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 2056.79 | 0 | 40
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-04-23 |  | 0-4015 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 1461.39 | 0 | 30
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-04-23 |  | 0-4015 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 1461.39 | 0 | 20
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-04-23 |  | 0-4015 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 1098.74 | 0 | 12
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-04-23 |  | 0-4015 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 567.3 | 0 | 10
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-04-23 |  | 0-4015 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 567.31 | 0 | 10
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-04-23 |  | 0-4015 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 567.29 | 0 | 0
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-04-30 |  | 0-4015 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 1533.19 | 0 | 30
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-04-30 |  | 0-4015 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 1172.95 | 0 | 20
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-04-30 |  | 0-4015 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 1172.95 | 0 | 20
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-04-30 |  | 0-4015 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 1172.95 | 0 | 20
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-05-07 |  | 0-4015 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 408.71 | 0 | 10
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-05-08 |  | 0-4015 | COST CODE TRANSFER 25-4005 | 0 | 0 |  |  |  | 0 | -41790.32 | 0 | -600
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-05-07 |  | 0-4015 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 704.9 | 0 | 10
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-05-07 |  | 0-4015 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 681.56 | 0 | 10
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-05-07 |  | 0-4015 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 490.64 | 0 | 10
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-05-07 |  | 0-4015 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 899.35 | 0 | 20
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-05-07 |  | 0-4015 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 899.35 | 0 | 20
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-05-07 |  | 0-4015 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 899.35 | 0 | 20
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-05-14 |  | 0-4015 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 1260.17 | 0 | 20
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-05-14 |  | 0-4015 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 655.04 | 0 | 10
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-05-14 |  | 0-4015 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 863.98 | 0 | 20
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-05-14 |  | 0-4015 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 863.98 | 0 | 20
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-05-14 |  | 0-4015 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 863.98 | 0 | 20
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-05-14 |  | 0-4015 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 863.98 | 0 | 20
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-05-21 |  | 0-4015 | PR P0COST 000531 (PR) Summary | 0 | 0 |  |  |  | 0 | 1199.65 | 0 | 20
ttJTrans | 0-4015 | LA |  | LA |  |  | 2026-05-21 |  | 0-4015 | PR P0COST 000531 (PR) Summary | 0 | 0 |  |  |  | 0 | 1199.65 | 0 | 20
ttJTrans | 0-4015 | MA | MA1010580 | MA | MA1010580 | 2026-03-13 | 2026-03-16 | 1 | 0-4015 | Yards of Fill Sand E-1125 | 28 | 334.11 | PO:COMMIT | 21358 | TEXAS GULF COAST AGGREGATES, LLC | 0 | 0 | 334.11 | 0
ttJTrans | 0-4015 | MA | MA1010580 | MA | MA1010580 | 2026-03-13 | 2026-03-16 | 1 | 0-4015 | Yards of Fill Sand E-1125 | 28 | 334.11 | INVOICE:ADJ-COMMIT | 21358 | TEXAS GULF COAST AGGREGATES, LLC | 0 | 0 | -334.11 | 0
ttJTrans | 0-4015 | MA | MA1010580 | MA | MA1010580 | 2026-03-13 | 2026-05-20 | 1 | 0-4015 | Yards of Fill Sand E-1125 | 28 | 334.11 | INVOICE | 21358 | TEXAS GULF COAST AGGREGATES, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4015 | MA |  | MA |  |  | 2026-05-20 |  | 0-4015 | 2 loads fill sand approved by Eugene | 0 | 0 |  | 21358 | TEXAS GULF COAST AGGREGATES, LLC | 0 | 325.83 | 0 | 0
ttJTrans | 0-4015 | OC | MA1010561 | OC | MA1010561 | 2026-03-12 | 2026-04-01 | 10 | 0-4015 | GAUCHO 1047-6-14GA.- 330' | 1 | 243.09 | INVOICE | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4015 | OC | MA1010561 | OC | MA1010561 | 2026-03-12 | 2026-04-01 | 7 | 0-4015 | MARKING WAND PRO | 1 | 43.28 | INVOICE | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4015 | OC | MA1010561 | OC | MA1010561 | 2026-03-12 | 2026-04-01 | 6 | 0-4015 | MARKING PAINT SB FL ORNG | 4 | 39.92 | INVOICE | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4015 | OC | MA1010561 | OC | MA1010561 | 2026-03-12 | 2026-04-01 | 1 | 0-4015 | 100PC BLACK 11.8" 50LB TENSILE S | 2 | 17.52 | INVOICE | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4015 | OC | MA1010561 | OC | MA1010561 | 2026-03-12 | 2026-04-01 | 11 | 0-4015 | T-POST 1.33 6.5' | 30 | 258.08 | INVOICE | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4015 | OC | MA1010561 | OC | MA1010561 | 2026-03-12 | 2026-04-01 | 8 | 0-4015 | POULTRY FENCE 3'X25' GRN | 2 | 71.02 | INVOICE | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4015 | OC | MA1010561 | OC | MA1010561 | 2026-03-12 | 2026-03-13 | 6 | 0-4015 | MARKING PAINT SB FL ORNG | 4 | 39.92 | PO:COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 39.92 | 0
ttJTrans | 0-4015 | OC | MA1010561 | OC | MA1010561 | 2026-03-12 | 2026-03-13 | 11 | 0-4015 | T-POST 1.33 6.5' | 30 | 258.08 | PO:COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 258.08 | 0
ttJTrans | 0-4015 | OC | MA1010561 | OC | MA1010561 | 2026-03-12 | 2026-03-13 | 8 | 0-4015 | POULTRY FENCE 3'X25' GRN | 2 | 71.02 | PO:COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 71.02 | 0
ttJTrans | 0-4015 | OC | MA1010561 | OC | MA1010561 | 2026-03-12 | 2026-03-13 | 7 | 0-4015 | MARKING WAND PRO | 1 | 43.28 | PO:COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 43.28 | 0
ttJTrans | 0-4015 | OC | MA1010561 | OC | MA1010561 | 2026-03-12 | 2026-03-13 | 7 | 0-4015 | MARKING WAND PRO | 1 | 43.28 | INVOICE:ADJ-COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | -43.28 | 0
ttJTrans | 0-4015 | OC | MA1010561 | OC | MA1010561 | 2026-03-12 | 2026-03-13 | 6 | 0-4015 | MARKING PAINT SB FL ORNG | 4 | 39.92 | INVOICE:ADJ-COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | -39.92 | 0
ttJTrans | 0-4015 | OC | MA1010561 | OC | MA1010561 | 2026-03-12 | 2026-03-13 | 1 | 0-4015 | 100PC BLACK 11.8" 50LB TENSILE S | 2 | 17.52 | INVOICE:ADJ-COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | -17.52 | 0
ttJTrans | 0-4015 | OC | MA1010561 | OC | MA1010561 | 2026-03-12 | 2026-03-13 | 11 | 0-4015 | T-POST 1.33 6.5' | 30 | 258.08 | INVOICE:ADJ-COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | -258.08 | 0
ttJTrans | 0-4015 | OC | MA1010561 | OC | MA1010561 | 2026-03-12 | 2026-03-13 | 10 | 0-4015 | GAUCHO 1047-6-14GA.- 330' | 1 | 243.09 | INVOICE:ADJ-COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | -243.09 | 0
ttJTrans | 0-4015 | OC | MA1010561 | OC | MA1010561 | 2026-03-12 | 2026-03-13 | 8 | 0-4015 | POULTRY FENCE 3'X25' GRN | 2 | 71.02 | INVOICE:ADJ-COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | -71.02 | 0
ttJTrans | 0-4015 | OC | MA1010561 | OC | MA1010561 | 2026-03-12 | 2026-03-13 | 10 | 0-4015 | GAUCHO 1047-6-14GA.- 330' | 1 | 243.09 | PO:COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 243.09 | 0
ttJTrans | 0-4015 | OC | MA1010561 | OC | MA1010561 | 2026-03-12 | 2026-03-13 | 1 | 0-4015 | 100PC BLACK 11.8" 50LB TENSILE S | 2 | 17.52 | PO:COMMIT | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 0 | 17.52 | 0
ttJTrans | 0-4015 | OC | MA1010600 | OC | MA1010600 | 2026-03-16 | 2026-03-17 | 2 | 0-4015 | CHRISNIK TIP MARKERS BLACK | 1 | 27.75 | PO:COMMIT | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | 27.75 | 0
ttJTrans | 0-4015 | OC | MA1010600 | OC | MA1010600 | 2026-03-16 | 2026-03-17 | 1 | 0-4015 | 1/2 X2X48 POPLAR LATH STAKES 50 PCS | 5 | 299.32 | INVOICE:ADJ-COMMIT | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | -299.32 | 0
ttJTrans | 0-4015 | OC | MA1010600 | OC | MA1010600 | 2026-03-16 | 2026-03-17 | 2 | 0-4015 | CHRISNIK TIP MARKERS BLACK | 1 | 27.75 | INVOICE:ADJ-COMMIT | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | -27.75 | 0
ttJTrans | 0-4015 | OC | MA1010600 | OC | MA1010600 | 2026-03-16 | 2026-03-17 | 1 | 0-4015 | 1/2 X2X48 POPLAR LATH STAKES 50 PCS | 5 | 299.32 | PO:COMMIT | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | 299.32 | 0
ttJTrans | 0-4015 | OC | MA1010600 | OC | MA1010600 | 2026-03-16 | 2026-04-09 | 2 | 0-4015 | CHRISNIK TIP MARKERS BLACK | 1 | 27.75 | INVOICE | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | 0 | 0
ttJTrans | 0-4015 | OC | MA1010600 | OC | MA1010600 | 2026-03-16 | 2026-04-09 | 1 | 0-4015 | 1/2 X2X48 POPLAR LATH STAKES 50 PCS | 5 | 299.32 | INVOICE | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | 0 | 0
ttJTrans | 0-4015 | OC |  | OC |  |  | 2026-04-01 |  | 0-4015 | Fencing Supplies T-post Wire Fencing Approved by Eugene | 0 | 0 |  | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 404.54 | 0 | 0
ttJTrans | 0-4015 | OC |  | OC |  |  | 2026-04-01 |  | 0-4015 | Fencing Supplies T-post Wire Fencing Approved by Eugene | 0 | 0 |  | 21265 | WHARTON FEED & SUPPLY LLC | 0 | 232.5 | 0 | 0
ttJTrans | 0-4015 | OC |  | OC |  |  | 2026-04-09 |  | 0-4015 | POPLAR LATH STAKE 50 PCS/ CHISEL TIP BLACK MARKERS | 0 | 0 |  | 20746 | ALLTERRA CENTRAL, INC | 0 | 318.97 | 0 | 0
ttJTrans | 0-4015 | SU | SO1000241 | SU | SO1000241 | 2025-11-03 | 2025-11-04 | 1 | 0-4015 | SURVEY | 1 | 28288.75 | CERTIFICATE | 20047 | FGS-SURVEYORS | 0 | 0 | -28288.75 | 0
ttJTrans | 0-4015 | SU | SO1000241 | SU | SO1000241 | 2025-11-03 | 2025-11-04 | 1 | 0-4015 | SURVEY | 1 | 28288.75 | PO:COMMIT | 20047 | FGS-SURVEYORS | 0 | 0 | 28288.75 | 0
ttJTrans | 0-4015 | SU |  | SU |  |  | 2026-03-31 |  | 0-4015 | SURVEY | 0 | 0 |  | 20047 |  | 0 | 26500 | 0 | 0
ttJTrans | 0-4015 | SU |  | SU |  |  | 2026-04-17 |  | 0-4015 | 25-4005 MARCH USE TAX ADJ | 0 | 0 |  |  |  | 0 | 1788.75 | 0 | 0
ttJTrans | 0-4015-01 | LA |  | LA |  |  | 2026-04-30 |  | 0-4015-01 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 399.4 | 0 | 5
ttJTrans | 0-4015-01 | LA |  | LA |  |  | 2026-04-30 |  | 0-4015-01 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 653.55 | 0 | 0
ttJTrans | 0-4015-01 | LA |  | LA |  |  | 2026-05-08 |  | 0-4015-01 | COST CODE TRANSFER 25-4005 | 0 | 0 |  |  |  | 0 | 41790.32 | 0 | 600
ttJTrans | 0-4015-01 | OC | MA1010930 | OC | MA1010930 | 2026-04-01 | 2026-04-15 | 3 | 0-4015-01 | Construction Flo Green Paint | 1 | 62.66 | INVOICE | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | 0 | 0
ttJTrans | 0-4015-01 | OC | MA1010930 | OC | MA1010930 | 2026-04-01 | 2026-04-15 | 2 | 0-4015-01 | Construction Flo Orange Paint | 5 | 313.29 | INVOICE | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | 0 | 0
ttJTrans | 0-4015-01 | OC | MA1010930 | OC | MA1010930 | 2026-04-01 | 2026-04-15 | 4 | 0-4015-01 | FLAGGING, TEXAS PINK GLO | 1 | 26.47 | INVOICE | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | 0 | 0
ttJTrans | 0-4015-01 | OC | MA1010930 | OC | MA1010930 | 2026-04-01 | 2026-04-15 | 1 | 0-4015-01 | ½ x 1-1/4 x 36 POPLAR LATH pcs | 10 | 587.36 | INVOICE | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | 0 | 0
ttJTrans | 0-4015-01 | OC | MA1010930 | OC | MA1010930 | 2026-04-01 | 2026-04-01 | 3 | 0-4015-01 | Construction Flo Green Paint | 1 | 62.66 | PO:COMMIT | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | 62.66 | 0
ttJTrans | 0-4015-01 | OC | MA1010930 | OC | MA1010930 | 2026-04-01 | 2026-04-01 | 1 | 0-4015-01 | ½ x 1-1/4 x 36 POPLAR LATH pcs | 10 | 587.36 | PO:COMMIT | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | 587.36 | 0
ttJTrans | 0-4015-01 | OC | MA1010930 | OC | MA1010930 | 2026-04-01 | 2026-04-01 | 2 | 0-4015-01 | Construction Flo Orange Paint | 5 | 313.29 | PO:COMMIT | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | 313.29 | 0
ttJTrans | 0-4015-01 | OC | MA1010930 | OC | MA1010930 | 2026-04-01 | 2026-04-01 | 1 | 0-4015-01 | ½ x 1-1/4 x 36 POPLAR LATH pcs | 10 | 587.36 | INVOICE:ADJ-COMMIT | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | -587.36 | 0
ttJTrans | 0-4015-01 | OC | MA1010930 | OC | MA1010930 | 2026-04-01 | 2026-04-01 | 4 | 0-4015-01 | FLAGGING, TEXAS PINK GLO | 1 | 26.47 | INVOICE:ADJ-COMMIT | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | -26.47 | 0
ttJTrans | 0-4015-01 | OC | MA1010930 | OC | MA1010930 | 2026-04-01 | 2026-04-01 | 3 | 0-4015-01 | Construction Flo Green Paint | 1 | 62.66 | INVOICE:ADJ-COMMIT | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | -62.66 | 0
ttJTrans | 0-4015-01 | OC | MA1010930 | OC | MA1010930 | 2026-04-01 | 2026-04-01 | 2 | 0-4015-01 | Construction Flo Orange Paint | 5 | 313.29 | INVOICE:ADJ-COMMIT | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | -313.29 | 0
ttJTrans | 0-4015-01 | OC | MA1010930 | OC | MA1010930 | 2026-04-01 | 2026-04-01 | 4 | 0-4015-01 | FLAGGING, TEXAS PINK GLO | 1 | 26.47 | PO:COMMIT | 20746 | ALLTERRA CENTRAL, INC | 0 | 0 | 26.47 | 0
ttJTrans | 0-4015-01 | OC | MA1010945 | OC | MA1010945 | 2026-04-01 | 2026-04-02 | 2 | 0-4015-01 | PULUZ Suction Cup Mount for Gopro Car Mount, | 1 | 11.09 | PO:COMMIT | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | 11.09 | 0
ttJTrans | 0-4015-01 | OC | MA1010945 | OC | MA1010945 | 2026-04-01 | 2026-04-02 | 1 | 0-4015-01 | GoPro Hero Ecommerce Packaging - Compact | 1 | 226.43 | INVOICE:ADJ-COMMIT | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | -226.43 | 0
ttJTrans | 0-4015-01 | OC | MA1010945 | OC | MA1010945 | 2026-04-01 | 2026-04-02 | 2 | 0-4015-01 | PULUZ Suction Cup Mount for Gopro Car Mount, | 1 | 11.09 | INVOICE:ADJ-COMMIT | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | -11.09 | 0
ttJTrans | 0-4015-01 | OC | MA1010945 | OC | MA1010945 | 2026-04-01 | 2026-04-02 | 1 | 0-4015-01 | GoPro Hero Ecommerce Packaging - Compact | 1 | 226.43 | PO:COMMIT | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | 226.43 | 0
ttJTrans | 0-4015-01 | OC | MA1010945 | OC | MA1010945 | 2026-04-01 | 2026-05-12 | 1 | 0-4015-01 | GoPro Hero Ecommerce Packaging - Compact | 1 | 226.43 | INVOICE | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4015-01 | OC | MA1010945 | OC | MA1010945 | 2026-04-01 | 2026-05-12 | 2 | 0-4015-01 | PULUZ Suction Cup Mount for Gopro Car Mount, | 1 | 11.09 | INVOICE | 20395 | AMAZON.COM SERVICES LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4015-01 | OC |  | OC |  |  | 2026-04-09 |  | 0-4015-01 | POPULAR LATH/ ORANGE PAINT/ GREEN PAINT/ FLAGGING TEXAS PINK GLO | 0 | 0 |  | 20746 | ALLTERRA CENTRAL, INC | 0 | 965.25 | 0 | 0
ttJTrans | 0-4015-01 | OC |  | OC |  |  | 2026-05-11 |  | 0-4015-01 | COMPACT WATERPROOF CAMERA / SUCTION CUP MOUNT | 0 | 0 |  | 20395 | AMAZON.COM SERVICES LLC | 0 | 231.63 | 0 | 0
ttJTrans | 0-4016 | SU | SO1000214 | SU | SO1000214 | 2025-10-06 | 2025-10-28 | 1 | 0-4016 | PERMITTING | 1 | 64797.25 | PO:COMMIT | 12043 | SCHOEFFLER ENERGY GROUP INC | 0 | 0 | 64797.25 | 0
ttJTrans | 0-4016 | SU | SO1000214 | SU | SO1000214 | 2025-10-06 | 2025-10-28 | 1 | 0-4016 | PERMITTING | 1 | 64797.25 | CERTIFICATE | 12043 | SCHOEFFLER ENERGY GROUP INC | 0 | 0 | -1617.26 | 0
ttJTrans | 0-4016 | SU | SO1000214 | SU | SO1000214 | 2025-10-06 | 2025-10-28 | 1 | 0-4016 | PERMITTING | 1 | 64797.25 | CERTIFICATE | 12043 | SCHOEFFLER ENERGY GROUP INC | 0 | 0 | -680.53 | 0
ttJTrans | 0-4016 | SU | SO1000214 | SU | SO1000214 | 2025-10-06 | 2025-10-28 | 1 | 0-4016 | PERMITTING | 1 | 64797.25 | CERTIFICATE | 12043 | SCHOEFFLER ENERGY GROUP INC | 0 | 0 | -2305.8 | 0
ttJTrans | 0-4016 | SU | SO1000214 | SU | SO1000214 | 2025-10-06 | 2025-10-28 | 1 | 0-4016 | PERMITTING | 1 | 64797.25 | CERTIFICATE | 12043 | SCHOEFFLER ENERGY GROUP INC | 0 | 0 | -1008.79 | 0
ttJTrans | 0-4016 | SU | SO1000214 | SU | SO1000214 | 2025-10-06 | 2025-10-28 | 1 | 0-4016 | PERMITTING | 1 | 64797.25 | CERTIFICATE | 12043 | SCHOEFFLER ENERGY GROUP INC | 0 | 0 | -2513.96 | 0
ttJTrans | 0-4016 | SU | SO1000214 | SU | SO1000214 | 2025-10-06 | 2025-10-28 | 1 | 0-4016 | PERMITTING | 1 | 64797.25 | CERTIFICATE | 12043 | SCHOEFFLER ENERGY GROUP INC | 0 | 0 | -1393.09 | 0
ttJTrans | 0-4016 | SU | SO1000214 | SU | SO1000214 | 2025-10-06 | 2025-10-28 | 1 | 0-4016 | PERMITTING | 1 | 64797.25 | CERTIFICATE | 12043 | SCHOEFFLER ENERGY GROUP INC | 0 | 0 | -576.45 | 0
ttJTrans | 0-4016 | SU | SO1000214 | SU | SO1000214 | 2025-10-06 | 2025-10-28 | 1 | 0-4016 | PERMITTING | 1 | 64797.25 | CERTIFICATE | 12043 | SCHOEFFLER ENERGY GROUP INC | 0 | 0 | -4499.51 | 0
ttJTrans | 0-4016 | SU | SO1000214 | SU | SO1000214 | 2025-10-06 | 2025-10-28 | 1 | 0-4016 | PERMITTING | 1 | 64797.25 | CERTIFICATE | 12043 | SCHOEFFLER ENERGY GROUP INC | 0 | 0 | -2193.71 | 0
ttJTrans | 0-4016 | SU | SO1000214 | SU | SO1000214 | 2025-10-06 | 2025-10-28 | 1 | 0-4016 | PERMITTING | 1 | 64797.25 | CERTIFICATE | 12043 | SCHOEFFLER ENERGY GROUP INC | 0 | 0 | -2921.6 | 0
ttJTrans | 0-4016 | SU | SO1000214 | SU | SO1000214 | 2025-10-06 | 2025-10-28 | 1 | 0-4016 | PERMITTING | 1 | 64797.25 | CERTIFICATE | 12043 | SCHOEFFLER ENERGY GROUP INC | 0 | 0 | -1665.3 | 0
ttJTrans | 2-4004 | SU | SO1000249 | SU | SO1000249 | 2026-03-17 | 2026-03-23 | 2 | 2-4004 | INCREASE AMOUNT PER MEGAN REDFIELD | 1 | 462331.05 | CERTIFICATE | 21204 | SIEMENS ENERGY, INC. | 0 | 0 | -462331.05 | 0
ttJTrans | 2-4004 | SU | SO1000249 | SU | SO1000249 | 2025-11-10 | 2025-12-14 | 1 | 2-4004 | BREAKER RESERVATION | 1 | 463540.53 | PO:COMMIT | 21204 | SIEMENS ENERGY, INC. | 0 | 0 | 463540.53 | 0
ttJTrans | 2-4004 | SU | SO1000249 | SU | SO1000249 | 2026-03-17 | 2026-03-23 | 2 | 2-4004 | INCREASE AMOUNT PER MEGAN REDFIELD | 1 | 462331.05 | PO:COMMIT | 21204 | SIEMENS ENERGY, INC. | 0 | 0 | 462331.05 | 0
ttJTrans | 2-4004 | SU | SO1000249 | SU | SO1000249 | 2025-11-10 | 2025-12-14 | 1 | 2-4004 | BREAKER RESERVATION | 1 | 463540.53 | CERTIFICATE | 21204 | SIEMENS ENERGY, INC. | 0 | 0 | -332423.63 | 0
ttJTrans | 2-4004 | SU | SO1000249 | SU | SO1000249 | 2025-11-10 | 2025-12-14 | 1 | 2-4004 | BREAKER RESERVATION | 1 | 463540.53 | CERTIFICATE | 21204 | SIEMENS ENERGY, INC. | 0 | 0 | -131116.9 | 0
ttJTrans | 2-4004 | SU | SO1000249 | SU | SO1000249 | 2026-03-27 | 2026-04-01 | 3 | 2-4004 | ENGINEERING | 1 | 9344114.12 | PO:COMMIT | 21204 | SIEMENS ENERGY, INC. | 0 | 0 | 9344114.12 | 0
ttJTrans | 0-4016 | SU |  | SU |  |  | 2025-11-02 |  | 0-4016 | PERMITTING | 0 | 0 |  | 12043 | SCHOEFFLER ENERGY GROUP INC | 0 | 637.5 | 0 | 0
ttJTrans | 0-4016 | SU |  | SU |  |  | 2025-11-23 |  | 0-4016 | PERMITTING | 0 | 0 |  | 12043 | SCHOEFFLER ENERGY GROUP INC | 0 | 1515 | 0 | 0
ttJTrans | 0-4016 | SU |  | SU |  |  | 2025-12-01 |  | 0-4016 | PERMITTING | 0 | 0 |  | 12043 | SCHOEFFLER ENERGY GROUP INC | 0 | 945 | 0 | 0
ttJTrans | 2-4004 | SU |  | SU |  |  | 2025-12-16 |  | 2-4004 | BREAKER RESERVATION | 0 | 0 |  | 21204 | SIEMENS ENERGY, INC. | 0 | 311403.86 | 0 | 0
ttJTrans | 0-4016 | SU |  | SU |  |  | 2025-12-09 |  | 0-4016 | PERMITTING | 0 | 0 |  | 12043 | SCHOEFFLER ENERGY GROUP INC | 0 | 540 | 0 | 0
ttJTrans | 2-4004 | SU |  | SU |  |  | 2025-12-16 |  | 2-4004 | BREAKER RESERVATION | 0 | 0 |  | 21204 | SIEMENS ENERGY, INC. | 0 | 122826.14 | 0 | 0
ttJTrans | 0-4016 | SU |  | SU |  |  | 2026-01-21 |  | 0-4016 | PERMITTING | 0 | 0 |  | 12043 | SCHOEFFLER ENERGY GROUP INC | 0 | 2160 | 0 | 0
ttJTrans | 0-4016 | SU |  | SU |  |  | 2026-02-24 |  | 0-4016 | PERMITTING | 0 | 0 |  | 12043 | SCHOEFFLER ENERGY GROUP INC | 0 | 2736.86 | 0 | 0
ttJTrans | 0-4016 | SU |  | SU |  |  | 2026-02-24 |  | 0-4016 | PERMITTING | 0 | 0 |  | 12043 | SCHOEFFLER ENERGY GROUP INC | 0 | 4215 | 0 | 0
ttJTrans | 0-4016 | SU |  | SU |  |  | 2026-02-02 |  | 0-4016 | PERMITTING | 0 | 0 |  | 12043 | SCHOEFFLER ENERGY GROUP INC | 0 | 2055 | 0 | 0
ttJTrans | 0-4016 | SU |  | SU |  |  | 2026-02-24 |  | 0-4016 | PERMITTING | 0 | 0 |  | 12043 | SCHOEFFLER ENERGY GROUP INC | 0 | 1560 | 0 | 0
ttJTrans | 2-4004 | SU |  | SU |  |  | 2026-03-17 |  | 2-4004 | INCREASE AMOUNT PER MEGAN REDFIELD | 0 | 0 |  | 21204 | SIEMENS ENERGY, INC. | 0 | 433097 | 0 | 0
ttJTrans | 0-4016 | SU |  | SU |  |  | 2026-04-16 |  | 0-4016 | PERMITTING | 0 | 0 |  | 12043 | SCHOEFFLER ENERGY GROUP INC | 0 | 1305 | 0 | 0
ttJTrans | 0-4016 | SU |  | SU |  |  | 2026-04-16 |  | 0-4016 | PERMITTING | 0 | 0 |  | 12043 | SCHOEFFLER ENERGY GROUP INC | 0 | 2355 | 0 | 0
ttJTrans | 0-4017 | OC | MA1010545 | OC | MA1010545 | 2026-03-11 | 2026-05-20 | 1 | 0-4017 | Water: $0.03 per gallon(monthly reading | 1 | 22200 | INVOICE | 21358 | TEXAS GULF COAST AGGREGATES, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4017 | OC | MA1010545 | OC | MA1010545 | 2026-03-11 | 2026-03-12 | 1 | 0-4017 | Water: $0.03 per gallon(monthly reading | 1 | 22200 | INVOICE:ADJ-COMMIT | 21358 | TEXAS GULF COAST AGGREGATES, LLC | 0 | 0 | -871.45 | 0
ttJTrans | 0-4017 | OC | MA1010545 | OC | MA1010545 | 2026-03-11 | 2026-03-12 | 1 | 0-4017 | Water: $0.03 per gallon(monthly reading | 1 | 22200 | PO:COMMIT | 21358 | TEXAS GULF COAST AGGREGATES, LLC | 0 | 0 | 22200 | 0
ttJTrans | 0-4017 | OC |  | OC |  |  | 2026-05-17 |  | 0-4017 | WATER FOR UTILITY TAKEN ON 3/12/26- 5/4/26 | 0 | 0 |  | 21358 | TEXAS GULF COAST AGGREGATES, LLC | 0 | 849.86 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-01-05 |  | 0-4018 | TRAVEL K BELTRAM 11/15/25 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 295.27 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-01-13 |  | 0-4018 | TRAVEL M BRIDGES 1/12/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 705.5 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-01-30 |  | 0-4018 | TRAVEL M BRIDGES 1/12/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 464.45 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-02-18 |  | 0-4018 | TRAVEL W PARKER 2/5/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 169.64 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-02-18 |  | 0-4018 | TRAVEL W PARKER 2/2/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 461.54 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-02-05 |  | 0-4018 | TRAVEL M GONZALEZ 2/1/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20.1 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-02-18 |  | 0-4018 | TRAVEL M GONZALEZ 2/1/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 595.97 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-02-18 |  | 0-4018 | TRAVEL J RION 2/19/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20.1 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-02-25 |  | 0-4018 | TRAVEL J RION 2/26/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20.1 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-02-25 |  | 0-4018 | TRAVEL J STEELMAN 2/26/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 21.46 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-02-25 |  | 0-4018 | ADAM TRAHAN EXPENSE REPORT | 0 | 0 |  | 16913 | TRAHAN, ADAM M. | 0 | 2075 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-12 |  | 0-4018 | TRAVEL E URBINA 3/9/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20.1 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-12 |  | 0-4018 | TRAVEL E URBINA 2/26/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 283.95 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-12 |  | 0-4018 | TRAVEL D DENNISON 2/2/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20.1 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-24 |  | 0-4018 | 25-4001 FEB USE TAX ADJ | 0 | 0 |  |  |  | 0 | -1.36 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-03 |  | 0-4018 | TRAVEL L COOLEY 2/26/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20.1 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-03 |  | 0-4018 | TRAVEL E URBINA 2/26/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20.1 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-05 |  | 0-4018 | BRYAN MCCURLEY EXPENSE REPORT | 0 | 0 |  | 20331 | MCCURLEY, MARCUS BRYAN | 0 | 453.98 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-24 |  | 0-4018 | TRAVEL J BARTLES 3/9/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 629.45 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-17 |  | 0-4018 | TRAVEL J BARTLES 3/12/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 246.71 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-17 |  | 0-4018 | TRAVEL D DENNISON 2/2/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 618.9 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-17 |  | 0-4018 | TRAVEL M MCCURLEY 3/11/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20.1 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-17 |  | 0-4018 | TRAVEL D HOPKINS 3/15/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20.1 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-17 |  | 0-4018 | TRAVEL L BIVENS 3/16/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20.1 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-17 |  | 0-4018 | TRAVEL R FIGUEROA 3/9/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20.1 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-17 |  | 0-4018 | TRAVEL M DUHON 3/9/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 40.2 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-24 |  | 0-4018 | TRAVEL J JULIAN 3/31/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20.1 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-24 |  | 0-4018 | TRAVEL J STEELMAN 3/10/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 40.2 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-24 |  | 0-4018 | TRAVEL D SALDANA 3/17/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20.1 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-24 |  | 0-4018 | TRAVEL D HOPKINS 3/15/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 303.82 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-24 |  | 0-4018 | TRAVEL M MCCURLEY 3/11/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 149.45 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-24 |  | 0-4018 | TRAVEL J BARTLES 3/16/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 937.56 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-24 |  | 0-4018 | TRAVEL J RION 3/9/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 491.07 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-24 |  | 0-4018 | TRAVEL R FIGUEROA 3/9/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 440.43 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-24 |  | 0-4018 | TRAVEL G BIGLER 3/15/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 640.75 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-24 |  | 0-4018 | TRAVEL D SALDANA 3/18/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 440.39 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-24 |  | 0-4018 | TRAVEL M DUHON 3/9/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 133.95 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-24 |  | 0-4018 | TRAVEL L BIVENS 3/9/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 432.32 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-24 |  | 0-4018 | TRAVEL A TREPAGNIER 3/30/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 988.32 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-31 |  | 0-4018 | TRAVEL J RION 3/31/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 794.34 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-31 |  | 0-4018 | TRAVEL A TREPAGNIER 3/30/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 442.37 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-31 |  | 0-4018 | TRAVEL L BIVENS 3/16/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 407.93 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-31 |  | 0-4018 | TRAVEL D SALDANA 3/17/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 137.57 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-31 |  | 0-4018 | TRAVEL D HOPKINS 3/15/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 794.44 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-31 |  | 0-4018 | TRAVEL M DUHON 3/10/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 215.59 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-31 |  | 0-4018 | TRAVEL E URBINA 3/9/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 1107.67 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-31 |  | 0-4018 | TRAVEL A TREPAGNIER 3/16/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 216.26 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-03-31 |  | 0-4018 | TRAVEL L BIVENS 3/30/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 853.59 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-04-01 |  | 0-4018 | CAR RENTAL J BARTLES 3/9/26 | 0 | 0 |  | 18873 | EAN SERVICES, LLC | 0 | 420.71 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-04-01 |  | 0-4018 | CAR RENTALG BIGLER 3/15/26 | 0 | 0 |  | 18873 | EAN SERVICES, LLC | 0 | 673.02 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-04-08 |  | 0-4018 | TRAVEL A TREPAGNIER 4/1/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20.1 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-04-08 |  | 0-4018 | TRAVEL A TREPAGNIER 4/1/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 82.12 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-04-08 |  | 0-4018 | JAMES BARTLES EXPENSE REPORTS | 0 | 0 |  | 19449 | BARTLES, JAMES E. | 0 | 266.72 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-04-15 |  | 0-4018 | TRAVEL P WARE 4/22/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 583.69 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-04-15 |  | 0-4018 | TRAVEL W TREPAGNIER 4/1/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 114.42 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-04-15 |  | 0-4018 | TRAVEL J RION 3/31/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 437.08 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-04-15 |  | 0-4018 | TRAVEL L BIVENS 3/30/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 140.74 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-04-15 |  | 0-4018 | TRAVEL J JULIAN 3/31/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 123.67 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-04-15 |  | 0-4018 | TRAVEL L BIVENS 4/7/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20.1 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-04-10 |  | 0-4018 | ANDREAU TREPAGNIER EXPENSE REPORT | 0 | 0 |  | 13733 | TREPAGNIER, ANDREAU P. | 0 | 9 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-04-10 |  | 0-4018 | ANDREAU TREPAGNIER EXPENSE REPORT | 0 | 0 |  | 13733 | TREPAGNIER, ANDREAU P. | 0 | 182.55 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-04-23 |  | 0-4018 | TRAVEL S SMITH 5/4/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 636.19 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-04-23 |  | 0-4018 | TRAVEL L BIVENS 4/22/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20.1 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-04-23 |  | 0-4018 | TRAVEL L BIVENS 4/7/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 416.33 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-04-30 |  | 0-4018 | TRAVEL P WARE 4/22/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 339.36 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-04-30 |  | 0-4018 | TRAVEL D SALDANA 4/22/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 390.14 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-04-30 |  | 0-4018 | TRAVEL D SALDANA 4/22/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 559.99 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-04-30 |  | 0-4018 | TRAVEL L BARTLES 5/4/26 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 1046.65 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-14 |  | 0-4018 | USFC-I30842095 LATORRENCE BIVENS 05/10/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 3.69 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-19 |  | 0-4018 | USFC-I30872405 SAMUEL WAYNE SMITH 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 2.14 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-14 |  | 0-4018 | USFC-I30791267 LATORRENCE BIVENS 04/28/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 373.9 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-14 |  | 0-4018 | USFC-I30846549 Andreau Trepagnier 05/10/2027 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 0.1 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-14 |  | 0-4018 | USFC-I30842095 LATORRENCE BIVENS 05/10/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 373.4 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-14 |  | 0-4018 | USFC-I30846549 Andreau Trepagnier 05/10/2027 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-14 |  | 0-4018 | USFC-I30842095 LATORRENCE BIVENS 05/10/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 10 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-14 |  | 0-4018 | USFC-I30842095 LATORRENCE BIVENS 05/10/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 355.5 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-14 |  | 0-4018 | USFC-I30839257 Andreau Trepagnier 05/08/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-14 |  | 0-4018 | USFC-I30839257 Andreau Trepagnier 05/08/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 0.1 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-14 |  | 0-4018 | USFC-I30775554 Andreau Trepagnier 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 0.1 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-14 |  | 0-4018 | USFC-I30775554 Andreau Trepagnier 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-14 |  | 0-4018 | USFC-I30833819 PHILLIP R WARE 05/10/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 10 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-14 |  | 0-4018 | USFC-I30833819 PHILLIP R WARE 05/10/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 1124.8 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-19 |  | 0-4018 | USFC-I30872634 John Steelman 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 360.09 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-19 |  | 0-4018 | USFC-I30873004 Andreau Trepagnier 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 516.03 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-19 |  | 0-4018 | USFC-I30873432 Andreau Trepagnier 05/08/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 0.63 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-19 |  | 0-4018 | USFC-I30875404 SAMUEL WAYNE SMITH 05/18/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-19 |  | 0-4018 | USFC-I30875404 SAMUEL WAYNE SMITH 05/18/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 10 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-19 |  | 0-4018 | USFC-I30875404 SAMUEL WAYNE SMITH 05/18/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 764.21 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-19 |  | 0-4018 | USFC-I30873004 Andreau Trepagnier 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 2.58 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-07 |  | 0-4018 | USFC-I30754610 John Steelman 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 0.1 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-07 |  | 0-4018 | USFC-I30675912 JESSIE DEAN RION 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 815.51 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-07 |  | 0-4018 | USFC-I30675912 JESSIE DEAN RION 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 4.23 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-07 |  | 0-4018 | USFC-I30665155 LOYD BARTLES 05/11/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 823.34 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-07 |  | 0-4018 | USFC-I30665155 LOYD BARTLES 05/11/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 10 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-07 |  | 0-4018 | USFC-I30665155 LOYD BARTLES 05/11/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-07 |  | 0-4018 | USFC-I30675912 JESSIE DEAN RION 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 10 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-07 |  | 0-4018 | USFC-I30675912 JESSIE DEAN RION 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-05 |  | 0-4018 | CAR RENTAL J RION 3/31/26 | 0 | 0 |  | 18873 | EAN SERVICES, LLC | 0 | 369.15 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-05 |  | 0-4018 | CAR RENTAL A TREPAGNIER 4/1/26 | 0 | 0 |  | 18873 | EAN SERVICES, LLC | 0 | 283.63 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-05 |  | 0-4018 | COMDATA 4/27/26 (LB) WHATABURGER 168 4/23/26 | 0 | 0 |  | 2300 |  | 0 | 10.95 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-05 |  | 0-4018 | COMDATA 4/27/26 (LB) UBER *TRIP 4/23/26 | 0 | 0 |  | 2300 |  | 0 | 55.96 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-07 |  | 0-4018 | USFC-I30754610 John Steelman 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-07 |  | 0-4018 | USFC-I30749708 ALEXIS PACHECO GONZALEZ 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 0.1 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-07 |  | 0-4018 | USFC-I30678811 WILLIAM MATTHEWS 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 7.78 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-07 |  | 0-4018 | USFC-I30662391 LOYD BARTLES 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | -1011.44 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-07 |  | 0-4018 | USFC-I30662391 LOYD BARTLES 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | -5.06 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-07 |  | 0-4018 | USFC-I30665155 LOYD BARTLES 05/11/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 4.27 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-07 |  | 0-4018 | USFC-I30688245 DAMIAN SALDANA 04/22/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 158.25 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-07 |  | 0-4018 | USFC-I30688245 DAMIAN SALDANA 04/22/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 0.79 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-07 |  | 0-4018 | USFC-I30678811 WILLIAM MATTHEWS 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 1526.4 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-07 |  | 0-4018 | USFC-I30678811 WILLIAM MATTHEWS 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 10 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-07 |  | 0-4018 | USFC-I30739125 LATORRENCE BIVENS 05/01/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 3.61 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-07 |  | 0-4018 | USFC-I30749708 ALEXIS PACHECO GONZALEZ 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-07 |  | 0-4018 | USFC-I30739125 LATORRENCE BIVENS 05/01/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 10 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-07 |  | 0-4018 | USFC-I30701095 JAMES Estel BARTLES 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 0.1 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-07 |  | 0-4018 | USFC-I30739125 LATORRENCE BIVENS 05/01/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 711 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-07 |  | 0-4018 | USFC-I30738246 LATORRENCE BIVENS 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 0.1 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-07 |  | 0-4018 | USFC-I30701095 JAMES Estel BARTLES 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-07 |  | 0-4018 | USFC-I30686785 Andreau Trepagnier 04/28/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 0.1 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-07 |  | 0-4018 | USFC-I30738246 LATORRENCE BIVENS 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-07 |  | 0-4018 | USFC-I30775554 Andreau Trepagnier 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 0.1 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-07 |  | 0-4018 | USFC-I30686785 Andreau Trepagnier 04/28/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-07 |  | 0-4018 | USFC-I30775554 Andreau Trepagnier 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-07 |  | 0-4018 | USFC-I30660559 LATORRENCE BIVENS 04/28/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-07 |  | 0-4018 | USFC-I30660559 LATORRENCE BIVENS 04/28/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 0.1 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-07 |  | 0-4018 | USFC-I30689819 LATORRENCE BIVENS 04/22/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 1.55 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-07 |  | 0-4018 | USFC-I30689819 LATORRENCE BIVENS 04/22/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 310.21 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-07 |  | 0-4018 | USFC-I30678811 WILLIAM MATTHEWS 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-14 |  | 0-4018 | PHILLIP WARE EXPENSE REPORT | 0 | 0 |  | 21107 | WARE, PHILLIP R. | 0 | 168.87 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-14 |  | 0-4018 | PHILLIP WARE EXPENSE REPORT | 0 | 0 |  | 21107 | WARE, PHILLIP R. | 0 | 214.38 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-14 |  | 0-4018 | USFC-I30833819 PHILLIP R WARE 05/10/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 5.77 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-14 |  | 0-4018 | USFC-I30833819 PHILLIP R WARE 05/10/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-14 |  | 0-4018 | USFC-I30791350 Andreau Trepagnier 04/28/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 362.43 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-19 |  | 0-4018 | USFC-I30872405 SAMUEL WAYNE SMITH 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 427.46 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-19 |  | 0-4018 | USFC-I30871665 WILLIAM MATTHEWS 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 1.97 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-19 |  | 0-4018 | USFC-I30871665 WILLIAM MATTHEWS 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 393.18 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-19 |  | 0-4018 | USFC-I30871684 JESSIE DEAN RION 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 2.07 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-19 |  | 0-4018 | USFC-I30871684 JESSIE DEAN RION 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 414.68 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-19 |  | 0-4018 | USFC-I30873076 LATORRENCE BIVENS 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 2.35 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-19 |  | 0-4018 | USFC-I30873076 LATORRENCE BIVENS 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 470.56 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-19 |  | 0-4018 | USFC-I30872976 JAMES Estel BARTLES 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 2.81 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-19 |  | 0-4018 | USFC-I30872976 JAMES Estel BARTLES 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 562.12 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-19 |  | 0-4018 | USFC-I30872634 John Steelman 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 1.8 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-19 |  | 0-4018 | USFC-I30873432 Andreau Trepagnier 05/08/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 125.48 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-19 |  | 0-4018 | USFC-I30873042 ALEXIS PACHECO GONZALEZ 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 2.51 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-19 |  | 0-4018 | USFC-I30873042 ALEXIS PACHECO GONZALEZ 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 501.27 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-19 |  | 0-4018 | USFC-I30872890 LOYD BARTLES 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 2.44 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-19 |  | 0-4018 | USFC-I30872890 LOYD BARTLES 05/04/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 488.16 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-19 |  | 0-4018 | USFC-I30937917 SAMUEL WAYNE SMITH 05/25/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 0.18 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-19 |  | 0-4018 | USFC-I30937917 SAMUEL WAYNE SMITH 05/25/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 35 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-19 |  | 0-4018 | USFC-I30929536 Jessie Dean Rion 05/17/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 0.1 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-19 |  | 0-4018 | USFC-I30929536 Jessie Dean Rion 05/17/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 20 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-19 |  | 0-4018 | USFC-I30875404 SAMUEL WAYNE SMITH 05/18/2026 | 0 | 0 |  | 20542 | CORPORATE TRAVELER | 0 | 3.97 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-19 |  | 0-4018 | JAMES BARTLES EXPENSE REPORT | 0 | 0 |  | 19449 | BARTLES, JAMES E. | 0 | 227.2 | 0 | 0
ttJTrans | 0-4018 | OC |  | OC |  |  | 2026-05-19 |  | 0-4018 | ALEXIS GONZALEZ EXPENSE REPORT | 0 | 0 |  | 21421 | GONZALEZ, ALEXIS P. | 0 | 217.66 | 0 | 0
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-16 |  | 0-4005 | PR P2COST 000285 (PR) Summary | 0 | 0 |  |  |  | 0 | 555.17 | 0 | 5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-16 |  | 0-4005 | PR P2COST 000285 (PR) Summary | 0 | 0 |  |  |  | 0 | 555.17 | 0 | 5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-16 |  | 0-4005 | PR P2COST 000285 (PR) Summary | 0 | 0 |  |  |  | 0 | 111.03 | 0 | 1
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-16 |  | 0-4005 | PR P2COST 000285 (PR) Summary | 0 | 0 |  |  |  | 0 | 888.27 | 0 | 8
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-16 |  | 0-4005 | PR P2COST 000285 (PR) Summary | 0 | 0 |  |  |  | 0 | 555.22 | 0 | 5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-16 |  | 0-4005 | PR P2COST 000285 (PR) Summary | 0 | 0 |  |  |  | 0 | 555.17 | 0 | 5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-16 |  | 0-4005 | PR P2COST 000285 (PR) Summary | 0 | 0 |  |  |  | 0 | 555.17 | 0 | 5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-02 |  | 0-4005 | PR P2COST 000284 (PR) Summary | 0 | 0 |  |  |  | 0 | 209.46 | 0 | 2
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-02 |  | 0-4005 | PR P2COST 000284 (PR) Summary | 0 | 0 |  |  |  | 0 | 523.67 | 0 | 5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-02-02 |  | 0-4005 | PR P2COST 000284 (PR) Summary | 0 | 0 |  |  |  | 0 | 418.93 | 0 | 4
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-02 |  | 0-4005 | PR P2COST 000286 (PR) Summary | 0 | 0 |  |  |  | 0 | 96.79 | 0 | 1
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-02 |  | 0-4005 | PR P2COST 000286 (PR) Summary | 0 | 0 |  |  |  | 0 | 96.79 | 0 | 1
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-02 |  | 0-4005 | PR P2COST 000286 (PR) Summary | 0 | 0 |  |  |  | 0 | 387.11 | 0 | 4
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-02 |  | 0-4005 | PR P2COST 000286 (PR) Summary | 0 | 0 |  |  |  | 0 | 96.79 | 0 | 1
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-02 |  | 0-4005 | PR P2COST 000286 (PR) Summary | 0 | 0 |  |  |  | 0 | 483.9 | 0 | 5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-02 |  | 0-4005 | PR P2COST 000286 (PR) Summary | 0 | 0 |  |  |  | 0 | 483.9 | 0 | 5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-02 |  | 0-4005 | PR P2COST 000286 (PR) Summary | 0 | 0 |  |  |  | 0 | 193.55 | 0 | 2
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-02 |  | 0-4005 | PR P2COST 000286 (PR) Summary | 0 | 0 |  |  |  | 0 | 193.55 | 0 | 2
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-16 |  | 0-4005 | PR P2COST 000287 (PR) Summary | 0 | 0 |  |  |  | 0 | 381.26 | 0 | 4
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-16 |  | 0-4005 | PR P2COST 000287 (PR) Summary | 0 | 0 |  |  |  | 0 | 190.63 | 0 | 2
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-16 |  | 0-4005 | PR P2COST 000287 (PR) Summary | 0 | 0 |  |  |  | 0 | 381.26 | 0 | 4
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-16 |  | 0-4005 | PR P2COST 000287 (PR) Summary | 0 | 0 |  |  |  | 0 | 95.32 | 0 | 1
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-16 |  | 0-4005 | PR P2COST 000287 (PR) Summary | 0 | 0 |  |  |  | 0 | 95.32 | 0 | 1
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-16 |  | 0-4005 | PR P2COST 000287 (PR) Summary | 0 | 0 |  |  |  | 0 | 95.32 | 0 | 1
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-30 |  | 0-4005 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 203.47 | 0 | 2
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-30 |  | 0-4005 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 406.91 | 0 | 4
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-30 |  | 0-4005 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 305.18 | 0 | 3
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-30 |  | 0-4005 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 203.47 | 0 | 2
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-30 |  | 0-4005 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 508.66 | 0 | 5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-30 |  | 0-4005 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 305.16 | 0 | 3
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-30 |  | 0-4005 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 305.18 | 0 | 3
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-30 |  | 0-4005 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 203.47 | 0 | 2
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-30 |  | 0-4005 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 101.73 | 0 | 1
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-03-30 |  | 0-4005 | PR P2COST 000288 (PR) Summary | 0 | 0 |  |  |  | 0 | 406.91 | 0 | 4
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-14 |  | 0-4005 | PR P2COST 000289 (PR) Summary | 0 | 0 |  |  |  | 0 | 388.62 | 0 | 4
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-14 |  | 0-4005 | PR P2COST 000289 (PR) Summary | 0 | 0 |  |  |  | 0 | 194.31 | 0 | 2
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-14 |  | 0-4005 | PR P2COST 000289 (PR) Summary | 0 | 0 |  |  |  | 0 | 194.31 | 0 | 2
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-14 |  | 0-4005 | PR P2COST 000289 (PR) Summary | 0 | 0 |  |  |  | 0 | 485.79 | 0 | 5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-14 |  | 0-4005 | PR P2COST 000289 (PR) Summary | 0 | 0 |  |  |  | 0 | 485.79 | 0 | 5
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-14 |  | 0-4005 | PR P2COST 000289 (PR) Summary | 0 | 0 |  |  |  | 0 | 194.31 | 0 | 2
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-27 |  | 0-4005 | PR P2COST 000290 (PR) Summary | 0 | 0 |  |  |  | 0 | 193.06 | 0 | 2
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-27 |  | 0-4005 | PR P2COST 000290 (PR) Summary | 0 | 0 |  |  |  | 0 | 193.07 | 0 | 2
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-27 |  | 0-4005 | PR P2COST 000290 (PR) Summary | 0 | 0 |  |  |  | 0 | 193.06 | 0 | 2
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-27 |  | 0-4005 | PR P2COST 000290 (PR) Summary | 0 | 0 |  |  |  | 0 | 193.06 | 0 | 2
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-27 |  | 0-4005 | PR P2COST 000290 (PR) Summary | 0 | 0 |  |  |  | 0 | 96.52 | 0 | 1
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-04-27 |  | 0-4005 | PR P2COST 000290 (PR) Summary | 0 | 0 |  |  |  | 0 | 193.06 | 0 | 2
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-08 |  | 0-4005 | COST CODE TRANSFER 25-4005 | 0 | 0 |  |  |  | 0 | -13092.02 | 0 | -128
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-12 |  | 0-4005 | PR P2COST 000292 (PR) Summary | 0 | 0 |  |  |  | 0 | 194.8 | 0 | 2
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-12 |  | 0-4005 | PR P2COST 000292 (PR) Summary | 0 | 0 |  |  |  | 0 | 97.4 | 0 | 1
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-12 |  | 0-4005 | PR P2COST 000292 (PR) Summary | 0 | 0 |  |  |  | 0 | 97.41 | 0 | 1
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-12 |  | 0-4005 | PR P2COST 000292 (PR) Summary | 0 | 0 |  |  |  | 0 | 97.4 | 0 | 1
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-12 |  | 0-4005 | PR P2COST 000292 (PR) Summary | 0 | 0 |  |  |  | 0 | 97.41 | 0 | 1
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-12 |  | 0-4005 | PR P2COST 000292 (PR) Summary | 0 | 0 |  |  |  | 0 | 194.8 | 0 | 2
ttJTrans | 0-4005 | LA |  | LA |  |  | 2026-05-12 |  | 0-4005 | PR P2COST 000292 (PR) Summary | 0 | 0 |  |  |  | 0 | 194.8 | 0 | 2
ttJTrans | 0-4024 | OC | MA1009670 | OC | MA1009670 | 2026-01-09 | 2026-01-09 | 2 | 0-4024 | Development Review Project 00023 WA3 TA159 | 1 | 18870 | PO:COMMIT | 21272 | SCHEIBE CONSULTING LLC | 0 | 0 | 18870 | 0
ttJTrans | 0-4024 | OC | MA1009670 | OC | MA1009670 | 2026-01-09 | 2026-01-09 | 2 | 0-4024 | Development Review Project 00023 WA3 TA159 | 1 | 18870 | INVOICE:ADJ-COMMIT | 21272 | SCHEIBE CONSULTING LLC | 0 | 0 | -18870 | 0
ttJTrans | 0-4024 | OC | MA1009670 | OC | MA1009670 | 2026-01-09 | 2026-01-09 | 1 | 0-4024 | Development Review Project 00023 WA3 TA159 | 1 | 3940.5 | INVOICE:ADJ-COMMIT | 21272 | SCHEIBE CONSULTING LLC | 0 | 0 | -3940.5 | 0
ttJTrans | 0-4024 | OC | MA1009670 | OC | MA1009670 | 2026-01-09 | 2026-01-09 | 1 | 0-4024 | Development Review Project 00023 WA3 TA159 | 1 | 3940.5 | PO:COMMIT | 21272 | SCHEIBE CONSULTING LLC | 0 | 0 | 3940.5 | 0
ttJTrans | 0-4024 | OC | MA1009670 | OC | MA1009670 | 2026-01-09 | 2026-01-12 | 2 | 0-4024 | Development Review Project 00023 WA3 TA159 | 1 | 18870 | INVOICE | 21272 | SCHEIBE CONSULTING LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4024 | OC | MA1009670 | OC | MA1009670 | 2026-01-09 | 2026-01-12 | 1 | 0-4024 | Development Review Project 00023 WA3 TA159 | 1 | 3940.5 | INVOICE | 21272 | SCHEIBE CONSULTING LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 20 | 0-4024 | 100FT REEL | 1 | 31.95 | INVOICE:ADJ-COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | -31.95 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 6 | 0-4024 | TIP 3/8'' PROBE ROD | 2 | 26.64 | INVOICE:ADJ-COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | -26.64 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 16 | 0-4024 | GREEN FLAGGING | 6 | 13.72 | INVOICE:ADJ-COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | -13.72 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 13 | 0-4024 | ORANGE FLAGGING | 6 | 13.72 | INVOICE:ADJ-COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | -13.72 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 5 | 0-4024 | PROBE ROD HEX CARBONSTEEL 3/8''X3' | 2 | 28.19 | INVOICE:ADJ-COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | -28.19 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 7 | 0-4024 | PROBE ROD MIGHTY ROUNDTIP 3/8'' | 2 | 14.52 | INVOICE:ADJ-COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | -14.52 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 10 | 0-4024 | GREEN SPRAY PAINT | 6 | 39.16 | INVOICE:ADJ-COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | -39.16 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 2 | 0-4024 | PROBE ROD | 2 | 154.71 | INVOICE:ADJ-COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | -154.71 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-02-12 | 4 | 0-4024 | PROBE ROD MIGHTY 6'EXTENSION | 1 | 42.31 | INVOICE | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 0 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 14 | 0-4024 | RED FLAGGING | 6 | 13.72 | INVOICE:ADJ-COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | -13.72 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 4 | 0-4024 | PROBE ROD MIGHTY 6'EXTENSION | 1 | 42.31 | INVOICE:ADJ-COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | -42.31 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 11 | 0-4024 | BLUE SPRAY PAINT | 6 | 39.16 | INVOICE:ADJ-COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | -39.16 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 3 | 0-4024 | PROBE ROD MIGHTY 4'EXTENSION | 1 | 41.72 | INVOICE:ADJ-COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | -41.72 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 15 | 0-4024 | BLUE FLAGGING | 6 | 13.72 | INVOICE:ADJ-COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | -13.72 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 1 | 0-4024 | LATHES 3/8 X 1-1/2 X 4850 PER BUNDLE | 8 | 410.61 | INVOICE:ADJ-COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | -410.61 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 9 | 0-4024 | RED SPRAY PAINT | 6 | 39.16 | INVOICE:ADJ-COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | -39.16 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 22 | 0-4024 | SPADE SHOVEL | 2 | 49.22 | PO:COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 49.22 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 21 | 0-4024 | ROUND SHOVEL | 2 | 33.5 | PO:COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 33.5 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 20 | 0-4024 | 100FT REEL | 1 | 31.95 | PO:COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 31.95 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 8 | 0-4024 | ORANGE SPRAY PAINT | 6 | 38.1 | INVOICE:ADJ-COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | -38.1 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 17 | 0-4024 | YELLOW FLAGGING | 6 | 13.92 | INVOICE:ADJ-COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | -13.92 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 18 | 0-4024 | BLACK MARKERS | 12 | 30.37 | INVOICE:ADJ-COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | -30.37 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 12 | 0-4024 | YELLOW SPRAY PAINT | 6 | 39.16 | INVOICE:ADJ-COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | -39.16 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-02-12 | 1 | 0-4024 | LATHES 3/8 X 1-1/2 X 4850 PER BUNDLE | 8 | 410.61 | INVOICE | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 0 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 22 | 0-4024 | SPADE SHOVEL | 2 | 49.22 | INVOICE:ADJ-COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | -49.22 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 19 | 0-4024 | 25FT TAPE MEASURE | 2 | 27.97 | INVOICE:ADJ-COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | -27.97 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 23 | 0-4024 | YELLOW FLAGGING STAKE PINS | 1 | 12.34 | INVOICE:ADJ-COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | -12.34 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-02-12 | 16 | 0-4024 | GREEN FLAGGING | 6 | 13.72 | INVOICE | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 0 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-02-12 | 5 | 0-4024 | PROBE ROD HEX CARBONSTEEL 3/8''X3' | 2 | 28.19 | INVOICE | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 0 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 21 | 0-4024 | ROUND SHOVEL | 2 | 33.5 | INVOICE:ADJ-COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | -33.5 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-02-12 | 22 | 0-4024 | SPADE SHOVEL | 2 | 49.22 | INVOICE | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 0 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 23 | 0-4024 | YELLOW FLAGGING STAKE PINS | 1 | 12.34 | PO:COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 12.34 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 16 | 0-4024 | GREEN FLAGGING | 6 | 13.72 | PO:COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 13.72 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 17 | 0-4024 | YELLOW FLAGGING | 6 | 13.92 | PO:COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 13.92 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 18 | 0-4024 | BLACK MARKERS | 12 | 30.37 | PO:COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 30.37 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 19 | 0-4024 | 25FT TAPE MEASURE | 2 | 27.97 | PO:COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 27.97 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 13 | 0-4024 | ORANGE FLAGGING | 6 | 13.72 | PO:COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 13.72 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 14 | 0-4024 | RED FLAGGING | 6 | 13.72 | PO:COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 13.72 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 15 | 0-4024 | BLUE FLAGGING | 6 | 13.72 | PO:COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 13.72 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 9 | 0-4024 | RED SPRAY PAINT | 6 | 39.16 | PO:COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 39.16 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 10 | 0-4024 | GREEN SPRAY PAINT | 6 | 39.16 | PO:COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 39.16 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 11 | 0-4024 | BLUE SPRAY PAINT | 6 | 39.16 | PO:COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 39.16 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 12 | 0-4024 | YELLOW SPRAY PAINT | 6 | 39.16 | PO:COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 39.16 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 5 | 0-4024 | PROBE ROD HEX CARBONSTEEL 3/8''X3' | 2 | 28.19 | PO:COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 28.19 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 6 | 0-4024 | TIP 3/8'' PROBE ROD | 2 | 26.64 | PO:COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 26.64 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 7 | 0-4024 | PROBE ROD MIGHTY ROUNDTIP 3/8'' | 2 | 14.52 | PO:COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 14.52 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 8 | 0-4024 | ORANGE SPRAY PAINT | 6 | 38.1 | PO:COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 38.1 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 1 | 0-4024 | LATHES 3/8 X 1-1/2 X 4850 PER BUNDLE | 8 | 410.61 | PO:COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 410.61 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 2 | 0-4024 | PROBE ROD | 2 | 154.71 | PO:COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 154.71 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 3 | 0-4024 | PROBE ROD MIGHTY 4'EXTENSION | 1 | 41.72 | PO:COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 41.72 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-01-31 | 4 | 0-4024 | PROBE ROD MIGHTY 6'EXTENSION | 1 | 42.31 | PO:COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 42.31 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-02-12 | 20 | 0-4024 | 100FT REEL | 1 | 31.95 | INVOICE | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 0 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-02-12 | 6 | 0-4024 | TIP 3/8'' PROBE ROD | 2 | 26.64 | INVOICE | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 0 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-02-12 | 23 | 0-4024 | YELLOW FLAGGING STAKE PINS | 1 | 12.34 | INVOICE | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 0 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-02-12 | 3 | 0-4024 | PROBE ROD MIGHTY 4'EXTENSION | 1 | 41.72 | INVOICE | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 0 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-02-12 | 11 | 0-4024 | BLUE SPRAY PAINT | 6 | 39.16 | INVOICE | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 0 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-02-12 | 17 | 0-4024 | YELLOW FLAGGING | 6 | 13.92 | INVOICE | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 0 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-02-12 | 8 | 0-4024 | ORANGE SPRAY PAINT | 6 | 38.1 | INVOICE | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 0 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-02-12 | 12 | 0-4024 | YELLOW SPRAY PAINT | 6 | 39.16 | INVOICE | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 0 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-02-12 | 21 | 0-4024 | ROUND SHOVEL | 2 | 33.5 | INVOICE | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 0 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-02-12 | 15 | 0-4024 | BLUE FLAGGING | 6 | 13.72 | INVOICE | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 0 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-02-12 | 9 | 0-4024 | RED SPRAY PAINT | 6 | 39.16 | INVOICE | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 0 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-02-12 | 14 | 0-4024 | RED FLAGGING | 6 | 13.72 | INVOICE | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 0 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-02-12 | 2 | 0-4024 | PROBE ROD | 2 | 154.71 | INVOICE | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 0 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-02-12 | 10 | 0-4024 | GREEN SPRAY PAINT | 6 | 39.16 | INVOICE | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 0 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-02-12 | 7 | 0-4024 | PROBE ROD MIGHTY ROUNDTIP 3/8'' | 2 | 14.52 | INVOICE | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 0 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-02-12 | 19 | 0-4024 | 25FT TAPE MEASURE | 2 | 27.97 | INVOICE | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 0 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-02-12 | 13 | 0-4024 | ORANGE FLAGGING | 6 | 13.72 | INVOICE | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 0 | 0
ttJTrans | 0-4024 | OC | MA1009906 | OC | MA1009906 | 2026-01-31 | 2026-02-12 | 18 | 0-4024 | BLACK MARKERS | 12 | 30.37 | INVOICE | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 0 | 0
ttJTrans | 0-4024 | OC | MA1009914 | OC | MA1009914 | 2026-02-02 | 2026-02-02 | 1 | 0-4024 | 48" HEAVY DUTY LATH BAG | 1 | 109.3 | INVOICE:ADJ-COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | -109.3 | 0
ttJTrans | 0-4024 | OC | MA1009914 | OC | MA1009914 | 2026-02-02 | 2026-02-12 | 1 | 0-4024 | 48" HEAVY DUTY LATH BAG | 1 | 109.3 | INVOICE | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 0 | 0
ttJTrans | 0-4024 | OC | MA1009914 | OC | MA1009914 | 2026-02-02 | 2026-02-02 | 1 | 0-4024 | 48" HEAVY DUTY LATH BAG | 1 | 109.3 | PO:COMMIT | 13089 | PSS INDUSTRIAL GROUP | 0 | 0 | 109.3 | 0
ttJTrans | 0-4024 | OC | MA1010087 | OC | MA1010087 | 2026-02-13 | 2026-02-23 | 1 | 0-4024 | Review of performance/capacity testing | 1 | 1623.38 | PO:COMMIT | 19943 | HIGH NOON CONSULTING INC. | 0 | 0 | 1623.38 | 0
ttJTrans | 0-4024 | OC | MA1010087 | OC | MA1010087 | 2026-02-13 | 2026-02-23 | 1 | 0-4024 | Review of performance/capacity testing | 1 | 1623.38 | INVOICE:ADJ-COMMIT | 19943 | HIGH NOON CONSULTING INC. | 0 | 0 | -1623.38 | 0
ttJTrans | 0-4024 | OC | MA1010087 | OC | MA1010087 | 2026-02-13 | 2026-03-31 | 1 | 0-4024 | Review of performance/capacity testing | 1 | 1623.38 | INVOICE | 19943 | HIGH NOON CONSULTING INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4024 | OC |  | OC |  |  | 2025-10-07 |  | 0-4024 | RECLASS 250604282,STELLAVISE INC,SUNROPER THERMAL MODELING FOR MV TRENCHES,04/30/25,WHC003 | 0 | 0 |  |  |  | 0 | 5000 | 0 | 0
ttJTrans | 0-4024 | OC |  | OC |  |  | 2026-01-12 |  | 0-4024 | DEVELOPMENT REVIEW I-00023-3-159 & 00023-3-159A | 0 | 0 |  | 21272 | SCHEIBE CONSULTING LLC | 0 | 17000 | 0 | 0
ttJTrans | 0-4024 | OC |  | OC |  |  | 2026-01-12 |  | 0-4024 | DEVELOPMENT REVIEW I-00023-3-159 & 00023-3-159A | 0 | 0 |  | 21272 | SCHEIBE CONSULTING LLC | 0 | 3550 | 0 | 0
ttJTrans | 0-4024 | OC |  | OC |  |  | 2026-01-19 |  | 0-4024 | STANDARD MAP REQUEST & SIGNATURE PROCESS | 0 | 0 |  | 11293 | CENTERPOINT ENERGY | 0 | 100 | 0 | 0
ttJTrans | 0-4024 | OC |  | OC |  |  | 2026-02-12 |  | 0-4024 | LATHES/ PROBE ROD/ PROBE TIP/ PAINT/ FLAGGING TAPE/ MARKERS/ TAPE MEASURE/ SHOVEL/FLAGGING STAKE | 0 | 0 |  | 13089 | PSS INDUSTRIAL GROUP | 0 | 47.76 | 0 | 0
ttJTrans | 0-4024 | OC |  | OC |  |  | 2026-02-12 |  | 0-4024 | LATHES/ PROBE ROD/ PROBE TIP/ PAINT/ FLAGGING TAPE/ MARKERS/ TAPE MEASURE/ SHOVEL/FLAGGING STAKE | 0 | 0 |  | 13089 | PSS INDUSTRIAL GROUP | 0 | 1075.36 | 0 | 0
ttJTrans | 0-4024 | OC |  | OC |  |  | 2026-02-12 |  | 0-4024 | LATHE BAG | 0 | 0 |  | 13089 | PSS INDUSTRIAL GROUP | 0 | 105.11 | 0 | 0
ttJTrans | 0-4024 | OC |  | OC |  |  | 2026-03-24 |  | 0-4024 | 25-4001 FEB USE TAX ADJ | 0 | 0 |  |  |  | 0 | -0.18 | 0 | 0
ttJTrans | 0-4024 | OC |  | OC |  |  | 2026-03-31 |  | 0-4024 | Engineering Work SUNROPER | 0 | 0 |  | 19943 | HIGH NOON CONSULTING INC. | 0 | 1462.5 | 0 | 0
ttJTrans | 0-4024 | SU | SO1000213 | SU | SO1000213 | 2025-10-06 | 2025-12-11 | 1 | 0-4024 | EARLY LIMITED FIBER DESIGN | 1 | 12810 | PO:COMMIT | 19065 | KIMLEY-HORN AND ASSOCIATES, INC. | 0 | 0 | 12810 | 0
ttJTrans | 0-4024 | SU | SO1000213 | SU | SO1000213 | 2026-02-06 | 2026-03-02 | 2 | 0-4024 | CIVIL ENGINEERING | 1 | 1176385 | CERTIFICATE | 19065 | KIMLEY-HORN AND ASSOCIATES, INC. | 0 | 0 | -112994.88 | 0
ttJTrans | 0-4024 | SU | SO1000213 | SU | SO1000213 | 2026-02-06 | 2026-03-02 | 2 | 0-4024 | CIVIL ENGINEERING | 1 | 1176385 | PO:COMMIT | 19065 | KIMLEY-HORN AND ASSOCIATES, INC. | 0 | 0 | 1176385 | 0
ttJTrans | 0-4024 | SU | SO1000213 | SU | SO1000213 | 2026-02-06 | 2026-03-02 | 2 | 0-4024 | CIVIL ENGINEERING | 1 | 1176385 | CERTIFICATE | 19065 | KIMLEY-HORN AND ASSOCIATES, INC. | 0 | 0 | -726992.1 | 0
ttJTrans | 0-4024 | SU | SO1000213 | SU | SO1000213 | 2026-02-06 | 2026-03-02 | 2 | 0-4024 | CIVIL ENGINEERING | 1 | 1176385 | CERTIFICATE | 19065 | KIMLEY-HORN AND ASSOCIATES, INC. | 0 | 0 | -231700.87 | 0
ttJTrans | 0-4024 | SU | SO1000213 | SU | SO1000213 | 2025-10-06 | 2025-12-11 | 1 | 0-4024 | EARLY LIMITED FIBER DESIGN | 1 | 12810 | CERTIFICATE | 19065 | KIMLEY-HORN AND ASSOCIATES, INC. | 0 | 0 | -12810 | 0
ttJTrans | 0-4024 | SU | SO1000213 | SU | SO1000213 | 2026-03-04 | 2026-03-10 | 3 | 0-4024 | CHANGE ORDER CO01 ADJUSTMENT - ATTACHED | 1 | 10675 | PO:COMMIT | 19065 | KIMLEY-HORN AND ASSOCIATES, INC. | 0 | 0 | 10675 | 0
ttJTrans | 0-4024 | SU | SO1000221 | SU | SO1000221 | 2025-10-09 | 2025-11-06 | 1 | 0-4024 | ENGINEERING | 1 | 120672.34 | CERTIFICATE | 13296 | TERRACON CONSULTANTS, INC | 0 | 0 | -52681.12 | 0
ttJTrans | 0-4024 | SU | SO1000221 | SU | SO1000221 | 2025-10-09 | 2025-11-06 | 1 | 0-4024 | ENGINEERING | 1 | 120672.34 | CERTIFICATE | 13296 | TERRACON CONSULTANTS, INC | 0 | 0 | -54004.83 | 0
ttJTrans | 0-4024 | SU | SO1000221 | SU | SO1000221 | 2025-10-09 | 2025-11-06 | 1 | 0-4024 | ENGINEERING | 1 | 120672.34 | CERTIFICATE | 13296 | TERRACON CONSULTANTS, INC | 0 | 0 | -13986.39 | 0
ttJTrans | 0-4024 | SU | SO1000221 | SU | SO1000221 | 2025-10-09 | 2025-11-06 | 1 | 0-4024 | ENGINEERING | 1 | 120672.34 | PO:COMMIT | 13296 | TERRACON CONSULTANTS, INC | 0 | 0 | 120672.34 | 0
ttJTrans | 0-4024 | SU | SO1000221 | SU | SO1000221 | 2026-04-13 | 2026-04-20 | 2 | 0-4024 | CHANGE ORDER 01 ADJUSTMENT - ATTACHED | 1 | 108281.86 | PO:COMMIT | 13296 | TERRACON CONSULTANTS, INC | 0 | 0 | 108281.86 | 0
ttJTrans | 0-4024 | SU |  | SU |  |  | 2025-12-16 |  | 0-4024 | EARLY LIMITED FIBER DESIGN | 0 | 0 |  | 19065 | KIMLEY-HORN AND ASSOCIATES, INC. | 0 | 12000 | 0 | 0
ttJTrans | 0-4024 | SU |  | SU |  |  | 2026-01-21 |  | 0-4024 | ENGINEERING | 0 | 0 |  | 13296 | TERRACON CONSULTANTS, INC | 0 | 50590 | 0 | 0
ttJTrans | 0-4024 | SU |  | SU |  |  | 2026-02-24 |  | 0-4024 | ENGINEERING | 0 | 0 |  | 13296 | TERRACON CONSULTANTS, INC | 0 | 49350 | 0 | 0
ttJTrans | 0-4024 | SU |  | SU |  |  | 2026-03-05 |  | 0-4024 | CIVIL ENGINEERING | 0 | 0 |  | 19065 | KIMLEY-HORN AND ASSOCIATES, INC. | 0 | 681023.04 | 0 | 0
ttJTrans | 0-4024 | SU |  | SU |  |  | 2026-03-17 |  | 0-4024 | CIVIL ENGINEERING | 0 | 0 |  | 19065 | KIMLEY-HORN AND ASSOCIATES, INC. | 0 | 217050 | 0 | 0
ttJTrans | 0-4024 | SU |  | SU |  |  | 2026-05-04 |  | 0-4024 | ENGINEERING | 0 | 0 |  | 13296 | TERRACON CONSULTANTS, INC | 0 | 13102 | 0 | 0
ttJTrans | 0-4024 | SU |  | SU |  |  | 2026-05-15 |  | 0-4024 | CIVIL ENGINEERING | 0 | 0 |  | 19065 | KIMLEY-HORN AND ASSOCIATES, INC. | 0 | 105850 | 0 | 0
ttJTrans | 0-4027 | LA |  | LA |  |  | 2025-11-20 |  | 0-4027 | PR P0COST 000503 (PR) Summary | 0 | 0 |  |  |  | 0 | 1818.43 | 0 | 40
ttJTrans | 0-4027 | LA |  | LA |  |  | 2026-02-01 |  | 0-4027 | 2025 AP ACCRUAL SMJV EMP COST -CHG TO PROJECTS | 0 | 0 |  |  |  | 0 | 2110 | 0 | 0
ttJTrans | 0-4027 | LA |  | LA |  |  | 2026-05-08 |  | 0-4027 | COST CODE TRANSFER 25-4005 | 0 | 0 |  |  |  | 0 | -3928.43 | 0 | -40
ttJTrans | 0-4027 | MA | MA1008600 | MA | MA1008600 | 2025-10-21 | 2025-10-21 | 3 | 0-4027 | 7210603 CEMENT LOW VOC QT #99 | 1 | 18.84 | INVOICE:ADJ-COMMIT | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | -18.84 | 0
ttJTrans | 0-4027 | MA | MA1008600 | MA | MA1008600 | 2025-10-21 | 2025-12-23 | 7 | 0-4027 | CUR 670 SCREW TYPE TELESCOPING REEL STAND - | 2 | 826.55 | INVOICE | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4027 | MA | MA1008600 | MA | MA1008600 | 2025-10-21 | 2025-10-21 | 1 | 0-4027 | 012ZU4-T4F22D20 12-F OS2 LT ALTOS BINDERLESS | 600 | 279.72 | INVOICE:ADJ-COMMIT | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | -279.72 | 0
ttJTrans | 0-4027 | MA | MA1008600 | MA | MA1008600 | 2025-10-21 | 2025-12-23 | 8 | 0-4027 | CUR 671 SPINDLE FOR MEDIUM REEL STAND | 1 | 490.09 | INVOICE | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4027 | MA | MA1008600 | MA | MA1008600 | 2025-10-21 | 2025-11-25 | 2 | 0-4027 | A53BE12 1 1/2 UL SCH-80 10'BE | 600 | 765.9 | INVOICE | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4027 | MA | MA1008600 | MA | MA1008600 | 2025-10-21 | 2025-11-24 | 6 | 0-4027 | 3M™ Adhesive Sealant 760 UV, Black, 290 mL | 12 | 246.69 | INVOICE | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4027 | MA | MA1008600 | MA | MA1008600 | 2025-10-21 | 2025-10-21 | 1 | 0-4027 | 012ZU4-T4F22D20 12-F OS2 LT ALTOS BINDERLESS | 600 | 279.72 | PO:COMMIT | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | 279.72 | 0
ttJTrans | 0-4027 | MA | MA1008600 | MA | MA1008600 | 2025-10-21 | 2025-10-21 | 6 | 0-4027 | 3M™ Adhesive Sealant 760 UV, Black, 290 mL | 12 | 246.69 | PO:COMMIT | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | 246.69 | 0
ttJTrans | 0-4027 | MA | MA1008600 | MA | MA1008600 | 2025-10-21 | 2025-10-21 | 5 | 0-4027 | 5144007 1 1/2 UL END BELL | 4 | 14.3 | PO:COMMIT | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | 14.3 | 0
ttJTrans | 0-4027 | MA | MA1008600 | MA | MA1008600 | 2025-10-21 | 2025-10-21 | 4 | 0-4027 | 5121007 1 1/2 UL80 45 BND STD R | 4 | 14.3 | PO:COMMIT | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | 14.3 | 0
ttJTrans | 0-4027 | MA | MA1008600 | MA | MA1008600 | 2025-10-21 | 2025-10-21 | 3 | 0-4027 | 7210603 CEMENT LOW VOC QT #99 | 1 | 18.84 | PO:COMMIT | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | 18.84 | 0
ttJTrans | 0-4027 | MA | MA1008600 | MA | MA1008600 | 2025-10-21 | 2025-10-21 | 13 | 0-4027 | 6" Wide Detectable Warning Burial Tape | 4 | 313.42 | PO:COMMIT | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | 313.42 | 0
ttJTrans | 0-4027 | MA | MA1008600 | MA | MA1008600 | 2025-10-21 | 2025-10-21 | 12 | 0-4027 | Boxes of Staples for Silt Fence | 1 | 71.83 | PO:COMMIT | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | 71.83 | 0
ttJTrans | 0-4027 | MA | MA1008600 | MA | MA1008600 | 2025-10-21 | 2025-10-21 | 11 | 0-4027 | 1" x 1" x 36" stakes - wooden | 220 | 449.33 | PO:COMMIT | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | 449.33 | 0
ttJTrans | 0-4027 | MA | MA1008600 | MA | MA1008600 | 2025-10-21 | 2025-10-21 | 10 | 0-4027 | Type B - Silt Fence 100ft/roll | 12 | 666 | PO:COMMIT | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | 666 | 0
ttJTrans | 0-4027 | MA | MA1008600 | MA | MA1008600 | 2025-10-21 | 2025-10-21 | 9 | 0-4027 | LES PS6500-210 LONESTAR 6500FT 210LB PULL | 1 | 36.56 | PO:COMMIT | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | 36.56 | 0
ttJTrans | 0-4027 | MA | MA1008600 | MA | MA1008600 | 2025-10-21 | 2025-10-21 | 8 | 0-4027 | CUR 671 SPINDLE FOR MEDIUM REEL STAND | 1 | 490.09 | PO:COMMIT | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | 490.09 | 0
ttJTrans | 0-4027 | MA | MA1008600 | MA | MA1008600 | 2025-10-21 | 2025-10-21 | 7 | 0-4027 | CUR 670 SCREW TYPE TELESCOPING REEL STAND - | 2 | 826.55 | PO:COMMIT | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | 826.55 | 0
ttJTrans | 0-4027 | MA | MA1008600 | MA | MA1008600 | 2025-10-21 | 2025-10-21 | 2 | 0-4027 | A53BE12 1 1/2 UL SCH-80 10'BE | 600 | 765.9 | PO:COMMIT | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | 765.9 | 0
ttJTrans | 0-4027 | MA | MA1008600 | MA | MA1008600 | 2025-10-21 | 2025-10-21 | 2 | 0-4027 | A53BE12 1 1/2 UL SCH-80 10'BE | 600 | 765.9 | INVOICE:ADJ-COMMIT | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | -762.57 | 0
ttJTrans | 0-4027 | MA | MA1008600 | MA | MA1008600 | 2025-10-21 | 2025-10-21 | 8 | 0-4027 | CUR 671 SPINDLE FOR MEDIUM REEL STAND | 1 | 490.09 | INVOICE:ADJ-COMMIT | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | -490.09 | 0
ttJTrans | 0-4027 | MA | MA1008600 | MA | MA1008600 | 2025-10-21 | 2025-10-21 | 9 | 0-4027 | LES PS6500-210 LONESTAR 6500FT 210LB PULL | 1 | 36.56 | INVOICE:ADJ-COMMIT | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | -36.56 | 0
ttJTrans | 0-4027 | MA | MA1008600 | MA | MA1008600 | 2025-10-21 | 2025-10-21 | 7 | 0-4027 | CUR 670 SCREW TYPE TELESCOPING REEL STAND - | 2 | 826.55 | INVOICE:ADJ-COMMIT | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | -826.55 | 0
ttJTrans | 0-4027 | MA | MA1008600 | MA | MA1008600 | 2025-10-21 | 2025-10-21 | 13 | 0-4027 | 6" Wide Detectable Warning Burial Tape | 4 | 313.42 | INVOICE:ADJ-COMMIT | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | -313.42 | 0
ttJTrans | 0-4027 | MA | MA1008600 | MA | MA1008600 | 2025-10-21 | 2026-01-08 | 13 | 0-4027 | 6" Wide Detectable Warning Burial Tape | 4 | 313.42 | INVOICE | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4027 | MA | MA1008600 | MA | MA1008600 | 2025-10-21 | 2025-12-23 | 9 | 0-4027 | LES PS6500-210 LONESTAR 6500FT 210LB PULL | 1 | 36.56 | INVOICE | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4027 | MA | MA1008600 | MA | MA1008600 | 2025-10-21 | 2025-11-22 | 5 | 0-4027 | 5144007 1 1/2 UL END BELL | 4 | 14.3 | INVOICE | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4027 | MA | MA1008600 | MA | MA1008600 | 2025-10-21 | 2025-11-22 | 4 | 0-4027 | 5121007 1 1/2 UL80 45 BND STD R | 4 | 14.3 | INVOICE | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4027 | MA | MA1008600 | MA | MA1008600 | 2025-10-21 | 2025-11-22 | 3 | 0-4027 | 7210603 CEMENT LOW VOC QT #99 | 1 | 18.84 | INVOICE | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4027 | MA | MA1008600 | MA | MA1008600 | 2025-10-21 | 2025-11-07 | 1 | 0-4027 | 012ZU4-T4F22D20 12-F OS2 LT ALTOS BINDERLESS | 600 | 279.72 | INVOICE | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4027 | MA | MA1008600 | MA | MA1008600 | 2025-10-21 | 2025-10-21 | 4 | 0-4027 | 5121007 1 1/2 UL80 45 BND STD R | 4 | 14.3 | INVOICE:ADJ-COMMIT | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | -14.3 | 0
ttJTrans | 0-4027 | MA | MA1008600 | MA | MA1008600 | 2025-10-21 | 2025-10-21 | 6 | 0-4027 | 3M™ Adhesive Sealant 760 UV, Black, 290 mL | 12 | 246.69 | INVOICE:ADJ-COMMIT | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | -246.67 | 0
ttJTrans | 0-4027 | MA | MA1008600 | MA | MA1008600 | 2025-10-21 | 2025-10-21 | 5 | 0-4027 | 5144007 1 1/2 UL END BELL | 4 | 14.3 | INVOICE:ADJ-COMMIT | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | -14.3 | 0
ttJTrans | 0-4027 | MA | MA1009005 | MA | MA1009005 | 2025-11-11 | 2025-11-11 | 1 | 0-4027 | 4AVP2 UNDERGROUND ENCLOSURE, 15,000LB, 12"L, | 2 | 1915.55 | INVOICE:ADJ-COMMIT | 12747 | GRAINGER, INC. | 0 | 0 | -1915.55 | 0
ttJTrans | 0-4027 | MA | MA1009005 | MA | MA1009005 | 2025-11-11 | 2025-12-03 | 1 | 0-4027 | 4AVP2 UNDERGROUND ENCLOSURE, 15,000LB, 12"L, | 2 | 1915.55 | INVOICE | 12747 | GRAINGER, INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4027 | MA | MA1009005 | MA | MA1009005 | 2025-11-11 | 2025-11-11 | 1 | 0-4027 | 4AVP2 UNDERGROUND ENCLOSURE, 15,000LB, 12"L, | 2 | 1915.55 | PO:COMMIT | 12747 | GRAINGER, INC. | 0 | 0 | 1915.55 | 0
ttJTrans | 0-4027 | MA | MA1009040 | MA | MA1009040 | 2025-11-13 | 2025-11-13 | 2 | 0-4027 | 0111-36 STAKE WOOD 1IN X 1IN X 36IN | 220 | 244.2 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -244.2 | 0
ttJTrans | 0-4027 | MA | MA1009040 | MA | MA1009040 | 2025-11-13 | 2025-11-13 | 3 | 0-4027 | 8IN ZIP TIE BLACK 1000/PK | 1 | 27.75 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -27.75 | 0
ttJTrans | 0-4027 | MA | MA1009040 | MA | MA1009040 | 2025-11-13 | 2025-11-13 | 1 | 0-4027 | SF726 SILT FENCE BX GRID REINF 3FT X 1 | 12 | 656.41 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -656.41 | 0
ttJTrans | 0-4027 | MA | MA1009040 | MA | MA1009040 | 2025-11-13 | 2025-12-23 | 2 | 0-4027 | 0111-36 STAKE WOOD 1IN X 1IN X 36IN | 220 | 244.2 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4027 | MA | MA1009040 | MA | MA1009040 | 2025-11-13 | 2025-11-13 | 1 | 0-4027 | SF726 SILT FENCE BX GRID REINF 3FT X 1 | 12 | 656.41 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 656.41 | 0
ttJTrans | 0-4027 | MA | MA1009040 | MA | MA1009040 | 2025-11-13 | 2025-11-13 | 3 | 0-4027 | 8IN ZIP TIE BLACK 1000/PK | 1 | 27.75 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 27.75 | 0
ttJTrans | 0-4027 | MA | MA1009040 | MA | MA1009040 | 2025-11-13 | 2025-12-23 | 1 | 0-4027 | SF726 SILT FENCE BX GRID REINF 3FT X 1 | 12 | 656.41 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4027 | MA | MA1009040 | MA | MA1009040 | 2025-11-13 | 2025-11-13 | 2 | 0-4027 | 0111-36 STAKE WOOD 1IN X 1IN X 36IN | 220 | 244.2 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 244.2 | 0
ttJTrans | 0-4027 | MA | MA1009040 | MA | MA1009040 | 2025-11-13 | 2025-12-23 | 3 | 0-4027 | 8IN ZIP TIE BLACK 1000/PK | 1 | 27.75 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4027 | MA |  | MA |  |  | 2025-11-09 |  | 0-4027 | BINDERLESS FAST ACCESS DIELECTRIC | 0 | 0 |  | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 275.38 | 0 | 0
ttJTrans | 0-4027 | MA |  | MA |  |  | 2025-11-23 |  | 0-4027 | CEMENT LOW VOC QT #99/ UL80 45 BND STD R/ UL END BELL | 0 | 0 |  | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 40.87 | 0 | 0
ttJTrans | 0-4027 | MA |  | MA |  |  | 2025-11-23 |  | 0-4027 | CEMENT LOW VOC QT #99/ UL80 45 BND STD R/ UL END BELL | 0 | 0 |  | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 46.26 | 0 | 0
ttJTrans | 0-4027 | MA |  | MA |  |  | 2025-11-24 |  | 0-4027 | ADHESIVE SEALANT | 0 | 0 |  | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 240.55 | 0 | 0
ttJTrans | 0-4027 | MA |  | MA |  |  | 2025-11-25 |  | 0-4027 | 1/2 UL SCH-80 10' BE | 0 | 0 |  | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 743.68 | 0 | 0
ttJTrans | 0-4027 | MA |  | MA |  |  | 2025-12-01 |  | 0-4027 | UNDERGROUND ENCLOSUR 15LB | 0 | 0 |  | 12747 | GRAINGER, INC. | 0 | 1868.09 | 0 | 0
ttJTrans | 0-4027 | MA |  | MA |  |  | 2025-12-23 |  | 0-4027 | SILT FENCE / STAKE WOOD / ZIP TIE | 0 | 0 |  | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 905.37 | 0 | 0
ttJTrans | 0-4027 | MA |  | MA |  |  | 2025-12-23 |  | 0-4027 | SCREW TYPE TELESCOPING REEL STAND / SPINDLE FOR MEDIUM REEL STAND / PULL STRING BUCKET | 0 | 0 |  | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 1319.69 | 0 | 0
ttJTrans | 0-4027 | MA |  | MA |  |  | 2026-01-08 |  | 0-4027 | DETECTABLE WARNING BURIAL TAPE | 0 | 0 |  | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 305.65 | 0 | 0
ttJTrans | 0-4027 | OC | MA1008600 | OC | MA1008600 | 2025-10-21 | 2025-12-23 | 14 | 0-4027 | FREIGHT | 1 | 832.5 | INVOICE | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4027 | OC | MA1008600 | OC | MA1008600 | 2025-10-21 | 2025-10-21 | 14 | 0-4027 | FREIGHT | 1 | 832.5 | INVOICE:ADJ-COMMIT | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | -832.5 | 0
ttJTrans | 0-4027 | OC | MA1008600 | OC | MA1008600 | 2025-10-21 | 2025-10-21 | 14 | 0-4027 | FREIGHT | 1 | 832.5 | PO:COMMIT | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 0 | 832.5 | 0
ttJTrans | 0-4027 | OC | MA1009040 | OC | MA1009040 | 2025-11-13 | 2025-12-23 | 4 | 0-4027 | ESTIMATED FREIGHT | 1 | 555 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4027 | OC | MA1009040 | OC | MA1009040 | 2025-11-13 | 2025-11-13 | 4 | 0-4027 | ESTIMATED FREIGHT | 1 | 555 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -555 | 0
ttJTrans | 0-4027 | OC | MA1009040 | OC | MA1009040 | 2025-11-13 | 2025-11-13 | 4 | 0-4027 | ESTIMATED FREIGHT | 1 | 555 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 555 | 0
ttJTrans | 0-4027 | OC |  | OC |  |  | 2025-12-20 |  | 0-4027 | COMDATA 11/24/25 (JRION) WHARTON FEED & SUPPLY 11/18/25 | 0 | 0 |  | 2208 |  | 0 | 184.89 | 0 | 0
ttJTrans | 0-4027 | OC |  | OC |  |  | 2025-12-20 |  | 0-4027 | COMDATA 11/24/25 (JRION) ALAMO LUMBER COMPANY W 11/20/25 | 0 | 0 |  | 2208 |  | 0 | 141.41 | 0 | 0
ttJTrans | 0-4027 | OC |  | OC |  |  | 2025-12-23 |  | 0-4027 | SILT FENCE / STAKE WOOD / ZIP TIE | 0 | 0 |  | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 541.25 | 0 | 0
ttJTrans | 0-4027 | OC |  | OC |  |  | 2025-12-23 |  | 0-4027 | SILT FENCE / STAKE WOOD / ZIP TIE | 0 | 0 |  | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 595.38 | 0 | 0
ttJTrans | 0-4027 | OC |  | OC |  |  | 2025-12-23 |  | 0-4027 | SCREW TYPE TELESCOPING REEL STAND / SPINDLE FOR MEDIUM REEL STAND / PULL STRING BUCKET | 0 | 0 |  | 20642 | GRIDPOWER SOLUTIONS, LLC | 0 | 811.89 | 0 | 0
ttJTrans | 0-4031 | EQ |  | EQ |  |  | 2026-03-15 |  | 0-4031 | RT1423 2024 FORD F250 XL CREW CAB GAS 2024 FORD F250 XL CREW CAB GAS | 0 | 0 |  | RT1423 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4031 | LA |  | LA |  |  | 2026-04-09 |  | 0-4031 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 3247.59 | 0 | 70
ttJTrans | 0-4031 | LA |  | LA |  |  | 2026-04-09 |  | 0-4031 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 2440.62 | 0 | 50
ttJTrans | 0-4031 | LA |  | LA |  |  | 2026-04-16 |  | 0-4031 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 289.27 | 0 | 8
ttJTrans | 0-4031 | LA |  | LA |  |  | 2026-04-23 |  | 0-4031 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 900.64 | 0 | 20
ttJTrans | 0-4031 | LA |  | LA |  |  | 2026-04-30 |  | 0-4031 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 2319.2 | 0 | 30
ttJTrans | 0-4031 | LA |  | LA |  |  | 2026-05-07 |  | 0-4031 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 367.4 | 0 | 8
ttJTrans | 0-4031 | LA |  | LA |  |  | 2026-05-07 |  | 0-4031 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 960.39 | 0 | 20
ttJTrans | 0-4031 | LA |  | LA |  |  | 2026-05-21 |  | 0-4031 | PR P0COST 000531 (PR) Summary | 0 | 0 |  |  |  | 0 | 2470.92 | 0 | 40
ttJTrans | 0-4031 | OC |  | OC |  |  | 2026-03-31 |  | 0-4031 | COMDATA 3/09/26 (AS) SQ *ABC SAFETY SOLUTIO 3/05/26 | 0 | 0 |  | 2264 |  | 0 | 630 | 0 | 0
ttJTrans | 0-4031 | OC |  | OC |  |  | 2026-05-07 |  | 0-4031 | DRUG SCREENS | 0 | 0 |  | 10630 | DISA GLOBAL SOLUTIONS INC | 0 | 150.75 | 0 | 0
ttJTrans | 0-4031 | OC |  | OC |  |  | 2026-05-19 |  | 0-4031 | MVR STATE FEES/ DQ NEW DRIVER / ONBOARDING/ SERVICE FEES | 0 | 0 |  | 20710 | NATIONAL ENERGY CONTROL SERVICES, INC. | 0 | 450 | 0 | 0
ttJTrans | 0-4031 | OC |  | OC |  |  | 2026-05-20 |  | 0-4031 | DRUG SCREEN | 0 | 0 |  | 10630 | DISA GLOBAL SOLUTIONS INC | 0 | 318.75 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-12 |  | 0-4100 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-19 |  | 0-4100 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4100 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4100 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4100 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4100 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4100 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4100 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4100 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4100 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4100 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4100 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4100 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4100 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4100 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4100 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4100 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4100 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4100 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4100 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4100 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4100 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-26 |  | 0-4100 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4100 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4100 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4100 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4100 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4100 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4100 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4100 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4100 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4100 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4100 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4100 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4100 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4100 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4100 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4100 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4100 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4100 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4100 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4100 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4100 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4100 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4100 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4100 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4100 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4100 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4100 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4100 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4100 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4100 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4100 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4100 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4100 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4100 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4100 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4100 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4100 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4100 | BH235 2023 KOMATSU PC88MR-11 EXCAVATOR 2023 KOMATSU PC88MR-11 EXCAVATOR | 0 | 0 |  | BH235 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4100 | BH235 2023 KOMATSU PC88MR-11 EXCAVATOR 2023 KOMATSU PC88MR-11 EXCAVATOR | 0 | 0 |  | BH235 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4100 | SSRAKE03 TITAN SSL-84 GRAPPLE RAKE TITAN SSL-84 GRAPPLE RAKE | 0 | 0 |  | SSRAKE03 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4100 | SSRAKE03 TITAN SSL-84 GRAPPLE RAKE TITAN SSL-84 GRAPPLE RAKE | 0 | 0 |  | SSRAKE03 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | TR425 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) 20FT ENCLOSED CARGO TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR425 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | BH235 2023 KOMATSU PC88MR-11 EXCAVATOR 2023 KOMATSU PC88MR-11 EXCAVATOR | 0 | 0 |  | BH235 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | BH235 2023 KOMATSU PC88MR-11 EXCAVATOR 2023 KOMATSU PC88MR-11 EXCAVATOR | 0 | 0 |  | BH235 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | BH235 2023 KOMATSU PC88MR-11 EXCAVATOR 2023 KOMATSU PC88MR-11 EXCAVATOR | 0 | 0 |  | BH235 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | BH235 2023 KOMATSU PC88MR-11 EXCAVATOR 2023 KOMATSU PC88MR-11 EXCAVATOR | 0 | 0 |  | BH235 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | BH235 2023 KOMATSU PC88MR-11 EXCAVATOR 2023 KOMATSU PC88MR-11 EXCAVATOR | 0 | 0 |  | BH235 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | BH235 2023 KOMATSU PC88MR-11 EXCAVATOR 2023 KOMATSU PC88MR-11 EXCAVATOR | 0 | 0 |  | BH235 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | SSRAKE03 TITAN SSL-84 GRAPPLE RAKE TITAN SSL-84 GRAPPLE RAKE | 0 | 0 |  | SSRAKE03 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100 | SSRAKE03 TITAN SSL-84 GRAPPLE RAKE TITAN SSL-84 GRAPPLE RAKE | 0 | 0 |  | SSRAKE03 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100 | TR145 20' CARGO TRAILER 20' CARGO TRAILER | 0 | 0 |  | TR145 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100 | BH235 2023 KOMATSU PC88MR-11 EXCAVATOR 2023 KOMATSU PC88MR-11 EXCAVATOR | 0 | 0 |  | BH235 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100 | BH235 2023 KOMATSU PC88MR-11 EXCAVATOR 2023 KOMATSU PC88MR-11 EXCAVATOR | 0 | 0 |  | BH235 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100 | BH235 2023 KOMATSU PC88MR-11 EXCAVATOR 2023 KOMATSU PC88MR-11 EXCAVATOR | 0 | 0 |  | BH235 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100 | BH235 2023 KOMATSU PC88MR-11 EXCAVATOR 2023 KOMATSU PC88MR-11 EXCAVATOR | 0 | 0 |  | BH235 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4100 | FE017 7' ROTARY CUTTER 7' ROTARY CUTTER | 0 | 0 |  | FE017 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-12 |  | 0-4100 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-12 |  | 0-4100 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-12 |  | 0-4100 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-12 |  | 0-4100 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-12 |  | 0-4100 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-12 |  | 0-4100 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-12 |  | 0-4100 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-12 |  | 0-4100 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-12 |  | 0-4100 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-12 |  | 0-4100 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-12 |  | 0-4100 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-12 |  | 0-4100 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-12 |  | 0-4100 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-12 |  | 0-4100 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-12 |  | 0-4100 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-12 |  | 0-4100 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-12 |  | 0-4100 | RAT440 POLARIS RANGER 1000 CREW CAB UTV POLARIS RANGER 1000 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-12 |  | 0-4100 | RAT440 POLARIS RANGER 1000 CREW CAB UTV POLARIS RANGER 1000 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-12 |  | 0-4100 | RAT440 POLARIS RANGER 1000 CREW CAB UTV POLARIS RANGER 1000 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-12 |  | 0-4100 | RAT440 POLARIS RANGER 1000 CREW CAB UTV POLARIS RANGER 1000 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-12 |  | 0-4100 | RAT440 POLARIS RANGER 1000 CREW CAB UTV POLARIS RANGER 1000 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-19 |  | 0-4100 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-19 |  | 0-4100 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-19 |  | 0-4100 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-19 |  | 0-4100 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-19 |  | 0-4100 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-19 |  | 0-4100 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-19 |  | 0-4100 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-19 |  | 0-4100 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-19 |  | 0-4100 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-19 |  | 0-4100 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-19 |  | 0-4100 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-19 |  | 0-4100 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-19 |  | 0-4100 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-19 |  | 0-4100 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-19 |  | 0-4100 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-19 |  | 0-4100 | RAT440 POLARIS RANGER 1000 CREW CAB UTV POLARIS RANGER 1000 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-19 |  | 0-4100 | RAT440 POLARIS RANGER 1000 CREW CAB UTV POLARIS RANGER 1000 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-19 |  | 0-4100 | RAT440 POLARIS RANGER 1000 CREW CAB UTV POLARIS RANGER 1000 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-19 |  | 0-4100 | RAT440 POLARIS RANGER 1000 CREW CAB UTV POLARIS RANGER 1000 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-19 |  | 0-4100 | RAT440 POLARIS RANGER 1000 CREW CAB UTV POLARIS RANGER 1000 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-19 |  | 0-4100 | RAT440 POLARIS RANGER 1000 CREW CAB UTV POLARIS RANGER 1000 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-26 |  | 0-4100 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-26 |  | 0-4100 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-26 |  | 0-4100 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-26 |  | 0-4100 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-26 |  | 0-4100 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-26 |  | 0-4100 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-26 |  | 0-4100 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-26 |  | 0-4100 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-26 |  | 0-4100 | RAT440 POLARIS RANGER 1000 CREW CAB UTV POLARIS RANGER 1000 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-26 |  | 0-4100 | RAT440 POLARIS RANGER 1000 CREW CAB UTV POLARIS RANGER 1000 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-26 |  | 0-4100 | RAT440 POLARIS RANGER 1000 CREW CAB UTV POLARIS RANGER 1000 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-30 |  | 0-4100 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-30 |  | 0-4100 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-30 |  | 0-4100 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-30 |  | 0-4100 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-30 |  | 0-4100 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-30 |  | 0-4100 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-30 |  | 0-4100 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-30 |  | 0-4100 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-30 |  | 0-4100 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-30 |  | 0-4100 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-30 |  | 0-4100 | RAT440 POLARIS RANGER 1000 CREW CAB UTV POLARIS RANGER 1000 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-30 |  | 0-4100 | RAT440 POLARIS RANGER 1000 CREW CAB UTV POLARIS RANGER 1000 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-30 |  | 0-4100 | RAT440 POLARIS RANGER 1000 CREW CAB UTV POLARIS RANGER 1000 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-04-30 |  | 0-4100 | RAT440 POLARIS RANGER 1000 CREW CAB UTV POLARIS RANGER 1000 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-05-10 |  | 0-4100 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-05-10 |  | 0-4100 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-05-10 |  | 0-4100 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-05-10 |  | 0-4100 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-05-10 |  | 0-4100 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-05-10 |  | 0-4100 | RAT440 CAN AM HD11 CREW CAB UTV CAN AM HD11 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-05-10 |  | 0-4100 | RAT440 CAN AM HD11 CREW CAB UTV CAN AM HD11 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-05-10 |  | 0-4100 | RAT440 CAN AM HD11 CREW CAB UTV CAN AM HD11 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-05-17 |  | 0-4100 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-05-17 |  | 0-4100 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-05-17 |  | 0-4100 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-05-17 |  | 0-4100 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-05-17 |  | 0-4100 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-05-17 |  | 0-4100 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-05-17 |  | 0-4100 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-05-17 |  | 0-4100 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-05-17 |  | 0-4100 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-05-17 |  | 0-4100 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-05-17 |  | 0-4100 | RAT440 CAN AM HD11 CREW CAB UTV CAN AM HD11 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-05-17 |  | 0-4100 | RAT440 CAN AM HD11 CREW CAB UTV CAN AM HD11 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-05-17 |  | 0-4100 | RAT440 CAN AM HD11 CREW CAB UTV CAN AM HD11 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-05-17 |  | 0-4100 | RAT440 CAN AM HD11 CREW CAB UTV CAN AM HD11 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-05-24 |  | 0-4100 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-05-24 |  | 0-4100 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-05-24 |  | 0-4100 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-05-24 |  | 0-4100 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-05-24 |  | 0-4100 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-05-24 |  | 0-4100 | RAT440 CAN AM HD11 CREW CAB UTV CAN AM HD11 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-05-24 |  | 0-4100 | RAT440 CAN AM HD11 CREW CAB UTV CAN AM HD11 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | ER |  | ER |  |  | 2026-05-24 |  | 0-4100 | RAT440 CAN AM HD11 CREW CAB UTV CAN AM HD11 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100 | LA |  | LA |  |  | 2026-04-09 |  | 0-4100 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 1961.61 | 0 | 32
ttJTrans | 0-4100 | LA |  | LA |  |  | 2026-04-09 |  | 0-4100 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 3829.49 | 0 | 60
ttJTrans | 0-4100 | LA |  | LA |  |  | 2026-04-09 |  | 0-4100 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 1653.87 | 0 | 40
ttJTrans | 0-4100 | LA |  | LA |  |  | 2026-04-09 |  | 0-4100 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 2653.45 | 0 | 60
ttJTrans | 0-4100 | LA |  | LA |  |  | 2026-04-09 |  | 0-4100 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 2440.61 | 0 | 50
ttJTrans | 0-4100 | LA |  | LA |  |  | 2026-04-09 |  | 0-4100 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 393.43 | 0 | 8
ttJTrans | 0-4100 | LA |  | LA |  |  | 2026-04-16 |  | 0-4100 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 4084.97 | 0 | 60
ttJTrans | 0-4100 | LA |  | LA |  |  | 2026-04-16 |  | 0-4100 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 4301.13 | 0 | 100
ttJTrans | 0-4100 | LA |  | LA |  |  | 2026-04-16 |  | 0-4100 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 4227.72 | 0 | 90
ttJTrans | 0-4100 | LA |  | LA |  |  | 2026-04-16 |  | 0-4100 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 3284.27 | 0 | 70
ttJTrans | 0-4100 | LA |  | LA |  |  | 2026-04-16 |  | 0-4100 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 3293.91 | 0 | 70
ttJTrans | 0-4100 | LA |  | LA |  |  | 2026-04-16 |  | 0-4100 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 498.25 | 0 | 10
ttJTrans | 0-4100 | LA |  | LA |  |  | 2026-04-23 |  | 0-4100 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 3364.97 | 0 | 70
ttJTrans | 0-4100 | LA |  | LA |  |  | 2026-04-23 |  | 0-4100 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 2782.34 | 0 | 60
ttJTrans | 0-4100 | LA |  | LA |  |  | 2026-04-23 |  | 0-4100 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 2601.26 | 0 | 56
ttJTrans | 0-4100 | LA |  | LA |  |  | 2026-04-23 |  | 0-4100 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 1692.49 | 0 | 32
ttJTrans | 0-4100 | LA |  | LA |  |  | 2026-04-23 |  | 0-4100 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 268.08 | 0 | 4
ttJTrans | 0-4100 | LA |  | LA |  |  | 2026-04-30 |  | 0-4100 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 3545.75 | 0 | 80
ttJTrans | 0-4100 | LA |  | LA |  |  | 2026-04-30 |  | 0-4100 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 3613.02 | 0 | 80
ttJTrans | 0-4100 | LA |  | LA |  |  | 2026-04-30 |  | 0-4100 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 3100.42 | 0 | 70
ttJTrans | 0-4100 | LA |  | LA |  |  | 2026-04-30 |  | 0-4100 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 2001.88 | 0 | 30
ttJTrans | 0-4100 | LA |  | LA |  |  | 2026-04-30 |  | 0-4100 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 3117.31 | 0 | 70
ttJTrans | 0-4100 | LA |  | LA |  |  | 2026-05-07 |  | 0-4100 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 3276.71 | 0 | 50
ttJTrans | 0-4100 | LA |  | LA |  |  | 2026-05-07 |  | 0-4100 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 3276.67 | 0 | 50
ttJTrans | 0-4100 | LA |  | LA |  |  | 2026-05-07 |  | 0-4100 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 2378.98 | 0 | 60
ttJTrans | 0-4100 | LA |  | LA |  |  | 2026-05-07 |  | 0-4100 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 2131.07 | 0 | 50
ttJTrans | 0-4100 | LA |  | LA |  |  | 2026-05-14 |  | 0-4100 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 2238.7 | 0 | 50
ttJTrans | 0-4100 | LA |  | LA |  |  | 2026-05-14 |  | 0-4100 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 2993.94 | 0 | 70
ttJTrans | 0-4100 | LA |  | LA |  |  | 2026-05-14 |  | 0-4100 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 2813.01 | 0 | 50
ttJTrans | 0-4100 | LA |  | LA |  |  | 2026-05-14 |  | 0-4100 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 2380.95 | 0 | 60
ttJTrans | 0-4100 | LA |  | LA |  |  | 2026-05-14 |  | 0-4100 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 2005.6 | 0 | 50
ttJTrans | 0-4100 | OC | MA1010837 | OC | MA1010837 | 2026-04-28 | 2026-05-01 | 1 | 0-4100 | 3X1200 CPOP BULK ROLL | 67 | 50199.75 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -50199.75 | 0
ttJTrans | 0-4100 | OC | MA1010837 | OC | MA1010837 | 2026-04-28 | 2026-05-01 | 1 | 0-4100 | 3X1200 CPOP BULK ROLL | 67 | 50199.75 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 50199.75 | 0
ttJTrans | 0-4100 | OC | MA1010837 | OC | MA1010837 | 2026-04-28 | 2026-05-07 | 1 | 0-4100 | 3X1200 CPOP BULK ROLL | 67 | 50199.75 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4100 | OC |  | OC |  |  | 2026-05-05 |  | 0-4100 | SITL FENCE ERIOUSION CONTROL SUPPLIES S624996 LUKE | 0 | 0 |  | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 48956.07 | 0 | 0
ttJTrans | 0-4100-01 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100-01 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100-01 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100-01 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100-01 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100-01 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100-01 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4100-01 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100-01 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100-01 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100-01 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4100-01 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100-01 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100-01 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100-01 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100-01 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100-01 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100-01 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100-01 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4100-01 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4100-01 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4100-01 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100-01 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4100-01 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100-01 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4100-01 | WLD146 SILT FENCE PLOW - SKID STEER SILT FENCE PLOW - SKID STEER | 0 | 0 |  | WLD146 |  | 0 | 50 | 0 | 0
ttJTrans | 0-4100-01 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4100-01 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4100-01 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4100-01 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4100-01 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4100-01 | SSAUGKIT1 SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT SKIDPRO SP300 PLANETARY AUGER DRIVE KIT W/ CRADLE & MOUNT | 0 | 0 |  | SSAUGKIT1 |  | 0 | 35 | 0 | 0
ttJTrans | 0-4100-01 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4100-01 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100-01 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4100-01 | TR428 CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) CARRY-ON 5X8 UTILITY TRAILER (CHARGED TO 22-4001) | 0 | 0 |  | TR428 |  | 0 | 15 | 0 | 0
ttJTrans | 0-4100-01 | ER |  | ER |  |  | 2026-05-17 |  | 0-4100-01 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100-01 | ER |  | ER |  |  | 2026-05-10 |  | 0-4100-01 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100-01 | ER |  | ER |  |  | 2026-05-10 |  | 0-4100-01 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100-01 | ER |  | ER |  |  | 2026-05-10 |  | 0-4100-01 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100-01 | ER |  | ER |  |  | 2026-05-10 |  | 0-4100-01 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100-01 | ER |  | ER |  |  | 2026-05-10 |  | 0-4100-01 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100-01 | ER |  | ER |  |  | 2026-05-10 |  | 0-4100-01 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100-01 | ER |  | ER |  |  | 2026-05-10 |  | 0-4100-01 | RAT440 CAN AM HD11 CREW CAB UTV CAN AM HD11 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100-01 | ER |  | ER |  |  | 2026-05-10 |  | 0-4100-01 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4100-01 | ER |  | ER |  |  | 2026-05-17 |  | 0-4100-01 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100-01 | ER |  | ER |  |  | 2026-05-17 |  | 0-4100-01 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100-01 | ER |  | ER |  |  | 2026-05-17 |  | 0-4100-01 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100-01 | ER |  | ER |  |  | 2026-05-24 |  | 0-4100-01 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100-01 | ER |  | ER |  |  | 2026-05-17 |  | 0-4100-01 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100-01 | ER |  | ER |  |  | 2026-05-17 |  | 0-4100-01 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100-01 | ER |  | ER |  |  | 2026-05-17 |  | 0-4100-01 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100-01 | ER |  | ER |  |  | 2026-05-17 |  | 0-4100-01 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100-01 | ER |  | ER |  |  | 2026-05-17 |  | 0-4100-01 | RAT440 CAN AM HD11 CREW CAB UTV CAN AM HD11 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100-01 | ER |  | ER |  |  | 2026-05-17 |  | 0-4100-01 | RAT440 CAN AM HD11 CREW CAB UTV CAN AM HD11 CREW CAB UTV | 0 | 0 |  | RAT440 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100-01 | ER |  | ER |  |  | 2026-05-17 |  | 0-4100-01 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4100-01 | ER |  | ER |  |  | 2026-05-24 |  | 0-4100-01 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100-01 | ER |  | ER |  |  | 2026-05-24 |  | 0-4100-01 | RLD292 CATERPILLAR 299D3 TRACK SKID STEER LOADER CATERPILLAR 299D3 TRACK SKID STEER LOADER | 0 | 0 |  | RLD292 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4100-01 | ER |  | ER |  |  | 2026-05-24 |  | 0-4100-01 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4100-01 | LA |  | LA |  |  | 2026-05-07 |  | 0-4100-01 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 1592.14 | 0 | 20.02
ttJTrans | 0-4100-01 | LA |  | LA |  |  | 2026-05-07 |  | 0-4100-01 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 1128.59 | 0 | 30
ttJTrans | 0-4100-01 | LA |  | LA |  |  | 2026-05-07 |  | 0-4100-01 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 2427.61 | 0 | 40
ttJTrans | 0-4100-01 | LA |  | LA |  |  | 2026-05-07 |  | 0-4100-01 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 2427.57 | 0 | 40
ttJTrans | 0-4100-01 | LA |  | LA |  |  | 2026-05-07 |  | 0-4100-01 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 1616.76 | 0 | 40
ttJTrans | 0-4100-01 | LA |  | LA |  |  | 2026-05-07 |  | 0-4100-01 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 3208.9 | 0 | 69.98
ttJTrans | 0-4100-01 | LA |  | LA |  |  | 2026-05-07 |  | 0-4100-01 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 1592.12 | 0 | 20
ttJTrans | 0-4100-01 | LA |  | LA |  |  | 2026-05-14 |  | 0-4100-01 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 3661.7 | 0 | 90
ttJTrans | 0-4100-01 | LA |  | LA |  |  | 2026-05-14 |  | 0-4100-01 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 1689.37 | 0 | 40
ttJTrans | 0-4100-01 | LA |  | LA |  |  | 2026-05-14 |  | 0-4100-01 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 1850.66 | 0 | 30
ttJTrans | 0-4100-01 | LA |  | LA |  |  | 2026-05-14 |  | 0-4100-01 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 3510.95 | 0 | 60
ttJTrans | 0-4100-01 | LA |  | LA |  |  | 2026-05-14 |  | 0-4100-01 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 1245.74 | 0 | 30
ttJTrans | 0-4100-01 | LA |  | LA |  |  | 2026-05-14 |  | 0-4100-01 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 1245.74 | 0 | 30
ttJTrans | 0-4100-01 | MA | MA1011245 | MA | MA1011245 | 2026-04-29 | 2026-05-07 | 4 | 0-4100-01 | ADDREGATE - ROADS AND EROSION CONTROL - | 1500 | 99900 | PO:COMMIT | 21358 | TEXAS GULF COAST AGGREGATES, LLC | 0 | 0 | 99900 | 0
ttJTrans | 0-4100-01 | OC | MA1010837 | OC | MA1010837 | 2026-04-28 | 2026-05-07 | 16 | 0-4100-01 | BAG FILTER NW 13 X 15 - 60/PLT | 20 | 2240.65 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4100-01 | OC | MA1010837 | OC | MA1010837 | 2026-04-28 | 2026-05-01 | 4 | 0-4100-01 | 4’x100’ HARDWARE CLOTH 1/4' ME | 15 | 1369.46 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -1369.46 | 0
ttJTrans | 0-4100-01 | OC | MA1010837 | OC | MA1010837 | 2026-04-28 | 2026-05-07 | 4 | 0-4100-01 | 4’x100’ HARDWARE CLOTH 1/4' ME | 15 | 1369.46 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4100-01 | OC | MA1010837 | OC | MA1010837 | 2026-04-28 | 2026-05-07 | 3 | 0-4100-01 | BLANKET STRAW 8FTX112.5FT DOUB | 20 | 777 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4100-01 | OC | MA1010837 | OC | MA1010837 | 2026-04-28 | 2026-05-07 | 2 | 0-4100-01 | STAKE WOOD 1.5X1.5X48 | 16000 | 20424 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4100-01 | OC | MA1010837 | OC | MA1010837 | 2026-04-28 | 2026-05-01 | 2 | 0-4100-01 | STAKE WOOD 1.5X1.5X48 | 16000 | 20424 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 20424 | 0
ttJTrans | 0-4100-01 | OC | MA1010837 | OC | MA1010837 | 2026-04-28 | 2026-05-01 | 4 | 0-4100-01 | 4’x100’ HARDWARE CLOTH 1/4' ME | 15 | 1369.46 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 1369.46 | 0
ttJTrans | 0-4100-01 | OC | MA1010837 | OC | MA1010837 | 2026-04-28 | 2026-05-01 | 16 | 0-4100-01 | BAG FILTER NW 13 X 15 - 60/PLT | 20 | 2240.65 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 2240.65 | 0
ttJTrans | 0-4100-01 | OC | MA1010837 | OC | MA1010837 | 2026-04-28 | 2026-05-01 | 16 | 0-4100-01 | BAG FILTER NW 13 X 15 - 60/PLT | 20 | 2240.65 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -2158.07 | 0
ttJTrans | 0-4100-01 | OC | MA1010837 | OC | MA1010837 | 2026-04-28 | 2026-05-01 | 2 | 0-4100-01 | STAKE WOOD 1.5X1.5X48 | 16000 | 20424 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -20424 | 0
ttJTrans | 0-4100-01 | OC | MA1010837 | OC | MA1010837 | 2026-04-28 | 2026-05-01 | 3 | 0-4100-01 | BLANKET STRAW 8FTX112.5FT DOUB | 20 | 777 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -777 | 0
ttJTrans | 0-4100-01 | OC | MA1010837 | OC | MA1010837 | 2026-04-28 | 2026-05-01 | 3 | 0-4100-01 | BLANKET STRAW 8FTX112.5FT DOUB | 20 | 777 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 777 | 0
ttJTrans | 0-4100-01 | OC | MA1011252 | OC | MA1011252 | 2026-04-15 | 2026-04-16 | 3 | 0-4100-01 | Wattles | 20 | 656.45 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 656.45 | 0
ttJTrans | 0-4100-01 | OC | MA1011252 | OC | MA1011252 | 2026-04-15 | 2026-04-29 | 3 | 0-4100-01 | Wattles | 20 | 656.45 | INVOICE | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 0 | 0
ttJTrans | 0-4100-01 | OC | MA1011252 | OC | MA1011252 | 2026-04-15 | 2026-04-16 | 3 | 0-4100-01 | Wattles | 20 | 656.45 | INVOICE:ADJ-COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | -656.45 | 0
ttJTrans | 0-4100-01 | OC |  | OC |  |  | 2026-05-05 |  | 0-4100-01 | SITL FENCE ERIOUSION CONTROL SUPPLIES S624996 LUKE | 0 | 0 |  | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 24115.88 | 0 | 0
ttJTrans | 0-4100-01 | OC |  | OC |  |  | 2026-04-29 |  | 0-4100-01 | PAINT/ 2X20 PVC SCH80 / WATTLE STRAW/ DEF/ RAGS/ GLASS CLNR/ VISQUEEN | 0 | 0 |  | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 640.19 | 0 | 0
ttJTrans | 0-4101 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4101 | SSRAKE03 TITAN SSL-84 GRAPPLE RAKE TITAN SSL-84 GRAPPLE RAKE | 0 | 0 |  | SSRAKE03 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4101 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4101 | SSRAKE03 TITAN SSL-84 GRAPPLE RAKE TITAN SSL-84 GRAPPLE RAKE | 0 | 0 |  | SSRAKE03 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4101 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4101 | SSRAKE03 TITAN SSL-84 GRAPPLE RAKE TITAN SSL-84 GRAPPLE RAKE | 0 | 0 |  | SSRAKE03 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4101 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4101 | SSRAKE03 TITAN SSL-84 GRAPPLE RAKE TITAN SSL-84 GRAPPLE RAKE | 0 | 0 |  | SSRAKE03 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4101 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4101 | SSRAKE03 TITAN SSL-84 GRAPPLE RAKE TITAN SSL-84 GRAPPLE RAKE | 0 | 0 |  | SSRAKE03 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4101 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4101 | BH235 2023 KOMATSU PC88MR-11 EXCAVATOR 2023 KOMATSU PC88MR-11 EXCAVATOR | 0 | 0 |  | BH235 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4101 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4101 | BH235 2023 KOMATSU PC88MR-11 EXCAVATOR 2023 KOMATSU PC88MR-11 EXCAVATOR | 0 | 0 |  | BH235 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4101 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4101 | SSRAKE03 TITAN SSL-84 GRAPPLE RAKE TITAN SSL-84 GRAPPLE RAKE | 0 | 0 |  | SSRAKE03 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4101 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4101 | SSRAKE03 TITAN SSL-84 GRAPPLE RAKE TITAN SSL-84 GRAPPLE RAKE | 0 | 0 |  | SSRAKE03 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4101 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4101 | SSRAKE03 TITAN SSL-84 GRAPPLE RAKE TITAN SSL-84 GRAPPLE RAKE | 0 | 0 |  | SSRAKE03 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4101 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4101 | SSRAKE03 TITAN SSL-84 GRAPPLE RAKE TITAN SSL-84 GRAPPLE RAKE | 0 | 0 |  | SSRAKE03 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4101 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4101 | SSRAKE03 TITAN SSL-84 GRAPPLE RAKE TITAN SSL-84 GRAPPLE RAKE | 0 | 0 |  | SSRAKE03 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4101 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4101 | SSRAKE03 TITAN SSL-84 GRAPPLE RAKE TITAN SSL-84 GRAPPLE RAKE | 0 | 0 |  | SSRAKE03 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4101 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4101 | BH235 2023 KOMATSU PC88MR-11 EXCAVATOR 2023 KOMATSU PC88MR-11 EXCAVATOR | 0 | 0 |  | BH235 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4101 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4101 | BH235 2023 KOMATSU PC88MR-11 EXCAVATOR 2023 KOMATSU PC88MR-11 EXCAVATOR | 0 | 0 |  | BH235 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4101 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4101 | BH235 2023 KOMATSU PC88MR-11 EXCAVATOR 2023 KOMATSU PC88MR-11 EXCAVATOR | 0 | 0 |  | BH235 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4101 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4101 | SSRAKE03 TITAN SSL-84 GRAPPLE RAKE TITAN SSL-84 GRAPPLE RAKE | 0 | 0 |  | SSRAKE03 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4101 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4101 | SSRAKE03 TITAN SSL-84 GRAPPLE RAKE TITAN SSL-84 GRAPPLE RAKE | 0 | 0 |  | SSRAKE03 |  | 0 | 0 | 0 | 0
ttJTrans | 0-4101 | ER |  | ER |  |  | 2026-05-24 |  | 0-4101 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4101 | ER |  | ER |  |  | 2026-04-19 |  | 0-4101 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4101 | ER |  | ER |  |  | 2026-04-19 |  | 0-4101 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4101 | ER |  | ER |  |  | 2026-04-19 |  | 0-4101 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4101 | ER |  | ER |  |  | 2026-04-26 |  | 0-4101 | RLD291 CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS CATERPILLAR 299D3 TRACK SKID STEER LOADER W FORKS | 0 | 0 |  | RLD291 |  | 0 | 186.27 | 0 | 0
ttJTrans | 0-4101 | ER |  | ER |  |  | 2026-04-30 |  | 0-4101 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4101 | ER |  | ER |  |  | 2026-04-30 |  | 0-4101 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4101 | ER |  | ER |  |  | 2026-04-30 |  | 0-4101 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4101 | ER |  | ER |  |  | 2026-04-30 |  | 0-4101 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4101 | ER |  | ER |  |  | 2026-04-30 |  | 0-4101 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4101 | ER |  | ER |  |  | 2026-04-30 |  | 0-4101 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4101 | ER |  | ER |  |  | 2026-04-30 |  | 0-4101 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4101 | ER |  | ER |  |  | 2026-05-10 |  | 0-4101 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4101 | ER |  | ER |  |  | 2026-05-10 |  | 0-4101 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4101 | ER |  | ER |  |  | 2026-05-10 |  | 0-4101 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4101 | ER |  | ER |  |  | 2026-05-10 |  | 0-4101 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4101 | ER |  | ER |  |  | 2026-05-17 |  | 0-4101 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4101 | ER |  | ER |  |  | 2026-05-17 |  | 0-4101 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4101 | ER |  | ER |  |  | 2026-05-17 |  | 0-4101 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4101 | ER |  | ER |  |  | 2026-05-17 |  | 0-4101 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4101 | ER |  | ER |  |  | 2026-05-17 |  | 0-4101 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4101 | ER |  | ER |  |  | 2026-05-17 |  | 0-4101 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4101 | ER |  | ER |  |  | 2026-05-24 |  | 0-4101 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4101 | ER |  | ER |  |  | 2026-05-24 |  | 0-4101 | RLD293 TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT TAKEUCHI TL10VS TRACK SKID STEER LOADER W TREE SAW ATTACHMENT | 0 | 0 |  | RLD293 |  | 0 | 282.06 | 0 | 0
ttJTrans | 0-4101 | LA |  | LA |  |  | 2026-04-30 |  | 0-4101 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 511.88 | 0 | 10
ttJTrans | 0-4101 | LA |  | LA |  |  | 2026-04-30 |  | 0-4101 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 511.88 | 0 | 10
ttJTrans | 0-4109 | MA | MA1011245 | MA | MA1011245 | 2026-04-29 | 2026-05-07 | 5 | 0-4109 | AGGREGATE - PV ROADS - TXDOT BASE | 42000 | 1993005 | PO:COMMIT | 21358 | TEXAS GULF COAST AGGREGATES, LLC | 0 | 0 | 1993005 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-10 |  | 0-4105 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-10 |  | 0-4105 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-10 |  | 0-4105 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-10 |  | 0-4105 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-10 |  | 0-4105 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-10 |  | 0-4105 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-10 |  | 0-4105 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-10 |  | 0-4105 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-10 |  | 0-4105 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-10 |  | 0-4105 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-17 |  | 0-4105 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-17 |  | 0-4105 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-17 |  | 0-4105 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-17 |  | 0-4105 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-17 |  | 0-4105 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-17 |  | 0-4105 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-17 |  | 0-4105 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-17 |  | 0-4105 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-17 |  | 0-4105 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-17 |  | 0-4105 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-17 |  | 0-4105 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-17 |  | 0-4105 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-17 |  | 0-4105 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-17 |  | 0-4105 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-17 |  | 0-4105 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-17 |  | 0-4105 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-17 |  | 0-4105 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-17 |  | 0-4105 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-17 |  | 0-4105 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-17 |  | 0-4105 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-17 |  | 0-4105 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-17 |  | 0-4105 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-24 |  | 0-4105 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-24 |  | 0-4105 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-24 |  | 0-4105 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-24 |  | 0-4105 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-24 |  | 0-4105 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-24 |  | 0-4105 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-24 |  | 0-4105 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-24 |  | 0-4105 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-24 |  | 0-4105 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-24 |  | 0-4105 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-24 |  | 0-4105 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-24 |  | 0-4105 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-24 |  | 0-4105 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-24 |  | 0-4105 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-10 |  | 0-4105 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4105 | ER |  | ER |  |  | 2026-05-10 |  | 0-4105 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4105 | LA |  | LA |  |  | 2026-04-16 |  | 0-4105 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 1162.7 | 0 | 20
ttJTrans | 0-4105 | LA |  | LA |  |  | 2026-05-07 |  | 0-4105 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 969.22 | 0 | 20
ttJTrans | 0-4105 | LA |  | LA |  |  | 2026-05-07 |  | 0-4105 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 1710.42 | 0 | 40
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-19 |  | 0-4107 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-19 |  | 0-4107 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-19 |  | 0-4107 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-19 |  | 0-4107 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-19 |  | 0-4107 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-19 |  | 0-4107 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-19 |  | 0-4107 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-19 |  | 0-4107 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-19 |  | 0-4107 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-19 |  | 0-4107 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-30 |  | 0-4107 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-30 |  | 0-4107 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-30 |  | 0-4107 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-30 |  | 0-4107 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-30 |  | 0-4107 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-30 |  | 0-4107 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-30 |  | 0-4107 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-30 |  | 0-4107 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-30 |  | 0-4107 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-30 |  | 0-4107 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-30 |  | 0-4107 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-30 |  | 0-4107 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-30 |  | 0-4107 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-30 |  | 0-4107 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-30 |  | 0-4107 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-30 |  | 0-4107 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-30 |  | 0-4107 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-30 |  | 0-4107 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-30 |  | 0-4107 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-30 |  | 0-4107 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-30 |  | 0-4107 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-10 |  | 0-4107 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-10 |  | 0-4107 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-10 |  | 0-4107 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-10 |  | 0-4107 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-10 |  | 0-4107 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-10 |  | 0-4107 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-10 |  | 0-4107 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-10 |  | 0-4107 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-10 |  | 0-4107 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-10 |  | 0-4107 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-10 |  | 0-4107 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-10 |  | 0-4107 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-10 |  | 0-4107 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-10 |  | 0-4107 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-10 |  | 0-4107 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-10 |  | 0-4107 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-10 |  | 0-4107 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-10 |  | 0-4107 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-10 |  | 0-4107 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-10 |  | 0-4107 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-10 |  | 0-4107 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-10 |  | 0-4107 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-10 |  | 0-4107 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-10 |  | 0-4107 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-17 |  | 0-4107 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-24 |  | 0-4107 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-24 |  | 0-4107 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-24 |  | 0-4107 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-24 |  | 0-4107 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-24 |  | 0-4107 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-24 |  | 0-4107 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-24 |  | 0-4107 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-24 |  | 0-4107 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-24 |  | 0-4107 | RFT891 CASE MAGNUM 220 FARM TRACTOR CASE MAGNUM 220 FARM TRACTOR | 0 | 0 |  | RFT891 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-24 |  | 0-4107 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-24 |  | 0-4107 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-24 |  | 0-4107 | RMS2319 25' SMOOTH ROLLER FOR FARM TRACTOR 25' SMOOTH ROLLER FOR FARM TRACTOR | 0 | 0 |  | RMS2319 |  | 0 | 179.6 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-24 |  | 0-4107 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-24 |  | 0-4107 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-24 |  | 0-4107 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-24 |  | 0-4107 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-24 |  | 0-4107 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-05-24 |  | 0-4107 | RMS2320 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2320 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-30 |  | 0-4107 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-19 |  | 0-4107 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-19 |  | 0-4107 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-26 |  | 0-4107 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-26 |  | 0-4107 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-26 |  | 0-4107 | RFT892 CASE PUMA 200 FARM TRACTOR W FRONT LOADER CASE PUMA 200 FARM TRACTOR W FRONT LOADER | 0 | 0 |  | RFT892 |  | 0 | 508.33 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-26 |  | 0-4107 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-26 |  | 0-4107 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-26 |  | 0-4107 | RMS2321 SEED DRILL FOR FARM TRACTOR SEED DRILL FOR FARM TRACTOR | 0 | 0 |  | RMS2321 |  | 0 | 1077.59 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-30 |  | 0-4107 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4107 | ER |  | ER |  |  | 2026-04-30 |  | 0-4107 | RFT890 CASE MAGNUN 220 FARM TRACTOR CASE MAGNUN 220 FARM TRACTOR | 0 | 0 |  | RFT890 |  | 0 | 500 | 0 | 0
ttJTrans | 0-4107 | LA |  | LA |  |  | 2026-04-09 |  | 0-4107 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 1154.91 | 0 | 20
ttJTrans | 0-4107 | LA |  | LA |  |  | 2026-04-16 |  | 0-4107 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 1723.05 | 0 | 30
ttJTrans | 0-4107 | LA |  | LA |  |  | 2026-04-16 |  | 0-4107 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 1723.05 | 0 | 30
ttJTrans | 0-4107 | LA |  | LA |  |  | 2026-04-16 |  | 0-4107 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 702.19 | 0 | 10
ttJTrans | 0-4107 | LA |  | LA |  |  | 2026-04-16 |  | 0-4107 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 1470.19 | 0 | 20
ttJTrans | 0-4107 | LA |  | LA |  |  | 2026-04-16 |  | 0-4107 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 2557.1 | 0 | 39.35
ttJTrans | 0-4107 | LA |  | LA |  |  | 2026-04-23 |  | 0-4107 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 1846.14 | 0 | 30
ttJTrans | 0-4107 | LA |  | LA |  |  | 2026-04-23 |  | 0-4107 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 1268.88 | 0 | 20
ttJTrans | 0-4107 | LA |  | LA |  |  | 2026-04-23 |  | 0-4107 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 1268.82 | 0 | 20
ttJTrans | 0-4107 | LA |  | LA |  |  | 2026-04-23 |  | 0-4107 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 457.24 | 0 | 8
ttJTrans | 0-4107 | LA |  | LA |  |  | 2026-04-30 |  | 0-4107 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 528.77 | 0 | 10
ttJTrans | 0-4107 | LA |  | LA |  |  | 2026-04-30 |  | 0-4107 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 1085.02 | 0 | 19.02
ttJTrans | 0-4107 | LA |  | LA |  |  | 2026-05-14 |  | 0-4107 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 1381.75 | 0 | 20
ttJTrans | 0-4107 | LA |  | LA |  |  | 2026-05-14 |  | 0-4107 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 1079.67 | 0 | 22.9
ttJTrans | 0-4107 | LA |  | LA |  |  | 2026-05-14 |  | 0-4107 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 1130.76 | 0 | 20.11
ttJTrans | 0-4107 | LA |  | LA |  |  | 2026-05-14 |  | 0-4107 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 1130.76 | 0 | 20
ttJTrans | 0-4107 | LA |  | LA |  |  | 2026-05-14 |  | 0-4107 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 593.81 | 0 | 12.61
ttJTrans | 0-4107 | LA |  | LA |  |  | 2026-05-14 |  | 0-4107 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 656.04 | 0 | 10.01
ttJTrans | 0-4107 | LA |  | LA |  |  | 2026-05-14 |  | 0-4107 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 656.04 | 0 | 8.02
ttJTrans | 0-4107 | LA |  | LA |  |  | 2026-05-21 |  | 0-4107 | PR P0COST 000531 (PR) Summary | 0 | 0 |  |  |  | 0 | 1891.06 | 0 | 30.02
ttJTrans | 0-4107 | LA |  | LA |  |  | 2026-05-21 |  | 0-4107 | PR P0COST 000531 (PR) Summary | 0 | 0 |  |  |  | 0 | 560.36 | 0 | 10
ttJTrans | 0-4107 | MA | MA1010834 | MA | MA1010834 | 2026-03-27 | 2026-03-30 | 1 | 0-4107 | Native Warm-Season MIX - Order #1 - 9.5 | 19000 | 397546.5 | PO:COMMIT | 12662 | ENVIRO SERVICES RENTAL, LLC | 0 | 0 | 397546.5 | 0
ttJTrans | 0-4107 | MA | MA1010834 | MA | MA1010834 | 2026-03-27 | 2026-03-30 | 2 | 0-4107 | Native Warm-Season MIX - Order #2 - 9.5 | 19000 | 397546.5 | PO:COMMIT | 12662 | ENVIRO SERVICES RENTAL, LLC | 0 | 0 | 397546.5 | 0
ttJTrans | 0-4107 | OC | MA1010834 | OC | MA1010834 | 2026-03-27 | 2026-03-30 | 3 | 0-4107 | TBD FREIGHT *Absolutely no cancellations or | 1 | 0 | PO:COMMIT | 12662 | ENVIRO SERVICES RENTAL, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4110 | LA |  | LA |  |  | 2026-04-23 |  | 0-4110 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 317.38 | 0 | 8
ttJTrans | 0-4111 | ER |  | ER |  |  | 2026-05-10 |  | 0-4111 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4111 | ER |  | ER |  |  | 2026-05-10 |  | 0-4111 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4111 | ER |  | ER |  |  | 2026-05-10 |  | 0-4111 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4111 | ER |  | ER |  |  | 2026-05-10 |  | 0-4111 | RPK500 CATERPILLAR 84" PADFOOT ROLLER CATERPILLAR 84" PADFOOT ROLLER | 0 | 0 |  | RPK500 |  | 0 | 340 | 0 | 0
ttJTrans | 0-4111 | ER |  | ER |  |  | 2026-05-10 |  | 0-4111 | RPK500 CATERPILLAR 84" PADFOOT ROLLER CATERPILLAR 84" PADFOOT ROLLER | 0 | 0 |  | RPK500 |  | 0 | 340 | 0 | 0
ttJTrans | 0-4111 | ER |  | ER |  |  | 2026-05-10 |  | 0-4111 | RPK500 CATERPILLAR 84" PADFOOT ROLLER CATERPILLAR 84" PADFOOT ROLLER | 0 | 0 |  | RPK500 |  | 0 | 340 | 0 | 0
ttJTrans | 0-4111 | ER |  | ER |  |  | 2026-05-10 |  | 0-4111 | RPK500 CATERPILLAR 84" PADFOOT ROLLER CATERPILLAR 84" PADFOOT ROLLER | 0 | 0 |  | RPK500 |  | 0 | 340 | 0 | 0
ttJTrans | 0-4111 | ER |  | ER |  |  | 2026-05-17 |  | 0-4111 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4111 | ER |  | ER |  |  | 2026-05-17 |  | 0-4111 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4111 | ER |  | ER |  |  | 2026-05-17 |  | 0-4111 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4111 | ER |  | ER |  |  | 2026-05-17 |  | 0-4111 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4111 | ER |  | ER |  |  | 2026-05-17 |  | 0-4111 | RPK500 CATERPILLAR 84" PADFOOT ROLLER CATERPILLAR 84" PADFOOT ROLLER | 0 | 0 |  | RPK500 |  | 0 | 340 | 0 | 0
ttJTrans | 0-4111 | ER |  | ER |  |  | 2026-05-17 |  | 0-4111 | RPK500 CATERPILLAR 84" PADFOOT ROLLER CATERPILLAR 84" PADFOOT ROLLER | 0 | 0 |  | RPK500 |  | 0 | 340 | 0 | 0
ttJTrans | 0-4111 | LA |  | LA |  |  | 2026-05-07 |  | 0-4111 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 2342.07 | 0 | 50
ttJTrans | 0-4111 | LA |  | LA |  |  | 2026-05-14 |  | 0-4111 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 2267.62 | 0 | 30
ttJTrans | 0-4111 | OC | MA1011065 | OC | MA1011065 | 46120 | 2026-04-08 | 1 | 0-4111 | SOIL PROCTOR TESTING BULK PO ALL CHARGES TO | 1 | 55500 | PO:COMMIT | 13296 | TERRACON CONSULTANTS, INC | 0 | 0 | 55500 | 0
ttJTrans | 0-4113 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4113 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4113 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4113 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4113 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4113 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4113 | EQ |  | EQ |  |  | 2026-04-30 |  | 0-4113 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4113 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4113 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4113 | EQ |  | EQ |  |  | 2026-05-03 |  | 0-4113 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4113 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4113 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4113 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4113 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4113 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4113 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4113 | ER |  | ER |  |  | 2026-04-30 |  | 0-4113 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4113 | ER |  | ER |  |  | 2026-04-30 |  | 0-4113 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4113 | ER |  | ER |  |  | 2026-04-30 |  | 0-4113 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4113 | ER |  | ER |  |  | 2026-04-30 |  | 0-4113 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 0-4113 | ER |  | ER |  |  | 2026-04-30 |  | 0-4113 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 0-4113 | LA |  | LA |  |  | 2026-04-30 |  | 0-4113 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 1705.23 | 0 | 30
ttJTrans | 0-4113 | LA |  | LA |  |  | 2026-04-30 |  | 0-4113 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 1705.23 | 0 | 30
ttJTrans | 0-4116 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4116 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4116 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4116 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4116 | EQ |  | EQ |  |  | 2026-05-10 |  | 0-4116 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4116 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4116 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4116 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4116 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4116 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4116 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4116 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4116 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4116 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4116 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4116 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4116 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4116 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4116 | FT011 JOHN DEERE 6130M TRACTOR W/ 620R LOADER JOHN DEERE 6130M TRACTOR W/ 620R LOADER | 0 | 0 |  | FT011 |  | 0 | 291.67 | 0 | 0
ttJTrans | 0-4116 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4116 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4116 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4116 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4116 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4116 | RT1385 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO 2024 RAM 2500 TRADESMAN GAS 4X4 CREW CAB 8FT BED W/ DRAGUP TANK & TOOLBOX COMBO | 0 | 0 |  | RT1385 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4116 | ER |  | ER |  |  | 2026-04-30 |  | 0-4116 | RMS2388 BUSH-HACKER 15' BRUSH CUTTER BUSH-HACKER 15' BRUSH CUTTER | 0 | 0 |  | RMS2388 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4116 | ER |  | ER |  |  | 2026-05-10 |  | 0-4116 | RMS2388 BUSH-HACKER 15' BRUSH CUTTER BUSH-HACKER 15' BRUSH CUTTER | 0 | 0 |  | RMS2388 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4116 | ER |  | ER |  |  | 2026-05-10 |  | 0-4116 | RMS2388 BUSH-HACKER 15' BRUSH CUTTER BUSH-HACKER 15' BRUSH CUTTER | 0 | 0 |  | RMS2388 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4116 | ER |  | ER |  |  | 2026-05-10 |  | 0-4116 | RMS2388 BUSH-HACKER 15' BRUSH CUTTER BUSH-HACKER 15' BRUSH CUTTER | 0 | 0 |  | RMS2388 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4116 | ER |  | ER |  |  | 2026-05-10 |  | 0-4116 | RPK500 CATERPILLAR 84" PADFOOT ROLLER CATERPILLAR 84" PADFOOT ROLLER | 0 | 0 |  | RPK500 |  | 0 | 340 | 0 | 0
ttJTrans | 0-4116 | ER |  | ER |  |  | 2026-05-17 |  | 0-4116 | RMS2388 BUSH-HACKER 15' BRUSH CUTTER BUSH-HACKER 15' BRUSH CUTTER | 0 | 0 |  | RMS2388 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4116 | ER |  | ER |  |  | 2026-05-17 |  | 0-4116 | RMS2388 BUSH-HACKER 15' BRUSH CUTTER BUSH-HACKER 15' BRUSH CUTTER | 0 | 0 |  | RMS2388 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4116 | ER |  | ER |  |  | 2026-05-17 |  | 0-4116 | RMS2388 BUSH-HACKER 15' BRUSH CUTTER BUSH-HACKER 15' BRUSH CUTTER | 0 | 0 |  | RMS2388 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4116 | ER |  | ER |  |  | 2026-05-17 |  | 0-4116 | RMS2388 BUSH-HACKER 15' BRUSH CUTTER BUSH-HACKER 15' BRUSH CUTTER | 0 | 0 |  | RMS2388 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4116 | ER |  | ER |  |  | 2026-05-17 |  | 0-4116 | RMS2388 BUSH-HACKER 15' BRUSH CUTTER BUSH-HACKER 15' BRUSH CUTTER | 0 | 0 |  | RMS2388 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4116 | ER |  | ER |  |  | 2026-05-17 |  | 0-4116 | RPK500 CATERPILLAR 84" PADFOOT ROLLER CATERPILLAR 84" PADFOOT ROLLER | 0 | 0 |  | RPK500 |  | 0 | 340 | 0 | 0
ttJTrans | 0-4116 | ER |  | ER |  |  | 2026-05-24 |  | 0-4116 | RMS2388 BUSH-HACKER 15' BRUSH CUTTER BUSH-HACKER 15' BRUSH CUTTER | 0 | 0 |  | RMS2388 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4116 | ER |  | ER |  |  | 2026-05-24 |  | 0-4116 | RMS2388 BUSH-HACKER 15' BRUSH CUTTER BUSH-HACKER 15' BRUSH CUTTER | 0 | 0 |  | RMS2388 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4116 | LA |  | LA |  |  | 2026-04-09 |  | 0-4116 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 410.68 | 0 | 10
ttJTrans | 0-4116 | LA |  | LA |  |  | 2026-04-16 |  | 0-4116 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 433.27 | 0 | 10
ttJTrans | 0-4116 | LA |  | LA |  |  | 2026-04-16 |  | 0-4116 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 647.3 | 0 | 10
ttJTrans | 0-4116 | LA |  | LA |  |  | 2026-04-16 |  | 0-4116 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 434.83 | 0 | 10
ttJTrans | 0-4116 | LA |  | LA |  |  | 2026-04-23 |  | 0-4116 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 680.6 | 0 | 16
ttJTrans | 0-4116 | LA |  | LA |  |  | 2026-05-08 |  | 0-4116 | COST CODE TRANSFER 25-4005 | 0 | 0 |  |  |  | 0 | -647.3 | 0 | -10
ttJTrans | 0-4116 | LA |  | LA |  |  | 2026-05-07 |  | 0-4116 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 391.13 | 0 | 10
ttJTrans | 0-4116 | LA |  | LA |  |  | 2026-05-07 |  | 0-4116 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 391.13 | 0 | 10
ttJTrans | 0-4116 | LA |  | LA |  |  | 2026-05-07 |  | 0-4116 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 709.24 | 0 | 10
ttJTrans | 0-4116 | LA |  | LA |  |  | 2026-05-07 |  | 0-4116 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 707.85 | 0 | 10
ttJTrans | 0-4116 | LA |  | LA |  |  | 2026-05-14 |  | 0-4116 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 581.08 | 0 | 10
ttJTrans | 0-4116 | LA |  | LA |  |  | 2026-05-14 |  | 0-4116 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 581.07 | 0 | 10
ttJTrans | 0-4116 | LA |  | LA |  |  | 2026-05-14 |  | 0-4116 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 391.13 | 0 | 10
ttJTrans | 0-4116 | LA |  | LA |  |  | 2026-05-14 |  | 0-4116 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 391.13 | 0 | 10
ttJTrans | 0-4116 | LA |  | LA |  |  | 2026-05-14 |  | 0-4116 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 391.13 | 0 | 10
ttJTrans | 0-4116 | LA |  | LA |  |  | 2026-05-14 |  | 0-4116 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 492.76 | 0 | 10
ttJTrans | 0-4116 | LA |  | LA |  |  | 2026-05-21 |  | 0-4116 | PR P0COST 000531 (PR) Summary | 0 | 0 |  |  |  | 0 | 1175.14 | 0 | 20
ttJTrans | 0-4116 | LA |  | LA |  |  | 2026-05-21 |  | 0-4116 | PR P0COST 000531 (PR) Summary | 0 | 0 |  |  |  | 0 | 2862.96 | 0 | 50
ttJTrans | 0-4121 | ER |  | ER |  |  | 2026-04-30 |  | 0-4121 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4121 | ER |  | ER |  |  | 2026-04-30 |  | 0-4121 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4121 | ER |  | ER |  |  | 2026-04-30 |  | 0-4121 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4121 | ER |  | ER |  |  | 2026-04-30 |  | 0-4121 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4121 | ER |  | ER |  |  | 2026-04-30 |  | 0-4121 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4121 | ER |  | ER |  |  | 2026-04-30 |  | 0-4121 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4121 | ER |  | ER |  |  | 2026-04-30 |  | 0-4121 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 0-4121 | ER |  | ER |  |  | 2026-05-10 |  | 0-4121 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4121 | ER |  | ER |  |  | 2026-04-30 |  | 0-4121 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4121 | ER |  | ER |  |  | 2026-04-30 |  | 0-4121 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4121 | ER |  | ER |  |  | 2026-04-30 |  | 0-4121 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4121 | ER |  | ER |  |  | 2026-04-30 |  | 0-4121 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4121 | ER |  | ER |  |  | 2026-04-30 |  | 0-4121 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4121 | ER |  | ER |  |  | 2026-04-30 |  | 0-4121 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4121 | ER |  | ER |  |  | 2026-04-30 |  | 0-4121 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4121 | ER |  | ER |  |  | 2026-04-30 |  | 0-4121 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 0-4121 | ER |  | ER |  |  | 2026-04-30 |  | 0-4121 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4121 | LA |  | LA |  |  | 2026-04-23 |  | 0-4121 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 1159.5 | 0 | 20
ttJTrans | 0-4121 | LA |  | LA |  |  | 2026-04-23 |  | 0-4121 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 1159.51 | 0 | 20
ttJTrans | 0-4121 | LA |  | LA |  |  | 2026-04-30 |  | 0-4121 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 993.54 | 0 | 20
ttJTrans | 0-4121 | LA |  | LA |  |  | 2026-04-30 |  | 0-4121 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 1414.61 | 0 | 30
ttJTrans | 0-4121 | LA |  | LA |  |  | 2026-04-30 |  | 0-4121 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 1414.61 | 0 | 30
ttJTrans | 0-4121 | LA |  | LA |  |  | 2026-04-30 |  | 0-4121 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 993.54 | 0 | 20
ttJTrans | 0-4121 | MA | MA1011245 | MA | MA1011245 | 46141 | 2026-05-20 | 1 | 0-4121 | AGGREGATE - LAYDOWN YARD AREAS - TXDOT BASE | 16000 | 759240 | INVOICE | 21358 | TEXAS GULF COAST AGGREGATES, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4121 | MA | MA1011245 | MA | MA1011245 | 46141 | 2026-05-07 | 1 | 0-4121 | AGGREGATE - LAYDOWN YARD AREAS - TXDOT BASE | 16000 | 759240 | PO:COMMIT | 21358 | TEXAS GULF COAST AGGREGATES, LLC | 0 | 0 | 759240 | 0
ttJTrans | 0-4121 | MA | MA1011245 | MA | MA1011245 | 46141 | 2026-05-07 | 1 | 0-4121 | AGGREGATE - LAYDOWN YARD AREAS - TXDOT BASE | 16000 | 759240 | INVOICE:ADJ-COMMIT | 21358 | TEXAS GULF COAST AGGREGATES, LLC | 0 | 0 | -162364.43 | 0
ttJTrans | 0-4121 | MA | MA1011507 | MA | MA1011507 | 46139 | 2026-04-27 | 1 | 0-4121 | 1X30'X24",16GA,GALVANIZED CMP, SOLID x30' | 30 | 1057.94 | PO:COMMIT | 15812 | CONSOLIDATED PIPE & SUPPLY CO. INC. | 1057.94 | 0 | 0 | 0
ttJTrans | 0-4121 | MA |  | MA |  |  | 2026-05-20 |  | 0-4121 | LIMESTONE | 0 | 0 |  | 21358 | TEXAS GULF COAST AGGREGATES, LLC | 0 | 156147.77 | 0 | 0
ttJTrans | 0-4121 | OC | MA1011507 | OC | MA1011507 | 46139 | 2026-04-27 | 2 | 0-4121 | FREIGHT | 1 | 832.5 | PO:COMMIT | 15812 | CONSOLIDATED PIPE & SUPPLY CO. INC. | 832.5 | 0 | 0 | 0
ttJTrans | 0-4122 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4122 | RT1423 2024 FORD F250 XL CREW CAB GAS 2024 FORD F250 XL CREW CAB GAS | 0 | 0 |  | RT1423 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4122 | EQ |  | EQ |  |  | 2026-03-29 |  | 0-4122 | RT1423 2024 FORD F250 XL CREW CAB GAS 2024 FORD F250 XL CREW CAB GAS | 0 | 0 |  | RT1423 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4122 | EQ |  | EQ |  |  | 2026-03-29 |  | 0-4122 | RT1423 2024 FORD F250 XL CREW CAB GAS 2024 FORD F250 XL CREW CAB GAS | 0 | 0 |  | RT1423 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4122 | EQ |  | EQ |  |  | 2026-03-29 |  | 0-4122 | RT1423 2024 FORD F250 XL CREW CAB GAS 2024 FORD F250 XL CREW CAB GAS | 0 | 0 |  | RT1423 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4122 | EQ |  | EQ |  |  | 2026-03-29 |  | 0-4122 | RT1423 2024 FORD F250 XL CREW CAB GAS 2024 FORD F250 XL CREW CAB GAS | 0 | 0 |  | RT1423 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4122 | EQ |  | EQ |  |  | 2026-03-29 |  | 0-4122 | RT1423 2024 FORD F250 XL CREW CAB GAS 2024 FORD F250 XL CREW CAB GAS | 0 | 0 |  | RT1423 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4122 | EQ |  | EQ |  |  | 2026-03-31 |  | 0-4122 | RT1423 2024 FORD F250 XL CREW CAB GAS 2024 FORD F250 XL CREW CAB GAS | 0 | 0 |  | RT1423 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4122 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4122 | RT1423 2024 FORD F250 XL CREW CAB GAS 2024 FORD F250 XL CREW CAB GAS | 0 | 0 |  | RT1423 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4122 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4122 | RT1423 2024 FORD F250 XL CREW CAB GAS 2024 FORD F250 XL CREW CAB GAS | 0 | 0 |  | RT1423 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4122 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4122 | RT1423 2024 FORD F250 XL CREW CAB GAS 2024 FORD F250 XL CREW CAB GAS | 0 | 0 |  | RT1423 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4122 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4122 | RT1423 2024 FORD F250 XL CREW CAB GAS 2024 FORD F250 XL CREW CAB GAS | 0 | 0 |  | RT1423 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4122 | EQ |  | EQ |  |  | 2026-03-22 |  | 0-4122 | RT1423 2024 FORD F250 XL CREW CAB GAS 2024 FORD F250 XL CREW CAB GAS | 0 | 0 |  | RT1423 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4122 | EQ |  | EQ |  |  | 2026-03-29 |  | 0-4122 | RT1423 2024 FORD F250 XL CREW CAB GAS 2024 FORD F250 XL CREW CAB GAS | 0 | 0 |  | RT1423 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4122 | EQ |  | EQ |  |  | 2026-03-15 |  | 0-4122 | RT1423 2024 FORD F250 XL CREW CAB GAS 2024 FORD F250 XL CREW CAB GAS | 0 | 0 |  | RT1423 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4122 | EQ |  | EQ |  |  | 2026-03-15 |  | 0-4122 | RT1423 2024 FORD F250 XL CREW CAB GAS 2024 FORD F250 XL CREW CAB GAS | 0 | 0 |  | RT1423 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4122 | EQ |  | EQ |  |  | 2026-03-15 |  | 0-4122 | RT1423 2024 FORD F250 XL CREW CAB GAS 2024 FORD F250 XL CREW CAB GAS | 0 | 0 |  | RT1423 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4122 | EQ |  | EQ |  |  | 2026-03-15 |  | 0-4122 | RT1423 2024 FORD F250 XL CREW CAB GAS 2024 FORD F250 XL CREW CAB GAS | 0 | 0 |  | RT1423 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4122 | EQ |  | EQ |  |  | 2026-03-15 |  | 0-4122 | RT1423 2024 FORD F250 XL CREW CAB GAS 2024 FORD F250 XL CREW CAB GAS | 0 | 0 |  | RT1423 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4122 | ER |  | ER |  |  | 2026-03-15 |  | 0-4122 | RMV34 2000 GAL WATER TRUCK 2000 GAL WATER TRUCK | 0 | 0 |  | RMV34 |  | 0 | 198.28 | 0 | 0
ttJTrans | 0-4122 | ER |  | ER |  |  | 2026-03-15 |  | 0-4122 | RMV34 2000 GAL WATER TRUCK 2000 GAL WATER TRUCK | 0 | 0 |  | RMV34 |  | 0 | 198.28 | 0 | 0
ttJTrans | 0-4122 | ER |  | ER |  |  | 2026-03-15 |  | 0-4122 | RMV34 2000 GAL WATER TRUCK 2000 GAL WATER TRUCK | 0 | 0 |  | RMV34 |  | 0 | 198.28 | 0 | 0
ttJTrans | 0-4122 | ER |  | ER |  |  | 2026-03-15 |  | 0-4122 | RMS2259 CORRECTION GROUP - IC-75 IHI MOROOKA CRAWLER CARRIER W/ VACUUM UNIT IC-75 IHI MOROOKA CRAWLER CARRIER W/ VACUUM UNIT | 0 | 0 |  | RMS2259 |  | 0 | 459.77 | 0 | 0
ttJTrans | 0-4122 | ER |  | ER |  |  | 2026-03-15 |  | 0-4122 | RMS2259 CORRECTION GROUP - IC-75 IHI MOROOKA CRAWLER CARRIER W/ VACUUM UNIT IC-75 IHI MOROOKA CRAWLER CARRIER W/ VACUUM UNIT | 0 | 0 |  | RMS2259 |  | 0 | 459.77 | 0 | 0
ttJTrans | 0-4122 | ER |  | ER |  |  | 2026-03-15 |  | 0-4122 | RMS2259 CORRECTION GROUP - IC-75 IHI MOROOKA CRAWLER CARRIER W/ VACUUM UNIT IC-75 IHI MOROOKA CRAWLER CARRIER W/ VACUUM UNIT | 0 | 0 |  | RMS2259 |  | 0 | 459.77 | 0 | 0
ttJTrans | 0-4122 | ER |  | ER |  |  | 2026-03-15 |  | 0-4122 | RMS2259 CORRECTION GROUP - IC-75 IHI MOROOKA CRAWLER CARRIER W/ VACUUM UNIT IC-75 IHI MOROOKA CRAWLER CARRIER W/ VACUUM UNIT | 0 | 0 |  | RMS2259 |  | 0 | 459.77 | 0 | 0
ttJTrans | 0-4122 | ER |  | ER |  |  | 2026-03-15 |  | 0-4122 | RMS2259 CORRECTION GROUP - IC-75 IHI MOROOKA CRAWLER CARRIER W/ VACUUM UNIT IC-75 IHI MOROOKA CRAWLER CARRIER W/ VACUUM UNIT | 0 | 0 |  | RMS2259 |  | 0 | 459.77 | 0 | 0
ttJTrans | 0-4122 | ER |  | ER |  |  | 2026-03-22 |  | 0-4122 | REX659 CATERPILLAR 315 TC EXCAVATOR CATERPILLAR 315 TC EXCAVATOR | 0 | 0 |  | REX659 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4122 | ER |  | ER |  |  | 2026-03-22 |  | 0-4122 | REX659 CATERPILLAR 315 TC EXCAVATOR CATERPILLAR 315 TC EXCAVATOR | 0 | 0 |  | REX659 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4122 | ER |  | ER |  |  | 2026-03-22 |  | 0-4122 | REX659 CATERPILLAR 315 TC EXCAVATOR CATERPILLAR 315 TC EXCAVATOR | 0 | 0 |  | REX659 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4122 | ER |  | ER |  |  | 2026-03-22 |  | 0-4122 | REX659 CATERPILLAR 315 TC EXCAVATOR CATERPILLAR 315 TC EXCAVATOR | 0 | 0 |  | REX659 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4122 | ER |  | ER |  |  | 2026-03-22 |  | 0-4122 | REX659 CATERPILLAR 315 TC EXCAVATOR CATERPILLAR 315 TC EXCAVATOR | 0 | 0 |  | REX659 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4122 | ER |  | ER |  |  | 2026-03-22 |  | 0-4122 | REX659 CATERPILLAR 315 TC EXCAVATOR CATERPILLAR 315 TC EXCAVATOR | 0 | 0 |  | REX659 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4122 | ER |  | ER |  |  | 2026-03-22 |  | 0-4122 | RMS2257 SKYJACK SJ1256TH FORKLIFT SKYJACK SJ1256TH FORKLIFT | 0 | 0 |  | RMS2257 |  | 0 | 270.83 | 0 | 0
ttJTrans | 0-4122 | ER |  | ER |  |  | 2026-03-22 |  | 0-4122 | RMS2257 SKYJACK SJ1256TH FORKLIFT SKYJACK SJ1256TH FORKLIFT | 0 | 0 |  | RMS2257 |  | 0 | 270.83 | 0 | 0
ttJTrans | 0-4122 | ER |  | ER |  |  | 2026-03-22 |  | 0-4122 | RMS2257 SKYJACK SJ1256TH FORKLIFT SKYJACK SJ1256TH FORKLIFT | 0 | 0 |  | RMS2257 |  | 0 | 270.83 | 0 | 0
ttJTrans | 0-4122 | ER |  | ER |  |  | 2026-03-22 |  | 0-4122 | RMS2257 SKYJACK SJ1256TH FORKLIFT SKYJACK SJ1256TH FORKLIFT | 0 | 0 |  | RMS2257 |  | 0 | 270.83 | 0 | 0
ttJTrans | 0-4122 | ER |  | ER |  |  | 2026-03-22 |  | 0-4122 | RMS2257 SKYJACK SJ1256TH FORKLIFT SKYJACK SJ1256TH FORKLIFT | 0 | 0 |  | RMS2257 |  | 0 | 270.83 | 0 | 0
ttJTrans | 0-4122 | ER |  | ER |  |  | 2026-03-22 |  | 0-4122 | RMS2257 SKYJACK SJ1256TH FORKLIFT SKYJACK SJ1256TH FORKLIFT | 0 | 0 |  | RMS2257 |  | 0 | 270.83 | 0 | 0
ttJTrans | 0-4122 | ER |  | ER |  |  | 2026-03-29 |  | 0-4122 | REX659 CATERPILLAR 315 TC EXCAVATOR CATERPILLAR 315 TC EXCAVATOR | 0 | 0 |  | REX659 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4122 | ER |  | ER |  |  | 2026-03-15 |  | 0-4122 | RMV34 2000 GAL WATER TRUCK 2000 GAL WATER TRUCK | 0 | 0 |  | RMV34 |  | 0 | 198.28 | 0 | 0
ttJTrans | 0-4122 | ER |  | ER |  |  | 2026-03-15 |  | 0-4122 | RMS2257 SKYJACK SJ1256TH FORKLIFT SKYJACK SJ1256TH FORKLIFT | 0 | 0 |  | RMS2257 |  | 0 | 270.83 | 0 | 0
ttJTrans | 0-4122 | ER |  | ER |  |  | 2026-03-15 |  | 0-4122 | REX659 CATERPILLAR 315 TC EXCAVATOR CATERPILLAR 315 TC EXCAVATOR | 0 | 0 |  | REX659 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4122 | ER |  | ER |  |  | 2026-03-15 |  | 0-4122 | RMS2257 SKYJACK SJ1256TH FORKLIFT SKYJACK SJ1256TH FORKLIFT | 0 | 0 |  | RMS2257 |  | 0 | 270.83 | 0 | 0
ttJTrans | 0-4122 | ER |  | ER |  |  | 2026-03-15 |  | 0-4122 | RMS2257 SKYJACK SJ1256TH FORKLIFT SKYJACK SJ1256TH FORKLIFT | 0 | 0 |  | RMS2257 |  | 0 | 270.83 | 0 | 0
ttJTrans | 0-4122 | ER |  | ER |  |  | 2026-03-15 |  | 0-4122 | RMS2257 SKYJACK SJ1256TH FORKLIFT SKYJACK SJ1256TH FORKLIFT | 0 | 0 |  | RMS2257 |  | 0 | 270.83 | 0 | 0
ttJTrans | 0-4122 | ER |  | ER |  |  | 2026-03-15 |  | 0-4122 | REX659 CATERPILLAR 315 TC EXCAVATOR CATERPILLAR 315 TC EXCAVATOR | 0 | 0 |  | REX659 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4122 | ER |  | ER |  |  | 2026-03-15 |  | 0-4122 | REX659 CATERPILLAR 315 TC EXCAVATOR CATERPILLAR 315 TC EXCAVATOR | 0 | 0 |  | REX659 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4122 | ER |  | ER |  |  | 2026-03-15 |  | 0-4122 | REX659 CATERPILLAR 315 TC EXCAVATOR CATERPILLAR 315 TC EXCAVATOR | 0 | 0 |  | REX659 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4122 | ER |  | ER |  |  | 2026-03-15 |  | 0-4122 | REX659 CATERPILLAR 315 TC EXCAVATOR CATERPILLAR 315 TC EXCAVATOR | 0 | 0 |  | REX659 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4122 | ER |  | ER |  |  | 2026-03-15 |  | 0-4122 | REX659 CATERPILLAR 315 TC EXCAVATOR CATERPILLAR 315 TC EXCAVATOR | 0 | 0 |  | REX659 |  | 0 | 250 | 0 | 0
ttJTrans | 0-4123 | ER |  | ER |  |  | 2026-05-17 |  | 0-4123 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4123 | ER |  | ER |  |  | 2026-05-10 |  | 0-4123 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4123 | ER |  | ER |  |  | 2026-05-10 |  | 0-4123 | RMS2388 BUSH-HACKER 15' BRUSH CUTTER BUSH-HACKER 15' BRUSH CUTTER | 0 | 0 |  | RMS2388 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4123 | ER |  | ER |  |  | 2026-05-24 |  | 0-4123 | RMS2388 BUSH-HACKER 15' BRUSH CUTTER BUSH-HACKER 15' BRUSH CUTTER | 0 | 0 |  | RMS2388 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4123 | ER |  | ER |  |  | 2026-05-17 |  | 0-4123 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4123 | ER |  | ER |  |  | 2026-05-17 |  | 0-4123 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4123 | ER |  | ER |  |  | 2026-05-17 |  | 0-4123 | RMS2388 BUSH-HACKER 15' BRUSH CUTTER BUSH-HACKER 15' BRUSH CUTTER | 0 | 0 |  | RMS2388 |  | 0 | 125 | 0 | 0
ttJTrans | 0-4123 | ER |  | ER |  |  | 2026-05-24 |  | 0-4123 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4123 | ER |  | ER |  |  | 2026-05-24 |  | 0-4123 | RHV96 PETERBILT 4,000 GALLON WATER TRUCK PETERBILT 4,000 GALLON WATER TRUCK | 0 | 0 |  | RHV96 |  | 0 | 200 | 0 | 0
ttJTrans | 0-4123 | LA |  | LA |  |  | 2026-05-14 |  | 0-4123 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 424.72 | 0 | 10
ttJTrans | 0-4123 | LA |  | LA |  |  | 2026-05-07 |  | 0-4123 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 424.72 | 0 | 10
ttJTrans | 0-4123 | LA |  | LA |  |  | 2026-05-07 |  | 0-4123 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 424.72 | 0 | 10
ttJTrans | 0-4123 | LA |  | LA |  |  | 2026-05-14 |  | 0-4123 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 630.81 | 0 | 10
ttJTrans | 0-4123 | LA |  | LA |  |  | 2026-05-14 |  | 0-4123 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 630.79 | 0 | 10
ttJTrans | 0-4123 | LA |  | LA |  |  | 2026-05-14 |  | 0-4123 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 424.72 | 0 | 10
ttJTrans | 0-4123 | LA |  | LA |  |  | 2026-05-21 |  | 0-4123 | PR P0COST 000531 (PR) Summary | 0 | 0 |  |  |  | 0 | 593.95 | 0 | 10
ttJTrans | 0-4125 | ER |  | ER |  |  | 2026-04-30 |  | 0-4125 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4125 | ER |  | ER |  |  | 2026-04-30 |  | 0-4125 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4125 | ER |  | ER |  |  | 2026-05-10 |  | 0-4125 | RAT439 CAN AM HD11XT CREW CAB UTV CAN AM HD11XT CREW CAB UTV | 0 | 0 |  | RAT439 |  | 0 | 62.5 | 0 | 0
ttJTrans | 0-4125 | ER |  | ER |  |  | 2026-05-24 |  | 0-4125 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 0-4125 | LA |  | LA |  |  | 2026-05-14 |  | 0-4125 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 982.71 | 0 | 20
ttJTrans | 0-4125 | LA |  | LA |  |  | 2026-04-30 |  | 0-4125 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 1032.06 | 0 | 20
ttJTrans | 0-4125 | LA |  | LA |  |  | 2026-04-30 |  | 0-4125 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 421.07 | 0 | 10
ttJTrans | 0-4125 | LA |  | LA |  |  | 2026-05-07 |  | 0-4125 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 916.63 | 0 | 20
ttJTrans | 0-4400 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4400 | RT1242 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS | 0 | 0 |  | RT1242 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4400 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4400 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4400 | EQ |  | EQ |  |  | 2026-05-17 |  | 0-4400 | RT1242 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS 2022 RAM 2500 TRADESMAN 4X4 CREW 8FT BED GAS | 0 | 0 |  | RT1242 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4400 | EQ |  | EQ |  |  | 2026-05-24 |  | 0-4400 | RT1344 2023 FORD F250 XL STX 4X4 DIESEL 2023 FORD F250 XL STX 4X4 DIESEL | 0 | 0 |  | RT1344 |  | 0 | 79.14 | 0 | 0
ttJTrans | 0-4400 | ER |  | ER |  |  | 2026-05-24 |  | 0-4400 | RLD0303 CATERPILLAR 950 WHEEL LOADER CATERPILLAR 950 WHEEL LOADER | 0 | 0 |  | RLD0303 |  | 0 | 437.5 | 0 | 0
ttJTrans | 0-4400 | ER |  | ER |  |  | 2026-05-24 |  | 0-4400 | RLD0303 CATERPILLAR 950 WHEEL LOADER CATERPILLAR 950 WHEEL LOADER | 0 | 0 |  | RLD0303 |  | 0 | 437.5 | 0 | 0
ttJTrans | 0-4400 | ER |  | ER |  |  | 2026-05-24 |  | 0-4400 | RLD0303 CATERPILLAR 950 WHEEL LOADER CATERPILLAR 950 WHEEL LOADER | 0 | 0 |  | RLD0303 |  | 0 | 437.5 | 0 | 0
ttJTrans | 0-4400 | ER |  | ER |  |  | 2026-05-17 |  | 0-4400 | RLD0303 CATERPILLAR 950 WHEEL LOADER CATERPILLAR 950 WHEEL LOADER | 0 | 0 |  | RLD0303 |  | 0 | 437.5 | 0 | 0
ttJTrans | 0-4400 | ER |  | ER |  |  | 2026-05-17 |  | 0-4400 | RLD0303 CATERPILLAR 950 WHEEL LOADER CATERPILLAR 950 WHEEL LOADER | 0 | 0 |  | RLD0303 |  | 0 | 437.5 | 0 | 0
ttJTrans | 0-4400 | ER |  | ER |  |  | 2026-05-17 |  | 0-4400 | RLD0303 CATERPILLAR 950 WHEEL LOADER CATERPILLAR 950 WHEEL LOADER | 0 | 0 |  | RLD0303 |  | 0 | 437.5 | 0 | 0
ttJTrans | 0-4400 | LA |  | LA |  |  | 2026-05-21 |  | 0-4400 | PR P0COST 000531 (PR) Summary | 0 | 0 |  |  |  | 0 | 907.66 | 0 | 20
ttJTrans | 0-4400 | LA |  | LA |  |  | 2026-05-07 |  | 0-4400 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 485.74 | 0 | 8
ttJTrans | 0-4400 | LA |  | LA |  |  | 2026-05-14 |  | 0-4400 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 1594.17 | 0 | 20
ttJTrans | 0-4400 | LA |  | LA |  |  | 2026-05-14 |  | 0-4400 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 893.84 | 0 | 16
ttJTrans | 0-4400 | LA |  | LA |  |  | 2026-05-14 |  | 0-4400 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 2013.2 | 0 | 46
ttJTrans | 0-4400 | LA |  | LA |  |  | 2026-05-14 |  | 0-4400 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 1238.87 | 0 | 26
ttJTrans | 0-4400 | LA |  | LA |  |  | 2026-05-14 |  | 0-4400 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 1683.38 | 0 | 30
ttJTrans | 0-4400 | LA |  | LA |  |  | 2026-05-14 |  | 0-4400 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 1489.49 | 0 | 40
ttJTrans | 0-4400 | LA |  | LA |  |  | 2026-05-14 |  | 0-4400 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 1131.91 | 0 | 30
ttJTrans | 0-4400 | LA |  | LA |  |  | 2026-05-21 |  | 0-4400 | PR P0COST 000531 (PR) Summary | 0 | 0 |  |  |  | 0 | 1254.2 | 0 | 20
ttJTrans | 0-4400 | LA |  | LA |  |  | 2026-05-21 |  | 0-4400 | PR P0COST 000531 (PR) Summary | 0 | 0 |  |  |  | 0 | 907.66 | 0 | 20
ttJTrans | 0-4400 | LA |  | LA |  |  | 2026-05-21 |  | 0-4400 | PR P0COST 000531 (PR) Summary | 0 | 0 |  |  |  | 0 | 1684.65 | 0 | 40
ttJTrans | 0-4414 | LA |  | LA |  |  | 2026-04-16 |  | 0-4414 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 423.59 | 0 | 10
ttJTrans | 0-4414 | LA |  | LA |  |  | 2026-04-23 |  | 0-4414 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 720.11 | 0 | 20
ttJTrans | 0-4414 | LA |  | LA |  |  | 2026-04-30 |  | 0-4414 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 1493.7 | 0 | 30
ttJTrans | 0-4414 | LA |  | LA |  |  | 2026-04-30 |  | 0-4414 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 296.52 | 0 | 10
ttJTrans | 0-4414 | LA |  | LA |  |  | 2026-05-08 |  | 0-4414 | COST CODE TRANSFER 25-4005 | 0 | 0 |  |  |  | 0 | -2287.4 | 0 | -40
ttJTrans | 0-4414 | LA |  | LA |  |  | 2026-05-07 |  | 0-4414 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 898.34 | 0 | 20
ttJTrans | 0-4414 | LA |  | LA |  |  | 2026-05-07 |  | 0-4414 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 898.34 | 0 | 20
ttJTrans | 0-4414 | LA |  | LA |  |  | 2026-05-14 |  | 0-4414 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 723.34 | 0 | 20
ttJTrans | 0-4414 | LA |  | LA |  |  | 2026-05-14 |  | 0-4414 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 723.34 | 0 | 20
ttJTrans | 0-4414 | LA |  | LA |  |  | 2026-04-23 |  | 0-4414 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 720.11 | 0 | 20
ttJTrans | 0-4414 | LA |  | LA |  |  | 2026-04-16 |  | 0-4414 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 423.59 | 0 | 10
ttJTrans | 0-4418 | LA |  | LA |  |  | 2026-04-02 |  | 0-4418 | PR P0COST 000524 (PR) Summary | 0 | 0 |  |  |  | 0 | 1023.95 | 0 | 20
ttJTrans | 0-4418 | LA |  | LA |  |  | 2026-04-09 |  | 0-4418 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 795.14 | 0 | 10
ttJTrans | 0-4418 | LA |  | LA |  |  | 2026-04-09 |  | 0-4418 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 534.59 | 0 | 10
ttJTrans | 0-4418 | LA |  | LA |  |  | 2026-04-09 |  | 0-4418 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 1338.57 | 0 | 20
ttJTrans | 0-4418 | LA |  | LA |  |  | 2026-04-09 |  | 0-4418 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 1338.57 | 0 | 20
ttJTrans | 0-4418 | LA |  | LA |  |  | 2026-04-09 |  | 0-4418 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 1338.58 | 0 | 20
ttJTrans | 0-4418 | LA |  | LA |  |  | 2026-04-09 |  | 0-4418 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 803.96 | 0 | 10
ttJTrans | 0-4418 | LA |  | LA |  |  | 2026-04-16 |  | 0-4418 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 795.14 | 0 | 10
ttJTrans | 0-4418 | LA |  | LA |  |  | 2026-04-16 |  | 0-4418 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 534.59 | 0 | 10
ttJTrans | 0-4418 | LA |  | LA |  |  | 2026-04-16 |  | 0-4418 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 534.59 | 0 | 10
ttJTrans | 0-4418 | LA |  | LA |  |  | 2026-04-16 |  | 0-4418 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 1177.78 | 0 | 20
ttJTrans | 0-4418 | LA |  | LA |  |  | 2026-04-16 |  | 0-4418 | PR P0COST 000526 (PR) Summary | 0 | 0 |  |  |  | 0 | 534.59 | 0 | 10
ttJTrans | 0-4418 | LA |  | LA |  |  | 2026-04-23 |  | 0-4418 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 588.74 | 0 | 10
ttJTrans | 0-4418 | LA |  | LA |  |  | 2026-04-23 |  | 0-4418 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 588.74 | 0 | 10
ttJTrans | 0-4418 | LA |  | LA |  |  | 2026-04-23 |  | 0-4418 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 588.74 | 0 | 10
ttJTrans | 0-4418 | LA |  | LA |  |  | 2026-04-23 |  | 0-4418 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 588.74 | 0 | 10
ttJTrans | 0-4418 | LA |  | LA |  |  | 2026-03-19 |  | 0-4418 | PR P0COST 000522 (PR) Summary | 0 | 0 |  |  |  | 0 | 390.14 | 0 | 10
ttJTrans | 0-4418 | LA |  | LA |  |  | 2026-04-02 |  | 0-4418 | PR P0COST 000524 (PR) Summary | 0 | 0 |  |  |  | 0 | 1023.98 | 0 | 20
ttJTrans | 0-4420 | LA |  | LA |  |  | 2026-05-08 |  | 0-4420 | COST CODE TRANSFER 25-4005 | 0 | 0 |  |  |  | 0 | -780.31 | 0 | -20
ttJTrans | 0-4420 | LA |  | LA |  |  | 2026-04-09 |  | 0-4420 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 390.16 | 0 | 10
ttJTrans | 0-4420 | LA |  | LA |  |  | 2026-04-09 |  | 0-4420 | PR P0COST 000525 (PR) Summary | 0 | 0 |  |  |  | 0 | 390.15 | 0 | 10
ttJTrans | 0-4500 | ER |  | ER |  |  | 2026-05-10 |  | 0-4500 | RTL1084 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1084 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4500 | ER |  | ER |  |  | 2026-05-10 |  | 0-4500 | RTL1085 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1085 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4500 | ER |  | ER |  |  | 2026-05-17 |  | 0-4500 | RTL1082 2023 PREMIER TRIPLEXING TRAILER 2023 PREMIER TRIPLEXING TRAILER | 0 | 0 |  | RTL1082 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4500 | ER |  | ER |  |  | 2026-05-17 |  | 0-4500 | RTL1083 2022 VELOCIWRAP TRIPLEXING TRAILER 2022 VELOCIWRAP TRIPLEXING TRAILER | 0 | 0 |  | RTL1083 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4500 | ER |  | ER |  |  | 2026-05-17 |  | 0-4500 | RTL1084 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1084 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4500 | ER |  | ER |  |  | 2026-05-17 |  | 0-4500 | RTL1085 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1085 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4500 | ER |  | ER |  |  | 2026-05-24 |  | 0-4500 | RTL1082 2023 PREMIER TRIPLEXING TRAILER 2023 PREMIER TRIPLEXING TRAILER | 0 | 0 |  | RTL1082 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4500 | ER |  | ER |  |  | 2026-05-24 |  | 0-4500 | RTL1083 2022 VELOCIWRAP TRIPLEXING TRAILER 2022 VELOCIWRAP TRIPLEXING TRAILER | 0 | 0 |  | RTL1083 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4500 | ER |  | ER |  |  | 2026-05-24 |  | 0-4500 | RTL1084 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1084 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4500 | ER |  | ER |  |  | 2026-05-24 |  | 0-4500 | RTL1085 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1085 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4500 | ER |  | ER |  |  | 2026-05-10 |  | 0-4500 | RTL1082 2023 PREMIER TRIPLEXING TRAILER 2023 PREMIER TRIPLEXING TRAILER | 0 | 0 |  | RTL1082 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4500 | ER |  | ER |  |  | 2026-05-10 |  | 0-4500 | RTL1083 2022 VELOCIWRAP TRIPLEXING TRAILER 2022 VELOCIWRAP TRIPLEXING TRAILER | 0 | 0 |  | RTL1083 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4500 | LA |  | LA |  |  | 2026-03-12 |  | 0-4500 | PR P0COST 000521 (PR) Summary | 0 | 0 |  |  |  | 0 | 889.77 | 0 | 10
ttJTrans | 0-4500 | LA |  | LA |  |  | 2026-03-12 |  | 0-4500 | PR P0COST 000521 (PR) Summary | 0 | 0 |  |  |  | 0 | 2401.44 | 0 | 40
ttJTrans | 0-4500 | LA |  | LA |  |  | 2026-05-08 |  | 0-4500 | COST CODE TRANSFER 25-4005 | 0 | 0 |  |  |  | 0 | -3291.21 | 0 | -50
ttJTrans | 0-4503 | ER |  | ER |  |  | 2026-05-10 |  | 0-4503 | RTL1085 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1085 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4503 | ER |  | ER |  |  | 2026-05-10 |  | 0-4503 | RTL1082 2023 PREMIER TRIPLEXING TRAILER 2023 PREMIER TRIPLEXING TRAILER | 0 | 0 |  | RTL1082 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4503 | ER |  | ER |  |  | 2026-05-10 |  | 0-4503 | RTL1083 2022 VELOCIWRAP TRIPLEXING TRAILER 2022 VELOCIWRAP TRIPLEXING TRAILER | 0 | 0 |  | RTL1083 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4503 | ER |  | ER |  |  | 2026-05-10 |  | 0-4503 | RTL1084 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1084 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4510 | MA | MA1011605 | MA | MA1011605 | 2026-05-12 | 2026-05-14 | 10 | 0-4510 | AMERICAN POLY AFT-16P4 - AFT AEROSOL FOAM | 52 | 5367.96 | PO:COMMIT | 18811 | CITY ELECTRIC SUPPLY CO. | 0 | 0 | 5367.96 | 0
ttJTrans | 0-4510 | MA | MA1011605 | MA | MA1011605 | 2026-05-12 | 2026-05-14 | 6 | 0-4510 | BURNDY YGHC26C2 - 1-2/0 TO 6-2 CU GRD C TAP | 100 | 924.63 | PO:COMMIT | 18811 | CITY ELECTRIC SUPPLY CO. | 0 | 0 | 924.63 | 0
ttJTrans | 0-4510 | MA | MA1011605 | MA | MA1011605 | 2026-05-12 | 2026-05-14 | 7 | 0-4510 | BURNDY YGLR29C34 - 2-250 GRD GRID TO 3/4 RO | 100 | 6805.41 | PO:COMMIT | 18811 | CITY ELECTRIC SUPPLY CO. | 0 | 0 | 6805.41 | 0
ttJTrans | 0-4510 | MA | MA1011605 | MA | MA1011605 | 2026-05-12 | 2026-05-14 | 5 | 0-4510 | BURNDY YGHC29C26 - 3/0-250 TO 6-2/0 CU COMP | 100 | 1195.47 | PO:COMMIT | 18811 | CITY ELECTRIC SUPPLY CO. | 0 | 0 | 1195.47 | 0
ttJTrans | 0-4510 | MA | MA1011605 | MA | MA1011605 | 2026-05-12 | 2026-05-14 | 3 | 0-4510 | UGTAPE3 - 3" NON- DETECT RED ELECT CAUSTION | 70 | 1933.18 | PO:COMMIT | 18811 | CITY ELECTRIC SUPPLY CO. | 0 | 0 | 1933.18 | 0
ttJTrans | 0-4510 | MA | MA1011605 | MA | MA1011605 | 2026-05-12 | 2026-05-14 | 4 | 0-4510 | BURNDY YGHC29C29 - GROUNDING CRIMP | 100 | 1283.16 | PO:COMMIT | 18811 | CITY ELECTRIC SUPPLY CO. | 0 | 0 | 1283.16 | 0
ttJTrans | 0-4510 | MA | MA1011605 | MA | MA1011605 | 2026-05-12 | 2026-05-14 | 2 | 0-4510 | 3M EC-3 - COLD SHRINK END CAPS ** SHIP | 60 | 1068.26 | PO:COMMIT | 18811 | CITY ELECTRIC SUPPLY CO. | 0 | 0 | 1068.26 | 0
ttJTrans | 0-4510 | MA | MA1011605 | MA | MA1011605 | 2026-05-12 | 2026-05-14 | 9 | 0-4510 | DBTAPE6 - 6" DETECT RED ELECT CAUTION TAPE | 7 | 723.15 | PO:COMMIT | 18811 | CITY ELECTRIC SUPPLY CO. | 0 | 0 | 723.15 | 0
ttJTrans | 0-4510 | MA | MA1011605 | MA | MA1011605 | 2026-05-12 | 2026-05-14 | 11 | 0-4510 | CSJ-SR-3513M5 4/0 SPLICES W/SEARBOLTS | 5 | 4414.75 | PO:COMMIT | 18811 | CITY ELECTRIC SUPPLY CO. | 0 | 0 | 4414.75 | 0
ttJTrans | 0-4510 | MA | MA1011605 | MA | MA1011605 | 2026-05-12 | 2026-05-14 | 8 | 0-4510 | CSJ-SR-3515M10 1250 SPLICES W/SEARBOLT | 34 | 46917.61 | PO:COMMIT | 18811 | CITY ELECTRIC SUPPLY CO. | 0 | 0 | 96595.09 | 0
ttJTrans | 0-4510 | MA | MA1011605 | MA | MA1011605 | 2026-05-12 | 2026-05-14 | 8 | 0-4510 | CSJ-SR-3515M10 1250 SPLICES W/SEARBOLT | 34 | 46917.61 | PO:COMMIT | 18811 | CITY ELECTRIC SUPPLY CO. | 0 | 0 | -49677.48 | 0
ttJTrans | 0-4510 | MA | MA1011605 | MA | MA1011605 | 2026-05-12 | 2026-05-14 | 12 | 0-4510 | GR3/4X10CU - GROUND ROD | 60 | 1945.39 | PO:COMMIT | 18811 | CITY ELECTRIC SUPPLY CO. | 0 | 0 | 1945.39 | 0
ttJTrans | 0-4510 | MA | MA1011605 | MA | MA1011605 | 2026-05-12 | 2026-05-14 | 1 | 0-4510 | 3M EC-4 - COLD SHRINK END CAPS ** SHIP 6/5/26 | 2000 | 46908.6 | PO:COMMIT | 18811 | CITY ELECTRIC SUPPLY CO. | 0 | 0 | 46908.6 | 0
ttJTrans | 0-4510 | MA | MA1011868 | MA | MA1011868 | 46164 | 2026-05-25 | 1 | 0-4510 | 3M 5468A(L)-20SB-Al-WF - 1250 KCMIL Splice | 36 | 54063.48 | PO:COMMIT | 19193 | CRAWFORD ELECTRIC SUPPLY CO., INC. | 54063.48 | 0 | 0 | 0
ttJTrans | 0-4510 | OC | MA1010991 | OC | MA1010991 | 46118 | 2026-04-06 | 1 | 0-4510 | MEGGER | 1 | 304.7 | INVOICE:ADJ-ACCRUAL | 19386 | TECHNICAL DIAGNOSTIC SERVICES, LLC | -304.7 | 0 | 0 | 0
ttJTrans | 0-4510 | OC | MA1010991 | OC | MA1010991 | 46118 | 2026-04-06 | 1 | 0-4510 | MEGGER | 1 | 304.7 | PO:COMMIT | 19386 | TECHNICAL DIAGNOSTIC SERVICES, LLC | 0 | 0 | 304.7 | 0
ttJTrans | 0-4510 | OC | MA1010991 | OC | MA1010991 | 46118 | 2026-05-11 | 1 | 0-4510 | MEGGER | 1 | 304.7 | INVOICE | 19386 | TECHNICAL DIAGNOSTIC SERVICES, LLC | 0 | 0 | 0 | 0
ttJTrans | 0-4510 | OC | MA1011868 | OC | MA1011868 | 46164 | 2026-05-25 | 2 | 0-4510 | Freight invoice 211710 | 1 | 305.01 | PO:COMMIT | 19193 | CRAWFORD ELECTRIC SUPPLY CO., INC. | 0 | 0 | 305.01 | 0
ttJTrans | 0-4510 | OC |  | OC |  |  | 2026-05-11 |  | 0-4510 | CALIBRATION OF MEGGER MIT1525 | 0 | 0 |  | 19386 | TDS RENTALS & LEASING, LLC | 0 | 274.5 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-24 |  | 0-4520 | RTL1085 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1085 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-10 |  | 0-4520 | RTL1082 2023 PREMIER TRIPLEXING TRAILER 2023 PREMIER TRIPLEXING TRAILER | 0 | 0 |  | RTL1082 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-10 |  | 0-4520 | RTL1082 2023 PREMIER TRIPLEXING TRAILER 2023 PREMIER TRIPLEXING TRAILER | 0 | 0 |  | RTL1082 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-10 |  | 0-4520 | RTL1082 2023 PREMIER TRIPLEXING TRAILER 2023 PREMIER TRIPLEXING TRAILER | 0 | 0 |  | RTL1082 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-10 |  | 0-4520 | RTL1082 2023 PREMIER TRIPLEXING TRAILER 2023 PREMIER TRIPLEXING TRAILER | 0 | 0 |  | RTL1082 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-10 |  | 0-4520 | RTL1083 2022 VELOCIWRAP TRIPLEXING TRAILER 2022 VELOCIWRAP TRIPLEXING TRAILER | 0 | 0 |  | RTL1083 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-10 |  | 0-4520 | RTL1083 2022 VELOCIWRAP TRIPLEXING TRAILER 2022 VELOCIWRAP TRIPLEXING TRAILER | 0 | 0 |  | RTL1083 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-10 |  | 0-4520 | RTL1083 2022 VELOCIWRAP TRIPLEXING TRAILER 2022 VELOCIWRAP TRIPLEXING TRAILER | 0 | 0 |  | RTL1083 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-10 |  | 0-4520 | RTL1083 2022 VELOCIWRAP TRIPLEXING TRAILER 2022 VELOCIWRAP TRIPLEXING TRAILER | 0 | 0 |  | RTL1083 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-10 |  | 0-4520 | RTL1084 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1084 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-10 |  | 0-4520 | RTL1084 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1084 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-10 |  | 0-4520 | RTL1084 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1084 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-10 |  | 0-4520 | RTL1084 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1084 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-10 |  | 0-4520 | RTL1085 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1085 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-10 |  | 0-4520 | RTL1085 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1085 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-10 |  | 0-4520 | RTL1085 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1085 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-10 |  | 0-4520 | RTL1085 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1085 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-17 |  | 0-4520 | RTL1082 2023 PREMIER TRIPLEXING TRAILER 2023 PREMIER TRIPLEXING TRAILER | 0 | 0 |  | RTL1082 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-17 |  | 0-4520 | RTL1082 2023 PREMIER TRIPLEXING TRAILER 2023 PREMIER TRIPLEXING TRAILER | 0 | 0 |  | RTL1082 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-17 |  | 0-4520 | RTL1082 2023 PREMIER TRIPLEXING TRAILER 2023 PREMIER TRIPLEXING TRAILER | 0 | 0 |  | RTL1082 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-17 |  | 0-4520 | RTL1082 2023 PREMIER TRIPLEXING TRAILER 2023 PREMIER TRIPLEXING TRAILER | 0 | 0 |  | RTL1082 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-17 |  | 0-4520 | RTL1082 2023 PREMIER TRIPLEXING TRAILER 2023 PREMIER TRIPLEXING TRAILER | 0 | 0 |  | RTL1082 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-17 |  | 0-4520 | RTL1083 2022 VELOCIWRAP TRIPLEXING TRAILER 2022 VELOCIWRAP TRIPLEXING TRAILER | 0 | 0 |  | RTL1083 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-17 |  | 0-4520 | RTL1083 2022 VELOCIWRAP TRIPLEXING TRAILER 2022 VELOCIWRAP TRIPLEXING TRAILER | 0 | 0 |  | RTL1083 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-17 |  | 0-4520 | RTL1083 2022 VELOCIWRAP TRIPLEXING TRAILER 2022 VELOCIWRAP TRIPLEXING TRAILER | 0 | 0 |  | RTL1083 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-17 |  | 0-4520 | RTL1083 2022 VELOCIWRAP TRIPLEXING TRAILER 2022 VELOCIWRAP TRIPLEXING TRAILER | 0 | 0 |  | RTL1083 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-17 |  | 0-4520 | RTL1083 2022 VELOCIWRAP TRIPLEXING TRAILER 2022 VELOCIWRAP TRIPLEXING TRAILER | 0 | 0 |  | RTL1083 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-17 |  | 0-4520 | RTL1084 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1084 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-17 |  | 0-4520 | RTL1084 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1084 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-17 |  | 0-4520 | RTL1084 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1084 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-17 |  | 0-4520 | RTL1084 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1084 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-17 |  | 0-4520 | RTL1084 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1084 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-17 |  | 0-4520 | RTL1085 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1085 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-17 |  | 0-4520 | RTL1085 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1085 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-17 |  | 0-4520 | RTL1085 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1085 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-17 |  | 0-4520 | RTL1085 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1085 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-17 |  | 0-4520 | RTL1085 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1085 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-24 |  | 0-4520 | RTL1082 2023 PREMIER TRIPLEXING TRAILER 2023 PREMIER TRIPLEXING TRAILER | 0 | 0 |  | RTL1082 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-24 |  | 0-4520 | RTL1082 2023 PREMIER TRIPLEXING TRAILER 2023 PREMIER TRIPLEXING TRAILER | 0 | 0 |  | RTL1082 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-24 |  | 0-4520 | RTL1082 2023 PREMIER TRIPLEXING TRAILER 2023 PREMIER TRIPLEXING TRAILER | 0 | 0 |  | RTL1082 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-24 |  | 0-4520 | RTL1082 2023 PREMIER TRIPLEXING TRAILER 2023 PREMIER TRIPLEXING TRAILER | 0 | 0 |  | RTL1082 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-24 |  | 0-4520 | RTL1082 2023 PREMIER TRIPLEXING TRAILER 2023 PREMIER TRIPLEXING TRAILER | 0 | 0 |  | RTL1082 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-24 |  | 0-4520 | RTL1083 2022 VELOCIWRAP TRIPLEXING TRAILER 2022 VELOCIWRAP TRIPLEXING TRAILER | 0 | 0 |  | RTL1083 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-24 |  | 0-4520 | RTL1083 2022 VELOCIWRAP TRIPLEXING TRAILER 2022 VELOCIWRAP TRIPLEXING TRAILER | 0 | 0 |  | RTL1083 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-24 |  | 0-4520 | RTL1083 2022 VELOCIWRAP TRIPLEXING TRAILER 2022 VELOCIWRAP TRIPLEXING TRAILER | 0 | 0 |  | RTL1083 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-24 |  | 0-4520 | RTL1083 2022 VELOCIWRAP TRIPLEXING TRAILER 2022 VELOCIWRAP TRIPLEXING TRAILER | 0 | 0 |  | RTL1083 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-24 |  | 0-4520 | RTL1083 2022 VELOCIWRAP TRIPLEXING TRAILER 2022 VELOCIWRAP TRIPLEXING TRAILER | 0 | 0 |  | RTL1083 |  | 0 | 65 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-24 |  | 0-4520 | RTL1084 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1084 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-24 |  | 0-4520 | RTL1084 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1084 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-24 |  | 0-4520 | RTL1084 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1084 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-24 |  | 0-4520 | RTL1084 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1084 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-24 |  | 0-4520 | RTL1084 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1084 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-24 |  | 0-4520 | RTL1085 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1085 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-24 |  | 0-4520 | RTL1085 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1085 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-24 |  | 0-4520 | RTL1085 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1085 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4520 | ER |  | ER |  |  | 2026-05-24 |  | 0-4520 | RTL1085 2022 VELOCIWRAP CABLE WRAPPER 2022 VELOCIWRAP CABLE WRAPPER | 0 | 0 |  | RTL1085 |  | 0 | 330.46 | 0 | 0
ttJTrans | 0-4701 | LA |  | LA |  |  | 2026-04-23 |  | 0-4701 | PR P0COST 000527 (PR) Summary | 0 | 0 |  |  |  | 0 | 433.5 | 0 | 8
ttJTrans | 0-4701 | LA |  | LA |  |  | 2026-04-30 |  | 0-4701 | PR P0COST 000528 (PR) Summary | 0 | 0 |  |  |  | 0 | 640.41 | 0 | 9.01
ttJTrans | 0-4999 | OC |  | OC |  |  | 2026-02-11 |  | 0-4999 | 260100618,LYLE MACHINERY,FREIGHT,11/12/25,P63489 | 0 | 0 |  |  |  | 0 | 386.06 | 0 | 0
ttJTrans | 0-4999 | OC |  | OC |  |  | 2026-04-28 |  | 0-4999 | COMDATA 4/20/26 (SW) WHARTON TRACTOR COMPAN 4/14/26 | 0 | 0 |  | 2294 |  | 0 | 649.79 | 0 | 0
ttJTrans | 2-4004 | SU | SO1000325 | SU | SO1000325 | 46119 | 2026-04-10 | 1 | 2-4004 | ENGINEERING | 1 | 228978.75 | PO:COMMIT | 20428 | KLS POWER CONSULTING, PLLC | 0 | 0 | 228978.75 | 0
ttJTrans | 2-4004 | SU | SO1000338 | SU | SO1000338 | 46125 | 2026-04-15 | 1 | 2-4004 | FENCING | 1 | 39764.38 | PO:COMMIT | 20603 | KAY SERVICES, INC. | 0 | 0 | 39764.38 | 0
ttJTrans | 2-4205 | EQ |  | EQ |  |  | 2026-05-24 |  | 2-4205 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 2-4205 | EQ |  | EQ |  |  | 2026-05-24 |  | 2-4205 | RT1447 2024 FORD F250 XL STX CREW CAB DIESEL SWB 2024 FORD F250 XL STX CREW CAB DIESEL SWB | 0 | 0 |  | RT1447 |  | 0 | 79.14 | 0 | 0
ttJTrans | 2-4205 | ER |  | ER |  |  | 2026-05-10 |  | 2-4205 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 2-4205 | ER |  | ER |  |  | 2026-05-10 |  | 2-4205 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 2-4205 | ER |  | ER |  |  | 2026-05-24 |  | 2-4205 | RPK500 CATERPILLAR 84" PADFOOT ROLLER CATERPILLAR 84" PADFOOT ROLLER | 0 | 0 |  | RPK500 |  | 0 | 340 | 0 | 0
ttJTrans | 2-4205 | ER |  | ER |  |  | 2026-05-24 |  | 2-4205 | RPK500 CATERPILLAR 84" PADFOOT ROLLER CATERPILLAR 84" PADFOOT ROLLER | 0 | 0 |  | RPK500 |  | 0 | 340 | 0 | 0
ttJTrans | 2-4205 | ER |  | ER |  |  | 2026-05-24 |  | 2-4205 | RPK500 CATERPILLAR 84" PADFOOT ROLLER CATERPILLAR 84" PADFOOT ROLLER | 0 | 0 |  | RPK500 |  | 0 | 340 | 0 | 0
ttJTrans | 2-4205 | ER |  | ER |  |  | 2026-05-24 |  | 2-4205 | RPK500 CATERPILLAR 84" PADFOOT ROLLER CATERPILLAR 84" PADFOOT ROLLER | 0 | 0 |  | RPK500 |  | 0 | 340 | 0 | 0
ttJTrans | 2-4205 | ER |  | ER |  |  | 2026-05-24 |  | 2-4205 | RPK500 CATERPILLAR 84" PADFOOT ROLLER CATERPILLAR 84" PADFOOT ROLLER | 0 | 0 |  | RPK500 |  | 0 | 340 | 0 | 0
ttJTrans | 2-4205 | ER |  | ER |  |  | 2026-05-24 |  | 2-4205 | RPK500 CATERPILLAR 84" PADFOOT ROLLER CATERPILLAR 84" PADFOOT ROLLER | 0 | 0 |  | RPK500 |  | 0 | 340 | 0 | 0
ttJTrans | 2-4205 | ER |  | ER |  |  | 2026-05-17 |  | 2-4205 | RPK500 CATERPILLAR 84" PADFOOT ROLLER CATERPILLAR 84" PADFOOT ROLLER | 0 | 0 |  | RPK500 |  | 0 | 340 | 0 | 0
ttJTrans | 2-4205 | ER |  | ER |  |  | 2026-05-17 |  | 2-4205 | RPK500 CATERPILLAR 84" PADFOOT ROLLER CATERPILLAR 84" PADFOOT ROLLER | 0 | 0 |  | RPK500 |  | 0 | 340 | 0 | 0
ttJTrans | 2-4205 | ER |  | ER |  |  | 2026-05-17 |  | 2-4205 | RPK500 CATERPILLAR 84" PADFOOT ROLLER CATERPILLAR 84" PADFOOT ROLLER | 0 | 0 |  | RPK500 |  | 0 | 340 | 0 | 0
ttJTrans | 2-4205 | ER |  | ER |  |  | 2026-05-17 |  | 2-4205 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 2-4205 | ER |  | ER |  |  | 2026-05-17 |  | 2-4205 | RPK482 HAMM 84' SINGLE DRUM ROLLER HAMM 84' SINGLE DRUM ROLLER | 0 | 0 |  | RPK482 |  | 0 | 300 | 0 | 0
ttJTrans | 2-4205 | ER |  | ER |  |  | 2026-05-17 |  | 2-4205 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 2-4205 | ER |  | ER |  |  | 2026-05-17 |  | 2-4205 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 2-4205 | ER |  | ER |  |  | 2026-05-17 |  | 2-4205 | RDZ318 CAT D5 LGPVPR DOZER 170 HP CAT D5 LGPVPR DOZER 170 HP | 0 | 0 |  | RDZ318 |  | 0 | 778.74 | 0 | 0
ttJTrans | 2-4205 | ER |  | ER |  |  | 2026-05-10 |  | 2-4205 | RPK500 CATERPILLAR 84" PADFOOT ROLLER CATERPILLAR 84" PADFOOT ROLLER | 0 | 0 |  | RPK500 |  | 0 | 340 | 0 | 0
ttJTrans | 2-4205 | ER |  | ER |  |  | 2026-05-10 |  | 2-4205 | RMS2317 TRIMBLE TD540 TOTAL STATING TRIMBLE TD540 TOTAL STATING | 0 | 0 |  | RMS2317 |  | 0 | 287.36 | 0 | 0
ttJTrans | 2-4205 | LA |  | LA |  |  | 2026-05-21 |  | 2-4205 | PR P0COST 000531 (PR) Summary | 0 | 0 |  |  |  | 0 | 3299.17 | 0 | 60
ttJTrans | 2-4205 | LA |  | LA |  |  | 2026-05-07 |  | 2-4205 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 1344.92 | 0 | 30
ttJTrans | 2-4205 | LA |  | LA |  |  | 2026-05-07 |  | 2-4205 | PR P0COST 000529 (PR) Summary | 0 | 0 |  |  |  | 0 | 383.66 | 0 | 10
ttJTrans | 2-4205 | LA |  | LA |  |  | 2026-05-14 |  | 2-4205 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 2381.39 | 0 | 40
ttJTrans | 2-4205 | LA |  | LA |  |  | 2026-05-14 |  | 2-4205 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 1241.07 | 0 | 20
ttJTrans | 2-4205 | LA |  | LA |  |  | 2026-05-14 |  | 2-4205 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 861.49 | 0 | 20
ttJTrans | 2-4205 | LA |  | LA |  |  | 2026-05-14 |  | 2-4205 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 861.49 | 0 | 20
ttJTrans | 2-4205 | LA |  | LA |  |  | 2026-05-14 |  | 2-4205 | PR P0COST 000530 (PR) Summary | 0 | 0 |  |  |  | 0 | 861.49 | 0 | 20
ttJTrans | 2-4205 | LA |  | LA |  |  | 2026-05-21 |  | 2-4205 | PR P0COST 000531 (PR) Summary | 0 | 0 |  |  |  | 0 | 4759.41 | 0 | 85
ttJTrans | 2-4205 | MA | MA1011245 | MA | MA1011245 | 46141 | 2026-05-07 | 3 | 2-4205 | SELECT FILL - SUBSTATION PAD | 40000 | 477300 | PO:COMMIT | 21358 | TEXAS GULF COAST AGGREGATES, LLC | 0 | 0 | 477300 | 0
ttJTrans | 2-4209 | ER |  | ER |  |  | 2026-05-10 |  | 2-4209 | RGR114 CATERPILLAR 150 AWD MOTOR GRADER CATERPILLAR 150 AWD MOTOR GRADER | 0 | 0 |  | RGR114 |  | 0 | 604.17 | 0 | 0
ttJTrans | 2-4209 | ER |  | ER |  |  | 2026-05-10 |  | 2-4209 | REX665 330 CATERPILLAR EXCAVATOR 330 CATERPILLAR EXCAVATOR | 0 | 0 |  | REX665 |  | 0 | 458.33 | 0 | 0
ttJTrans | 2-4209 | MA | MA1011242 | MA | MA1011242 | 46127 | 2026-04-15 | 2 | 2-4209 | 24IN PAIRS 6:1 GALV END TREATM | 3 | 2014.65 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 2014.65 | 0
ttJTrans | 2-4209 | MA | MA1011242 | MA | MA1011242 | 46127 | 2026-04-15 | 3 | 2-4209 | 24IN GALV BANDS | 6 | 599.4 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 599.4 | 0
ttJTrans | 2-4209 | MA | MA1011242 | MA | MA1011242 | 46127 | 2026-04-15 | 1 | 2-4209 | 24IN X 30FT GALVANIZED CMP | 3 | 3496.5 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 3496.5 | 0
ttJTrans | 2-4209 | MA | MA1011245 | MA | MA1011245 | 46141 | 2026-05-07 | 2 | 2-4209 | AGGREGATE - SUBSTAITON ROADS - TXDOT BASE | 5000 | 237262.5 | PO:COMMIT | 21358 | TEXAS GULF COAST AGGREGATES, LLC | 0 | 0 | 237262.5 | 0
ttJTrans | 2-4209 | OC | MA1011242 | OC | MA1011242 | 46127 | 2026-04-15 | 4 | 2-4209 | FREIGHT | 1 | 666 | PO:COMMIT | 12561 | CROSS COUNTRY INFRASTRUCTURE SERVICES INC. | 0 | 0 | 666 | 0
ttJTrans | 2-4209 | OC |  | OC |  |  | 2026-04-01 |  | 2-4209 | SUNROPER LLC SUBSTATION 6922 S SH 60 HWY | 0 | 0 |  | 21409 | COUNTY OF WHARTON | 0 | 500 | 0 | 0
Note on T188: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Delete these hrs